## Dashboard_30s
PROJECT COST IN 30 SECONDS
Inputs
Project | KSA Project
Budget (SAR) | 70000000
As of | 2026-01-28
KPI | Value
Actual (SAR) | 17896030.49
Committed (SAR) | 41596507.79
Exposure (Actual + Committed) | 59492538.28
Budget Remaining | 10507461.72
Budget Used % | 84.99%
Overrun Risk | 0
Net Discounts / Credits | 1013922.24
Burn Rate (Actual last 30 days) | 4099089.88
Top 8 Cost Codes by Exposure
Rank | Cost Code | Actual | Committed | Exposure | Used | 59492538.28
1 | KSA-000084 | 0 | 15303365.08 | 15303365.08 | Remaining | 10507461.72
2 | KSA-000084 | 0 | 15303365.08 | 15303365.08
3 | Cost-000001 | 1990974.22 | 9916028.26 | 11907002.48
4 | KSA-000084 | 4385321.82 | 4923085.98 | 9308407.8
5 | Cost-000133 | 2752370.83 | 975713.49 | 3728084.32
6 | Cost-000001 | 1444557.35 | 2210516.59 | 3655073.94
7 | Cost-000133 | 2663050.6 | 853605 | 3516655.6
8 | KSA-000084 | 2802725.39 | 694534.75 | 3497260.14
Cost Center Breakdown (Exposure)
Cost Center | Actual | Committed | Exposure
Materials | 149645.83 | 65831.01 | 215476.84
Services | 1898224.08 | 1052095.77 | 2950319.85
Equipment / Plant | 101653.55 | 34121.58 | 135775.13
Subcontractor / Manpower | 9782763.28 | 39736001.34 | 49518764.62
Permits / Government Fees | 188052 | 0 | 188052
Materials / Misc | 623037.81 | 708458.09 | 1331495.9
Other | 5152653.94 | 0 | 5152653.94

## Map_Category
Category | CostCenterBucket (edit) | Example Item Name
Mat013100-003SEV | Materials / Misc | Facility Services Coordination
Mat013500-010SEV | Materials / Misc | Owner Safety Requirements
Mat013500-023SEV | Materials / Misc | Period Treatment Procedures
Mat013700-003SEV | Materials / Misc | Property Insurance
Mat014000-003SEV | Equipment / Plant | Electrical Tools
Mat014000-004SEV | Equipment / Plant | Hand Tools
Mat014100-008SEV | Materials / Misc | Employee Accommodation
Mat014100-009SEV | Materials / Misc | Employee Food
Mat014100-011SEV | Services | Employee Transportation
Mat014100-017SEV | Subcontractor / Manpower | Manpower Rental
Mat014100-018SEV | Services | Project Security
Mat014300-011SEV | Materials / Misc | Safety Training
Mat014300-012SEV | Services | Safety 3rd Party Testing
Mat014300-014SEV | Equipment / Plant | Saftey Tools
Mat014500-005SEV | Services | Testing And Inspecting Services
Mat014500-007SEV | Services | Testing Laboratory Services
Mat015200-001SEV | Materials / Misc | Construction Facilities
Mat015400-005SEV | Materials / Misc | Temporary Scaffolding And Platforms
Mat015700-003SEV | Materials / Misc | Temporary Pest Control
Mat016500-001SEV | Materials / Misc | Product Delivery Requirements
Mat016500-002SEV | Services | Materials Transportation
Mat017100-002SEV | Materials / Misc | Mobilization
Mat017100-003SEV | Materials / Misc | Site Mobilization
Mat017100-004SEV | Materials / Misc | Site Accommodation
Mat017100-015SEV | Materials / Misc | Staff Accommodation
Mat017100-016SEV | Services | Labour Accommodation
Mat017100-018SEV | Materials / Misc | Demobalization
Mat017400-001SEV | Materials / Misc | Cleaning And Waste Management
Mat017400-004SEV | Materials / Misc | Construction Waste Management And Disposal
Mat017800-012SEV | Materials / Misc | Spare Parts
Mat017800-020SEV | Permits / Government Fees | Permits and Licenses
Mat018500-004SEV | Materials | Diesel
Mat018500-010SEV | Services | Equipment Rental
Mat018900-004SEV | Materials / Misc | Site Plumbing Utilities Performance Requirements
Mat019300-004SEV | Materials / Misc | Maintenance Fees
SEC-011000 | Subcontractor / Manpower | Summary Of Work
SEC-013000 | Subcontractor / Manpower | Office Furniture
SEC-014000 | Subcontractor / Manpower | Manpower Rental
SEC-015000 | Subcontractor / Manpower | Temporary Water
SEC-016000 | Subcontractor / Manpower | Materials Transportation
SEC-017000 | Subcontractor / Manpower | Construction Waste Management And Disposal
SEC-018000 | Subcontractor / Manpower | Diesel
SEC-022000SC | Subcontractor / Manpower | Fences And Gates
SEC-028000SC | Subcontractor / Manpower | Removal And Disposal Of Materials With Mold
SEC-030000 | Subcontractor / Manpower | Reinforcement Bars
SEC-030000SC | Subcontractor / Manpower | Common Work Results For Concrete
SEC-034000SC | Subcontractor / Manpower | Precast Structural Concrete
SEC-036000 | Subcontractor / Manpower | Cementitious Grouting
SEC-036000SC | Subcontractor / Manpower | Epoxy Grouting
SEC-040000 | Subcontractor / Manpower | Epoxy Masonry Mortaring
SEC-042000SC | Subcontractor / Manpower | Unit Masonry Panels
SEC-044000SC | Subcontractor / Manpower | Exterior Stone Cladding
SEC-051000 | Subcontractor / Manpower | Structural Steel Framing
SEC-052000SC | Subcontractor / Manpower | Steel Joist Framing
SEC-053000SC | Subcontractor / Manpower | Aluminum Decking
SEC-054000 | Subcontractor / Manpower | Metal Support Assemblies
SEC-054000SC | Subcontractor / Manpower | Structural Metal Stud Framing
SEC-055000SC | Subcontractor / Manpower | Petroleum And Coal Products Manufacturing Equipment
SEC-061000 | Subcontractor / Manpower | Heavy Timber Construction
SEC-064000SC | Subcontractor / Manpower | Architectural Wood Casework
SEC-071000SC | Subcontractor / Manpower | Sheet Waterproofing
SEC-072000 | Subcontractor / Manpower | Thermal Insulation
SEC-072000SC | Subcontractor / Manpower | Porous Concrete Blocks
SEC-075000SC | Subcontractor / Manpower | Marble Flooring Tiles
SEC-076000SC | Subcontractor / Manpower | Epoxy Floor Sealant
SEC-077000SC | Subcontractor / Manpower | Epoxy Flooring Coating
SEC-078000SC | Subcontractor / Manpower | Firestopping
SEC-079000 | Subcontractor / Manpower | Joint Sealants
SEC-081000SC | Subcontractor / Manpower | Wood Doors
SEC-084000SC | Subcontractor / Manpower | Polyethylene Sheeting (For Dust Protection)
SEC-086000SC | Subcontractor / Manpower | Warning Tape
SEC-087000 | Subcontractor / Manpower | Threshold
SEC-087000SC | Subcontractor / Manpower | Construction Waste Bags
SEC-088000SC | Subcontractor / Manpower | High Efficiency Curing Compound
SEC-092000 | Subcontractor / Manpower | Plaster And Gypsum Board Assemblies
SEC-092000SC | Subcontractor / Manpower | Cement Plastering
SEC-093000 | Subcontractor / Manpower | Waterproofing-Membrane Tiling
SEC-095000SC | Subcontractor / Manpower | Filler Board
SEC-096000SC | Subcontractor / Manpower | Epoxy Tile Adhesive & Grout
SEC-098000SC | Subcontractor / Manpower | Acoustic Insulation
SEC-099000 | Subcontractor / Manpower | Painting
SEC-099000SC | Subcontractor / Manpower | Painting
SEC-100000SC | Subcontractor / Manpower | Rebar Tie Wire
SEC-101000 | Subcontractor / Manpower | Signage
SEC-101000SC | Subcontractor / Manpower | Plywood Sheets (Marine Grade)
SEC-102000SC | Subcontractor / Manpower | Wooden Lattice Panels
SEC-105000SC | Subcontractor / Manpower | Supporting System - Hexa Nut
SEC-108000SC | Subcontractor / Manpower | Supporting System - Threaded Rod
SEC-110000SC | Subcontractor / Manpower | Supporting System - C Clamp
SEC-111000SC | Subcontractor / Manpower | Raceway And Boxes - Pvc Coupling
SEC-112000 | Subcontractor / Manpower | Office Equipment
SEC-112000SC | Subcontractor / Manpower | Raceway And Boxes - Pvc Pound Spring Clips
SEC-114000SC | Subcontractor / Manpower | Raceway And Boxes - Pvc Bend Heavy Gauge
SEC-115000SC | Subcontractor / Manpower | Raceway And Boxes - Emt Conduit
SEC-116000SC | Subcontractor / Manpower | Raceway And Boxes - Emt Strap Clamp 1-Hole ( C Clamp)
SEC-117000SC | Subcontractor / Manpower | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit)
SEC-120000SC | Subcontractor / Manpower | Raceway And Boxes - Square Boxes
SEC-121000SC | Subcontractor / Manpower | Raceway And Boxes - Ring Extension Square Boxes
SEC-122000SC | Subcontractor / Manpower | Raceway And Boxes - Wearther Proof Boxes
SEC-123000SC | Subcontractor / Manpower | Cable Trays - Hdg Steel Cable Tray
SEC-125000SC | Subcontractor / Manpower | Office Furniture
SEC-132000SC | Subcontractor / Manpower | Cable Trays - Straight Cable Ladder
SEC-134000SC | Subcontractor / Manpower | Sound, Vibration, And Seismic Control
SEC-142000SC | Subcontractor / Manpower | Elevator Equipment And Controls
SEC-212000SC | Subcontractor / Manpower | Gas-Based Fire-Extinguishing Systems
SEC-221000 | Subcontractor / Manpower | Domestic Water Piping Specialties-Gate Valve
SEC-221000SC | Subcontractor / Manpower | Underground Ducts And Raceways - Upvc Pipes
SEC-224000 | Subcontractor / Manpower | Hand Spray
SEC-230000 | Subcontractor / Manpower | Duct Tape
SEC-230000SC | Subcontractor / Manpower | Cable Connectors
SEC-233000 | Subcontractor / Manpower | Exhaust Air Louver
SEC-233000SC | Subcontractor / Manpower | Hvac Ducts And Casings
SEC-236000 | Subcontractor / Manpower | Refrigerant Condensers
SEC-237000SC | Subcontractor / Manpower | Cable Sleeving
SEC-255000SC | Subcontractor / Manpower | Electrical Accessories
SEC-259000SC | Subcontractor / Manpower | Anchor Bolt
SEC-260000 | Subcontractor / Manpower | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc
SEC-260000SC | Subcontractor / Manpower | Pipe Clamps
SEC-262000 | Subcontractor / Manpower | Wiring Devices - Single Socket Outlet 13A Switched Wheather
SEC-265000 | Subcontractor / Manpower | Special Purpose Lighting
SEC-271000 | Subcontractor / Manpower | Communications Cabinets, Racks, Frames, And Enclosures - Mai
SEC-280000SC | Subcontractor / Manpower | Testing And Commissioning
SEC-281000SC | Subcontractor / Manpower | Cpvc 45 Elbow
SEC-282000SC | Subcontractor / Manpower | Cpvc 90 Elbow
SEC-283000SC | Subcontractor / Manpower | Cpvc - Equal Tee
SEC-284000 | Subcontractor / Manpower | Fire Alarm System - Smoke Detector
SEC-284000SC | Subcontractor / Manpower | Pvc 45 Elbow
SEC-285000SC | Subcontractor / Manpower | Pvc - Female Tee
SEC-313000SC | Subcontractor / Manpower | Termite Control
SEC-314000SC | Subcontractor / Manpower | Shoring
SEC-321000SC | Subcontractor / Manpower | Handsaw
SEC-323000SC | Subcontractor / Manpower | Sledgehammer
SEC-328000SC | Subcontractor / Manpower | Clamps
SEC-333000SC | Subcontractor / Manpower | Tile Spacers
SEC-335000SC | Subcontractor / Manpower | Safety Gloves
SEC-336000SC | Subcontractor / Manpower | Dust Mask
SEC-337000SC | Subcontractor / Manpower | Site Grounding
SEC-340000SC | Subcontractor / Manpower | Hard Hat (Helmet)
SEC-350000SC | Subcontractor / Manpower | Breathing Mask (Full Face)
SEC-400000SC | Subcontractor / Manpower | Hand Tools
SEC-410000SC | Subcontractor / Manpower | Material Testing
SEC-420000SC | Subcontractor / Manpower | Demolition
SEC-460000 | Subcontractor / Manpower | Oil And Grease Separation And Removal Equipment
SEC-460000SC | Subcontractor / Manpower | Residuals Dewatering Equipment
SEC-502000 | Subcontractor / Manpower | Fixing Brackets
SEC-503000 | Subcontractor / Manpower | Porous Concrete Blocks
SEC-504000 | Subcontractor / Manpower | Aggregates For Earthwork
SEC-505000 | Subcontractor / Manpower | Safety Vest

## Fact_Helper
Project | Activity number | Item Code | Item Name | Amount | Transaction type | Transaction date | Category | Source | Year | Month | YearMonth | ProjectActivityKey | CostCenterBucket
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 1569275.39 | Committed | 2026-01-18 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 1569275.39 | Committed | 2026-01-18 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 1543021.2 | Committed | 2026-01-13 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-233100-001 | Hvac Ducts And Casings | 809050 | Committed | 2025-07-10 | SEC-233000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-233100-001 | Hvac Ducts And Casings | 809050 | Committed | 2025-07-10 | SEC-233000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 778477.57 | Item actual | 2025-12-31 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 681000.26 | Item actual | 2025-11-30 | Mat014100-017SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 641896 | Committed | 2025-10-19 | Mat014100-017SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 630669.4 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 595050.04 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 595050.04 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 595050.04 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 548175.15 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 517133 | Committed | 2025-12-28 | Mat014100-017SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 504204 | Committed | 2026-01-18 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 504204 | Committed | 2026-01-18 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 495768.6 | Committed | 2026-01-13 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-064100-001 | Architectural Wood Casework | 482950 | Committed | 2025-11-19 | SEC-064000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000022 | SC-064100-001 | Architectural Wood Casework | 482950 | Committed | 2025-12-23 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000022 | Subcontractor / Manpower
KSA Project | MIDA-000069 | SC-064100-001 | Architectural Wood Casework | 482950 | Committed | 2025-10-07 | SEC-064000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000069 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 480789.9 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 437196.9 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 427769.85 | Committed | 2026-01-18 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 427769.85 | Committed | 2026-01-18 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 420613.2 | Committed | 2026-01-13 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 413178 | Item actual | 2025-12-24 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-310500-003 | Aggregates For Earthwork | 410250 | Committed | 2025-11-13 | SEC-504000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 394223.26 | Item actual | 2025-08-31 | Mat014100-017SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 | M-014100-017 | Manpower Rental | 369957 | Item actual | 2025-12-24 | SEC-014000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 369957 | Item actual | 2025-12-29 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 361450.77 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-014100-017 | Manpower Rental | 360947 | Item actual | 2025-11-30 | SEC-014000 | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 360947 | Item actual | 2025-11-30 | Mat014100-017SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 325296 | Item actual | 2025-11-30 | Mat014100-017SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 308112 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 301496.33 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 292992 | Committed | 2025-10-19 | Mat014100-017SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-039100-001 | Ready-Mix Concrete | 279477.31 | Committed | 2025-11-26 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 268151 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 255489.04 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 250269.5 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 242127.6 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 242127.6 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 240460.54 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 236866 | Committed | 2025-11-26 | Mat014100-017SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 235919.2 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 235839.73 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 235839.73 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 229792.55 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-034100-001 | Precast Structural Concrete | 226350 | Committed | 2025-07-10 | SEC-034000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000023 | M-014100-017 | Manpower Rental | 224825 | Item actual | 2025-09-30 | SEC-014000 | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 224825 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 211376.02 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-034100-001 | Precast Structural Concrete | 210150 | Committed | 2025-07-10 | SEC-034000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 207695.63 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 207695.63 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 202370.1 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000117 | SC-284600-001 | Fire Alarm System | 196792.37 | Committed | 2026-01-13 | SEC-284000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000117 | Subcontractor / Manpower
KSA Project | MIDA-000117 | SC-284600-001 | Fire Alarm System | 196792.37 | Committed | 2026-01-18 | SEC-284000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000117 | Subcontractor / Manpower
KSA Project | MIDA-000117 | SC-284600-001 | Fire Alarm System | 196792.37 | Committed | 2026-01-18 | SEC-284000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000117 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 193703.7 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 193703.7 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000036 | SC-321100-001 | Base Courses | 192280 | Committed | 2025-12-22 | SEC-321000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000036 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-310500-003 | Aggregates For Earthwork | 191450 | Committed | 2025-11-13 | SEC-504000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 189675.98 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 188736.94 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 186829.9 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 186724.38 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 186650.7 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 186650.7 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000036 | SC-321100-001 | Base Courses | 185725 | Committed | 2025-12-22 | SEC-321000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000036 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-034100-001 | Precast Structural Concrete | 185328 | Committed | 2025-07-10 | SEC-034000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 181864.79 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 181707.86 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-233100-001 | Hvac Ducts And Casings | 180675 | Item actual | 2025-11-30 | SEC-233000SC | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-233100-001 | Hvac Ducts And Casings | 180675 | Item actual | 2025-11-30 | SEC-233000SC | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017800-020 | Permits and Licenses | 179052 | Item actual | 2025-08-31 | Mat017800-020SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Permits / Government Fees
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 178951.07 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 178951.07 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-034100-001 | Precast Structural Concrete | 177552 | Committed | 2025-07-10 | SEC-034000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 177000 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 174362.58 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-310500-003 | Aggregates For Earthwork | 165380 | Committed | 2025-11-13 | SEC-504000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 157953.46 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 157953.46 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 153903.37 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 150467.9 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 150467.9 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 147663 | Item actual | 2025-12-22 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 146609.75 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096800-001 | Carpeting | 143967.27 | Committed | 2025-07-08 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096800-001 | Carpeting | 143967.27 | Committed | 2025-07-23 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096800-001 | Carpeting | 143967.27 | Committed | 2025-07-23 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-142800-001 | Elevator Equipment And Controls | 136000 | Committed | 2025-07-23 | SEC-142000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 135600 | Committed | 2025-11-26 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 133999.66 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 133999.66 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000117 | SC-284600-001 | Fire Alarm System | 133309.89 | Committed | 2026-01-13 | SEC-284000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000117 | Subcontractor / Manpower
KSA Project | MIDA-000117 | SC-284600-001 | Fire Alarm System | 133309.89 | Committed | 2026-01-18 | SEC-284000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000117 | Subcontractor / Manpower
KSA Project | MIDA-000117 | SC-284600-001 | Fire Alarm System | 133309.89 | Committed | 2026-01-18 | SEC-284000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000117 | Subcontractor / Manpower
KSA Project | (Blank) | SC-096200-001 | Specialty Flooring | 131040 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 131040 | Committed | 2025-07-20 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 131040 | Committed | 2025-09-28 | SEC-096000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 130563.77 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 125302.65 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 125302.65 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 122089.76 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000126 | SC-142800-001 | Elevator Equipment And Controls | 120600 | Item actual | 2025-12-31 | SEC-142000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000126 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 119745.71 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 118345.75 | Committed | 2025-10-29 | Mat014100-017SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 118042.72 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-237300-001 | Air-Handling Units | 115000 | Committed | 2025-07-10 | SEC-237000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-237300-001 | Air-Handling Units | 115000 | Committed | 2025-07-10 | SEC-237000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 110630.95 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 110630.95 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 109732.68 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 109732.68 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 108684.7 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 108684.7 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 107794.26 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 106919.02 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 105897.92 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000126 | SC-142800-001 | Elevator Equipment And Controls | 104000 | Item actual | 2025-12-31 | SEC-142000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000126 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 102264.92 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 102264.92 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 99642.74 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 117-001 | Marble Flooring Tiles | 97200 | Committed | 2025-11-13 | SEC-075000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 117-001 | Marble Flooring Tiles | 97200 | Committed | 2025-11-13 | SEC-075000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 95378.2 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 95378.2 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 92932.61 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-077700-001 | Wall Specialties | 90000 | Committed | 2025-07-26 | SEC-077000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-237500-001 | Custom-Packaged Outdoor Hvac Equipment | 88800 | Committed | 2025-07-10 | SEC-237000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-237500-001 | Custom-Packaged Outdoor Hvac Equipment | 88800 | Committed | 2025-07-10 | SEC-237000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-054100-001 | Structural Metal Stud Framing | 87223.5 | Committed | 2025-06-30 | SEC-054000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-054100-001 | Structural Metal Stud Framing | 87223.5 | Committed | 2025-07-06 | SEC-054000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-054100-001 | Structural Metal Stud Framing | 87223.5 | Committed | 2025-07-06 | SEC-054000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-018 | Project Security | 86400 | Committed | 2025-11-12 | Mat014100-018SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Services
KSA Project | MIDA-000024 | M-230700-012 | Acoustic Insulation | 85600 | Committed | 2025-10-06 | SEC-230000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000024 | Subcontractor / Manpower
KSA Project | MIDA-000024 | SC-098100-001 | Acoustic Insulation | 85600 | Committed | 2025-10-06 | SEC-098000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000024 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-016 | Labour Accommodation | 85500 | Committed | 2025-10-27 | Mat017100-016SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Services
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 83200 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000024 | SC-098100-001 | Acoustic Insulation | 82390 | Committed | 2025-10-06 | SEC-098000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000024 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 82053 | Committed | 2025-12-20 | Mat014100-017SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 80007.31 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 80007.31 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-132200-001 | Office Shelters And Booths | 80000 | Committed | 2025-04-09 | SEC-132000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 78693.65 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 77955.84 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 75334.99 | Committed | 2025-11-26 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-030500-001 | Common Work Results For Concrete | 74100 | Committed | 2025-08-16 | SEC-030000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-030500-001 | Common Work Results For Concrete | 74100 | Committed | 2025-08-16 | SEC-030000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 74054.56 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 74054.56 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 74054.56 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 74054.56 | Committed | 2025-12-16 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 73995 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 72155.72 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 72155.72 | Committed | 2025-12-15 | SEC-212000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 70200 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 70158 | Committed | 2025-10-19 | Mat014100-017SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 69624 | Item actual | 2025-12-07 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000047 | Mat014100-017 | Manpower Rental | 69241.5 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000047 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 69241.5 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 68648.5 | Committed | 2026-01-18 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 68648.5 | Committed | 2026-01-18 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 67500 | Committed | 2026-01-13 | SEC-212000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000084 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-052100-001 | Steel Joist Framing | 67187.5 | Committed | 2025-11-19 | SEC-052000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 67187.5 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 67187.5 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 65779.5 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 65496.48 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | MIDA-000040 | SC-054100-001 | Structural Metal Stud Framing | 65000 | Committed | 2025-12-28 | SEC-054000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000040 | Subcontractor / Manpower
KSA Project | MIDA-000040 | SC-054100-001 | Structural Metal Stud Framing | 65000 | Committed | 2025-12-28 | SEC-054000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000040 | Subcontractor / Manpower
KSA Project | MIDA-000040 | SC-054100-001 | Structural Metal Stud Framing | 65000 | Committed | 2025-12-01 | SEC-054000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000040 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 65000 | Committed | 2025-09-09 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 65000 | Committed | 2025-09-09 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 62261 | Committed | 2025-11-02 | Mat014100-017SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-034100-001 | Precast Structural Concrete | 61000 | Committed | 2025-07-10 | SEC-034000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 60840 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-034100-001 | Precast Structural Concrete | 60500 | Committed | 2025-07-10 | SEC-034000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-092400-001 | Cement Plastering | 60000 | Committed | 2025-07-26 | SEC-092000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 117-001 | Marble Flooring Tiles | 59925.6 | Committed | 2025-11-26 | SEC-075000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 57964.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 57964.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 57260 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 57260 | Committed | 2025-07-20 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 57260 | Committed | 2025-09-28 | SEC-096000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 57002.84 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 55440 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-233100-001 | Hvac Ducts And Casings | 54750 | Committed | 2025-07-10 | SEC-233000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-233100-001 | Hvac Ducts And Casings | 54750 | Committed | 2025-07-10 | SEC-233000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 54138 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 54000 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000023 | M-014100-017 | Manpower Rental | 53563 | Item actual | 2025-10-31 | SEC-014000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 53563 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 117-001 | Marble Flooring Tiles | 52128 | Committed | 2025-11-26 | SEC-075000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 52098.02 | Committed | 2025-11-25 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 51498 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 51480 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 50200 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 50123.34 | Committed | 2025-11-25 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 49037.84 | Committed | 2025-11-25 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 47000 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 46320 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 46246 | Committed | 2025-11-25 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000129 | Mat018500-004 | Diesel | 45556.52 | Item actual | 2025-09-30 | Mat018500-004SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000129 | Materials
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 45540 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-034100-001 | Precast Structural Concrete | 45450 | Committed | 2025-07-10 | SEC-034000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 45360 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 45000 | Committed | 2025-11-26 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-036300-001 | Epoxy Grouting | 44804 | Committed | 2025-07-14 | SEC-036000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-036300-001 | Epoxy Grouting | 44804 | Committed | 2025-07-14 | SEC-036000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-036300-001 | Epoxy Grouting | 44804 | Committed | 2025-12-22 | SEC-036000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 44267.87 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 44267.87 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 44267.87 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 44121.6 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 44121.6 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 43428.61 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 43428.61 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 43424.13 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 43000 | Committed | 2025-08-02 | SEC-030000 | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | MC-50 10 103-001 | Porous Concrete Blocks | 43000 | Committed | 2025-10-27 | SEC-072000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-092100-001 | Plaster And Gypsum Board Assemblies | 42875 | Committed | 2025-11-25 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat014100-008 | Employee Accommodation | 42750 | Committed | 2025-12-03 | Mat014100-008SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000054 | SC-092300-001 | Gypsum Plastering | 42350 | Committed | 2025-10-09 | SEC-092000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-034100-001 | Precast Structural Concrete | 42300 | Committed | 2025-07-10 | SEC-034000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 42235.5 | Item actual | 2025-12-31 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 42000 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | MIDA-000040 | M-032100-001 | Reinforcement Bars | 42000 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000040 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 41580 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 40500 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 40500 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | Mat014100-017 | Manpower Rental | 40485.75 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 40485.75 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000129 | Mat018500-004 | Diesel | 40361.61 | Item actual | 2025-10-31 | Mat018500-004SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000129 | Materials
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 40000 | Committed | 2025-11-24 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 39219.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 39219.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 39200 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 39200 | Committed | 2025-11-26 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 38884.05 | Committed | 2025-08-12 | SEC-075000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-075100-001 | Built-Up Bituminous Roofing | 38884.05 | Committed | 2025-12-04 | SEC-075000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 38884.05 | Committed | 2025-07-20 | SEC-075000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000138 | Mat014500-007 | Testing Laboratory Services | 38650 | Item actual | 2025-05-31 | Mat014500-007SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000138 | Services
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 37756 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000129 | Mat018500-004 | Diesel | 37128.57 | Item actual | 2025-09-30 | Mat018500-004SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000129 | Materials
KSA Project | (Blank) | Mat011100-001 | Summary Of Work | 36792.45 | Item actual | 2025-01-31 | SEC-011000 | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-004 | Diesel | 36739.13 | Item actual | 2025-07-31 | SEC-018000 | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000107 | SC-092400-001 | Cement Plastering | 36256.5 | Item actual | 2025-11-30 | SEC-092000SC | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000107 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 35892 | Committed | 2025-12-18 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 35892 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 35892 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 35000 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 34655.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 34327.5 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 34327.5 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | M-032100-001 | Reinforcement Bars | 34200 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000047 | Mat014100-017 | Manpower Rental | 34103.25 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000047 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 34103.25 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 33907.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 33907.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-064100-001 | Architectural Wood Casework | 33792.5 | Committed | 2025-11-19 | SEC-064000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000022 | SC-064100-001 | Architectural Wood Casework | 33792.5 | Committed | 2025-12-23 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000022 | Subcontractor / Manpower
KSA Project | MIDA-000069 | SC-064100-001 | Architectural Wood Casework | 33792.5 | Committed | 2025-10-07 | SEC-064000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000069 | Subcontractor / Manpower
KSA Project | MIDA-000132 | M-310500-003 | Aggregates For Earthwork | 33780 | Committed | 2026-01-27 | SEC-504000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000132 | Subcontractor / Manpower
KSA Project | MIDA-000129 | Mat018500-004 | Diesel | 33473.37 | Committed | 2025-05-31 | Mat018500-004SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000129 | Materials
KSA Project | MIDA-000001 | Mat014100-017 | Manpower Rental | 33154.5 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 33154.5 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | Mat014100-017 | Manpower Rental | 32900 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 117-001 | Marble Flooring Tiles | 32886 | Committed | 2025-11-26 | SEC-075000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 32633 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 32500 | Committed | 2025-10-09 | Mat017100-015SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 32500 | Committed | 2025-10-09 | Mat017100-015SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat014100-008 | Employee Accommodation | 32500 | Committed | 2026-01-01 | Mat014100-008SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat014100-008 | Employee Accommodation | 32500 | Committed | 2026-01-01 | Mat014100-008SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000129 | Mat018500-004 | Diesel | 32357.64 | Committed | 2025-05-31 | Mat018500-004SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000129 | Materials
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 32065 | Committed | 2025-11-26 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 31971.33 | Committed | 2025-08-12 | SEC-075000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-075100-001 | Built-Up Bituminous Roofing | 31971.33 | Committed | 2025-12-04 | SEC-075000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 31971.33 | Committed | 2025-07-20 | SEC-075000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000138 | Mat014500-007 | Testing Laboratory Services | 31803 | Item actual | 2025-06-30 | Mat014500-007SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000138 | Services
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 31621.13 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 31621.13 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 31621.13 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 31153.5 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | Mat014100-017 | Manpower Rental | 31136.25 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 30966.4 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 30966.4 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 30800 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 30525 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | (Blank) |  |  | 30000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 30000 | Expense actual | 2025-03-31 | Mat014100-026 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 30000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 30000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 30000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 30000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 30000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 30000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 30000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 30000 | Expense actual | 2025-11-30 | Mat014100-026 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 30000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat017100-016 | Labour Accommodation | 30000 | Committed | 2025-10-30 | Mat017100-016SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000059 | M-032100-001 | Reinforcement Bars | 29960 | Committed | 2026-01-28 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000059 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-237300-001 | Air-Handling Units | 29400 | Committed | 2025-07-10 | SEC-237000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-237300-001 | Air-Handling Units | 29400 | Committed | 2025-07-10 | SEC-237000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 29000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-092100-001 | Plaster And Gypsum Board Assemblies | 28665 | Committed | 2025-11-13 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 28350 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 28350 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 28350 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 28080 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 27600 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 27552 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 27500 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000035 | SC-042200-001 | Concrete Unit Masonry | 27500 | Committed | 2025-10-06 | SEC-042000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000035 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 27353 | Committed | 2025-08-16 | Mat018500-010SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MC-50 10 117-001 | Marble Flooring Tiles | 26935.2 | Committed | 2025-11-25 | SEC-075000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000107 | SC-092400-001 | Cement Plastering | 26851.5 | Item actual | 2025-12-22 | SEC-092000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000107 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 26700 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 89-001 | Wooden Lattice Panels | 26700 | Committed | 2025-11-26 | SEC-102000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-004 | Diesel | 26599.13 | Item actual | 2025-07-31 | Mat018500-004SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Materials
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 26480 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 26460.48 | Committed | 2025-05-29 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000126 | SC-142800-001 | Elevator Equipment And Controls | 26000 | Committed | 2026-01-28 | SEC-142000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000126 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 25922.04 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 25922.04 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 25725 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 25500 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 25240 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 25229.76 | Item actual | 2025-12-21 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 25000 | Committed | 2025-08-02 | SEC-030000 | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000053 | SC-078400-001 | Firestopping | 24550.43 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000053 | Subcontractor / Manpower
KSA Project | MIDA-000053 | SC-078400-001 | Firestopping | 24550.43 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000053 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 24537.48 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 24500 | Committed | 2025-10-27 | SEC-030000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 24383.64 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 23974.85 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000018 | Mat014100-017 | Manpower Rental | 23700 | Item actual | 2025-11-30 | Mat014100-017SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000018 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-016 | Labour Accommodation | 23600 | Committed | 2025-11-27 | Mat017100-016SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | SC-337900-001 | Site Grounding | 23520.21 | Committed | 2025-04-15 | SEC-337000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-337900-001 | Site Grounding | 23520.14 | Committed | 2025-04-15 | SEC-337000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 23475.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 23475.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 23400 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 23306.76 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 23152.92 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000001 | SC-102100-001 | Compartments And Cubicles | 23120 | Committed | 2025-06-30 | SEC-102000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-102100-001 | Compartments And Cubicles | 23120 | Committed | 2025-07-02 | SEC-102000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-102100-001 | Compartments And Cubicles | 23120 | Committed | 2025-12-22 | SEC-102000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000090 | SC-467600-001 | Residuals Dewatering Equipment | 22880 | Committed | 2025-05-01 | SEC-460000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000090 | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 22849.42 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 22849.42 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 22849.42 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 22707.44 | Committed | 2025-11-04 | Mat018500-010SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 22614.48 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000017 | MC-50 10 117-001 | Marble Flooring Tiles | 22500 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-016 | Labour Accommodation | 22500 | Committed | 2025-10-30 | Mat017100-016SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat017100-016 | Labour Accommodation | 22500 | Committed | 2025-10-30 | Mat017100-016SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 22380.9 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 22380.9 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 22380.9 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000107 | SC-092400-001 | Cement Plastering | 22367.1 | Item actual | 2025-12-22 | SEC-092000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000107 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 22345 | Expense actual | 2025-09-16 | Mat014100-011 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 22280 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 22280 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 21993.75 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000099 | MM-502010-027 | Fixing Brackets | 21963.28 | Committed | 2026-01-27 | SEC-502000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000099 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 21922.2 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 21750 | Committed | 2025-11-16 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-005 | Testing And Inspecting Services | 21736.8 | Committed | 2025-04-15 | Mat014500-005SEV | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 21725 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | MIDA-000142 | Mat014000-004 | Hand Tools | 21600 | Item actual | 2025-12-31 | Mat014000-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000142 | Equipment / Plant
KSA Project | MIDA-000001 | SC-233400-001 | Hvac Fans | 21600 | Committed | 2025-07-10 | SEC-233000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-233400-001 | Hvac Fans | 21600 | Committed | 2025-07-10 | SEC-233000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 21500 | Committed | 2025-08-02 | SEC-030000 | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 21500 | Committed | 2025-10-27 | SEC-030000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 21496.25 | Expense actual | 2025-06-29 | Mat014100-011 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 21153 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 21106.8 | Item actual | 2025-10-31 | Mat014000-003SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | MIDA-000040 | M-032100-001 | Reinforcement Bars | 21000 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000040 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 20921.6 | Committed | 2025-11-04 | Mat018500-010SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 20901.1 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 20895 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-039100-001 | Ready-Mix Concrete | 20825 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 20801.25 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 20801.25 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000148 | Mat017100-018 | Demobalization | 20700 | Committed | 2025-09-14 | Mat017100-018SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000148 | Materials / Misc
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 20680 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 20500 | Committed | 2025-12-27 | Mat018500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | MC-50 10 79-001 | Copper Wire | 20394 | Committed | 2025-11-26 | SEC-100000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 20383.8 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 20227.5 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 20204 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 20000 | Committed | 2025-05-29 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000107 | SC-092400-001 | Cement Plastering | 19887.6 | Item actual | 2025-11-30 | SEC-092000SC | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000107 | Subcontractor / Manpower
KSA Project | MIDA-000038 | SC-099100-001 | Painting | 19879.3 | Item actual | 2025-12-22 | SEC-099000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000038 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 19813.37 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 19801.25 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 19801.25 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 19801.25 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 19801.25 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 19801.25 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 19801.25 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-036100-001 | Cementitious Grouting | 19789 | Committed | 2025-11-13 | SEC-036000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000017 | MC-50 10 117-001 | Marble Flooring Tiles | 19692.43 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | MIDA-000009 | M-061300-001 | Heavy Timber Construction | 19600 | Committed | 2026-01-27 | SEC-061000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 19600 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 19565.86 | Item actual | 2025-11-30 | Mat014100-017SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 19550 | Item actual | 2025-03-31 | Mat018500-010SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 19500 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | M-051200-001 | Structural Steel Framing | 19200 | Committed | 2025-11-13 | SEC-051000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 19089 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000023 | SC-044200-001 | Exterior Stone Cladding | 19000 | Item actual | 2025-12-28 | SEC-044000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-011 | Employee Transportation | 19000 | Committed | 2025-07-09 | Mat014100-011SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-036100-001 | Cementitious Grouting | 18848 | Committed | 2025-11-25 | SEC-036000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-036100-001 | Cementitious Grouting | 18761 | Committed | 2025-11-25 | SEC-036000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000056 | MC-50 10 126-001 | Epoxy Flooring Coating | 18760 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000056 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-052100-001 | Steel Joist Framing | 18750 | Committed | 2025-11-19 | SEC-052000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 18750 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 18750 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 18720 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 18650 | Item actual | 2025-02-28 | Mat018500-010SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 18606.78 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 18591.05 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 18553.64 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 18383.88 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 18334 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 18334 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 18334 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 18334 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 18334 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 18334 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 18334 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 18334 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 18270 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 18225 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 18225 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 18150 | Committed | 2026-01-17 | Mat017400-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 18057.6 | Item actual | 2025-10-31 | Mat014000-003SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | (Blank) |  |  | 18000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 18000 | Committed | 2025-08-09 | Mat018500-010SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 17999.8 | Committed | 2025-10-16 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 17957.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-036100-001 | Cementitious Grouting | 17905.6 | Committed | 2025-11-13 | SEC-036000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 17760 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 17760 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 17760 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 17760 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 17742.58 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 17490 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 17490 | Committed | 2025-07-20 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 17490 | Committed | 2025-09-28 | SEC-096000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 17460.84 | Committed | 2025-10-16 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000138 | Mat014500-007 | Testing Laboratory Services | 17402 | Item actual | 2025-05-31 | Mat014500-007SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000138 | Services
KSA Project | MIDA-000149 | SC-132200-001 | Office Shelters And Booths | 17391.3 | Committed | 2025-04-09 | SEC-132000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 17267.25 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 17267.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 17200 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 17200 | Committed | 2025-10-27 | SEC-030000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 17119.2 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | Mat016500-001 | Product Delivery Requirements | 16950 | Item actual | 2025-06-30 | Mat016500-001SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 16900 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 16800 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000001 | SC-237500-001 | Custom-Packaged Outdoor Hvac Equipment | 16800 | Committed | 2025-07-10 | SEC-237000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-237500-001 | Custom-Packaged Outdoor Hvac Equipment | 16800 | Committed | 2025-07-10 | SEC-237000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 16738.76 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 16738.76 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 16738.76 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 16705 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat017100-015 | Staff Accommodation | 16695.65 | Committed | 2025-11-24 | Mat017100-015SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 16475.05 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 16475.05 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 16380 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 16356.33 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 16356.33 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 16356.33 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 16133 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 16125 | Committed | 2025-11-22 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 16125 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 16125 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 16125 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 15995 | Item actual | 2025-12-23 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 15900 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 15900 | Committed | 2025-07-31 | Mat018500-010SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | SC-024100-001 | Demolition | 15810 | Item actual | 2025-11-30 | SEC-420000SC | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 15795 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | SC-024100-001 | Demolition | 15780.43 | Item actual | 2025-07-31 | SEC-420000SC | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000132 | M-310500-003 | Aggregates For Earthwork | 15764 | Committed | 2026-01-27 | SEC-504000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000132 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 15625 | Item actual | 2025-04-30 | Mat018500-010SEV | Item transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 15600 | Item actual | 2025-04-30 | Mat018500-010SEV | Item transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 15600 | Committed | 2025-07-31 | Mat018500-010SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 15555 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 15483.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 15483.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 15400 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 15318 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 15318 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 15234.82 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000001 | SC-052100-001 | Steel Joist Framing | 15029.3 | Committed | 2025-11-19 | SEC-052000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 15029.3 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 15029.3 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-018 | Project Security | 15000 | Item actual | 2025-05-31 | Mat014100-018SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-018 | Project Security | 15000 | Item actual | 2025-06-30 | SEC-014000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-018 | Project Security | 15000 | Item actual | 2025-07-31 | Mat014100-018SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-018 | Project Security | 15000 | Item actual | 2025-08-31 | Mat014100-018SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000140 | Mat014100-018 | Project Security | 15000 | Item actual | 2025-09-30 | Mat014100-018SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000140 | Services
KSA Project | MIDA-000140 | Mat014100-018 | Project Security | 15000 | Item actual | 2025-10-31 | Mat014100-018SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Services
KSA Project | MIDA-000140 | Mat014100-018 | Project Security | 15000 | Item actual | 2025-12-31 | Mat014100-018SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | MIDA-000133 |  |  | 15000 | Expense actual | 2025-08-06 | Mat014100-027 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014100-018 | Project Security | 15000 | Committed | 2025-05-15 | SEC-014000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-018 | Project Security | 15000 | Committed | 2025-06-19 | Mat014100-018SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | SC-052100-001 | Steel Joist Framing | 14980.46 | Committed | 2025-11-19 | SEC-052000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 14980.46 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 14980.46 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 14973 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 14950 | Item actual | 2025-03-31 | Mat018500-010SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 14880 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 14880 | Committed | 2025-07-20 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 14880 | Committed | 2025-09-28 | SEC-096000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 14662.5 | Committed | 2025-10-29 | Mat014100-017SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 14575 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 14500 | Committed | 2025-11-16 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 14434.2 | Item actual | 2025-10-31 | Mat014000-003SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | MIDA-000147 | Mat017100-016 | Labour Accommodation | 14400 | Committed | 2025-12-08 | Mat017100-016SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000147 | Services
KSA Project | MIDA-000133 | Mat014100-018 | Project Security | 14400 | Committed | 2025-11-12 | Mat014100-018SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Services
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 14252.25 | Item actual | 2025-09-30 | Mat017100-015SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 14132.24 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 14132.24 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 14132.24 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 14050 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000040 | M-032100-001 | Reinforcement Bars | 14040 | Committed | 2026-01-28 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000040 | Subcontractor / Manpower
KSA Project | MIDA-000054 | SC-092300-001 | Gypsum Plastering | 14000 | Item actual | 2025-12-31 | SEC-092000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000054 | SC-092300-001 | Gypsum Plastering | 14000 | Item actual | 2025-12-31 | SEC-092000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 14000 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | SC-101400-001 | Signage | 14000 | Committed | 2025-08-04 | SEC-101000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 13878 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 13851.75 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 13817.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-039100-001 | Ready-Mix Concrete | 13720 | Committed | 2025-11-26 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 13708.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 13708.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 13622.78 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 13500 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 13500 | Committed | 2025-08-02 | SEC-030000 | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 13500 | Committed | 2025-08-02 | SEC-030000 | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 13500 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 13461 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000126 | SC-142800-001 | Elevator Equipment And Controls | 13400 | Committed | 2026-01-28 | SEC-142000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000126 | Subcontractor / Manpower
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 13396.2 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 13368 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 13368 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 13300 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 13275.6 | Committed | 2025-07-09 | Mat018500-010SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000107 | SC-092400-001 | Cement Plastering | 13260.9 | Item actual | 2025-11-30 | SEC-092000SC | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000107 | Subcontractor / Manpower
KSA Project | (Blank) | Mat011100-001 | Summary Of Work | 13207.55 | Item actual | 2025-01-31 | SEC-011000 | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 13200 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 13000 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 13000 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 12948 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 12948 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 12948 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) | Mat016500-002 | Materials Transportation | 12900 | Committed | 2025-05-22 | Mat016500-002SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000058 | M-032100-001 | Reinforcement Bars | 12840 | Committed | 2026-01-28 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000058 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 12810 | Item actual | 2025-06-30 | SEC-018000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 12785.5 | Committed | 2025-07-09 | Mat018500-010SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 12730.26 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000087 | Mat014100-017 | Manpower Rental | 12706.75 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 12706.75 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 12640 | Item actual | 2025-10-31 | Mat017100-002SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 12639.38 | Committed | 2025-07-09 | Mat018500-010SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 12639 | Committed | 2025-12-29 | Mat014100-017SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 12600 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 12500 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 12500 | Committed | 2025-09-11 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 12500 | Committed | 2025-09-11 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 12500 | Committed | 2025-09-11 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 12500 | Committed | 2025-09-11 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000133 | Mat014100-018 | Project Security | 12480 | Item actual | 2025-11-30 | Mat014100-018SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Services
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 12375 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071300-001 | Sheet Waterproofing | 12375 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 12375 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 12349.12 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 12283.78 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 12250 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000054 | M-092100-001 | Plaster And Gypsum Board Assemblies | 12250 | Committed | 2026-01-27 | SEC-092000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 12241.52 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 12090 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 12025.79 | Committed | 2025-05-26 | Mat014100-009SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 12015.12 | Committed | 2025-11-25 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 12000 | Item actual | 2025-05-31 | Mat014100-018SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Services
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 12000 | Item actual | 2025-07-31 | Mat014100-018SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Services
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 12000 | Item actual | 2025-09-30 | Mat014100-018SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000001 | Services
KSA Project | (Blank) | Mat014100-018 | Project Security | 12000 | Item actual | 2025-11-30 | Mat014100-018SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 12000 | Item actual | 2025-12-22 | Mat014100-018SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Services
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 12000 | Item actual | 2025-12-31 | Mat014100-018SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Services
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 12000 | Committed | 2025-06-22 | Mat014100-018SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Services
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 12000 | Committed | 2025-06-22 | Mat014100-018SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Services
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 12000 | Committed | 2025-06-22 | Mat014100-018SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 12000 | Committed | 2025-11-12 | Mat018500-010SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | SC-101400-001 | Signage | 12000 | Committed | 2025-08-04 | SEC-101000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | SC-101400-001 | Signage | 12000 | Committed | 2025-08-04 | SEC-101000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 11950 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 11860.55 | Item actual | 2025-07-31 | SEC-018000 | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 11800 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 11777 | Item actual | 2025-04-30 | Mat018500-010SEV | Item transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 11760 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 11730 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 11700 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 11700 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 11700 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 11700 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 11691.55 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 11609.25 | Item actual | 2025-05-31 | Mat014100-017SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 11609.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 11571.43 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 11500 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 11500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 11500 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 11500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 11500 | Committed | 2025-11-26 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 11500 | Committed | 2025-11-24 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 11500 | Committed | 2025-11-26 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 11480 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | MIDA-000107 | SC-092400-001 | Cement Plastering | 11376.4 | Committed | 2025-09-15 | SEC-092000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000107 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 11360.83 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 11360 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 11287.77 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 11275 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 11260.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 11260.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 11253.11 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 11200 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 11071.62 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 11064 | Item actual | 2025-05-31 | Mat018500-010SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 11056.07 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 11050 | Committed | 2025-08-16 | Mat018500-010SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000094 | MC-50 20 00-014 | Supporting System - Anchor Bolt | 11000 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000094 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 10972.5 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 10960.84 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 10850 | Committed | 2025-05-20 | Mat017400-004SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000148 | Mat017100-018 | Demobalization | 10800 | Item actual | 2025-02-28 | Mat017100-018SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦MIDA-000148 | Materials / Misc
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 10782.8 | Committed | 2025-11-25 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-011 | Employee Transportation | 10742.76 | Item actual | 2025-08-31 | Mat014100-011SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000144 | Mat014100-009 | Employee Food | 10737.47 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000144 | Materials / Misc
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 10656 | Committed | 2025-08-17 | Mat014000-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 10653.42 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | M-310500-011 | Cement And Concrete For Earthwork | 10620 | Committed | 2025-11-13 | SEC-504000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-011 | Employee Transportation | 10558.89 | Item actual | 2025-08-31 | Mat014100-011SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MC-50 10 126-001 | Epoxy Flooring Coating | 10535 | Committed | 2025-11-25 | SEC-077000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 10525.72 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 10500 | Item actual | 2025-02-28 | Mat018500-010SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 10500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 10500 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 10500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 10500 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat013500-023 | Period Treatment Procedures | 10500 | Committed | 2025-09-07 | Mat013500-023SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 10500 | Committed | 2025-12-27 | Mat018500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 10478 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000112 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 10400 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000112 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 10400 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 10400 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 10400 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 10231.2 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 10230 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000001 | SC-064100-001 | Architectural Wood Casework | 10080 | Committed | 2025-11-19 | SEC-064000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000022 | SC-064100-001 | Architectural Wood Casework | 10080 | Committed | 2025-12-23 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000022 | Subcontractor / Manpower
KSA Project | MIDA-000069 | SC-064100-001 | Architectural Wood Casework | 10080 | Committed | 2025-10-07 | SEC-064000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000069 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-072100-001 | Thermal Insulation | 10000 | Committed | 2025-10-27 | SEC-072000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 10000 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-072100-001 | Thermal Insulation | 10000 | Committed | 2025-11-25 | SEC-072000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 10000 | Committed | 2025-05-11 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 10000 | Committed | 2025-05-11 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 9999.6 | Committed | 2025-10-16 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 9974.75 | Item actual | 2025-12-21 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 9936 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 9920 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 9900 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 9855 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) | Mat014100-009 | Employee Food | 9850.43 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 9832.5 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 9832.5 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 9819.12 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 9707 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000144 |  |  | 9700 | Expense actual | 2025-01-16 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 9669.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 9669.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 9669.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 9653.46 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 9616.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 9616.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 9613.5 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 9548 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 9539.77 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 9504.99 | Committed | 2025-08-12 | SEC-075000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-075100-001 | Built-Up Bituminous Roofing | 9504.99 | Committed | 2025-12-04 | SEC-075000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 9504.99 | Committed | 2025-07-20 | SEC-075000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000100 | Mat014500-007 | Testing Laboratory Services | 9504 | Item actual | 2025-12-31 | Mat014500-007SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000100 | Services
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 9501.6 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000132 | SC-064100-001 | Architectural Wood Casework | 9500 | Committed | 2025-12-23 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000132 | Subcontractor / Manpower
KSA Project | MIDA-000069 | SC-064100-001 | Architectural Wood Casework | 9500 | Committed | 2025-10-07 | SEC-064000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000069 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-064100-001 | Architectural Wood Casework | 9500 | Committed | 2025-11-19 | SEC-064000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 9468 | Item actual | 2025-12-31 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 9450 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 9366.75 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 9282.7 | Committed | 2025-05-26 | Mat014100-009SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000087 | Mat014100-017 | Manpower Rental | 9228.75 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 9228.75 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 79-001 | Copper Wire | 9166.5 | Committed | 2025-11-26 | SEC-100000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 9135 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 9095 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 9080 | Committed | 2025-11-26 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 9026.09 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 9000 | Item actual | 2025-01-31 | Mat018500-010SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 9000 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | SC-092400-001 | Cement Plastering | 9000 | Item actual | 2025-12-22 | SEC-092000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 9000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 9000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 9000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 9000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 9000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 9000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 9000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 9000 | Committed | 2025-08-02 | SEC-030000 | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 9000 | Committed | 2025-11-13 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 9000 | Committed | 2025-12-02 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 9000 | Committed | 2025-12-03 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 9000 | Committed | 2025-12-23 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 9000 | Committed | 2026-01-27 | Mat018500-010SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 8964.9 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 8964 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 8880 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 8857.14 | Item actual | 2025-02-28 | Mat014100-018SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦MIDA-000001 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 8845.8 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 8775 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 8775 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000054 | SC-092300-001 | Gypsum Plastering | 8750 | Item actual | 2025-12-31 | SEC-092000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 8750 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 8702.62 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000001 | SC-030500-001 | Common Work Results For Concrete | 8640 | Committed | 2025-08-16 | SEC-030000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-030500-001 | Common Work Results For Concrete | 8640 | Committed | 2025-08-16 | SEC-030000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000060 | M-032100-001 | Reinforcement Bars | 8560 | Committed | 2026-01-28 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000060 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 8551.44 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000001 | MC-50 10 103-001 | Porous Concrete Blocks | 8550 | Committed | 2025-10-23 | SEC-072000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 8550 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 8500 | Committed | 2026-01-12 | Mat018500-010SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 8466 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 8466 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 8466 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 8449.72 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 8445 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 8425.96 | Item actual | 2025-12-21 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 8400 | Item actual | 2025-12-22 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000054 | SC-092300-001 | Gypsum Plastering | 8400 | Item actual | 2025-12-31 | SEC-092000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-016500-002 | Materials Transportation | 8400 | Committed | 2025-10-27 | SEC-016000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat017400-004 | Construction Waste Management And Disposal | 8400 | Committed | 2025-05-20 | Mat017400-004SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 8379 | Committed | 2025-12-18 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 8379 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 8379 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 8352 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 8300 | Item actual | 2025-08-31 | Mat019300-004SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 8300 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000046 | Mat018500-010 | Equipment Rental | 8280 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Services
KSA Project | (Blank) | Mat014100-009 | Employee Food | 8274.77 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 8255 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-009 | Employee Food | 8250.13 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 8235.9 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 8235.9 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 8200 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 8175 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 8144.46 | Item actual | 2025-11-30 | Mat017100-015SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | Mat014100-009 | Employee Food | 8135.65 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000038 | SC-099100-001 | Painting | 8120.7 | Committed | 2025-09-15 | SEC-099000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000038 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 8101.47 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 8100 | Committed | 2025-11-26 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 8097.39 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 8050 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 8004 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 8000 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 8000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 8000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 8000 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 8000 | Committed | 2025-08-09 | Mat017100-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 8000 | Committed | 2025-08-16 | Mat018500-010SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 8000 | Committed | 2025-10-23 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000017 | M-015100-009 | Temporary Water | 7990 | Committed | 2025-05-21 | SEC-015000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 7961.75 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000001 | SC-028700-006 | Removal And Disposal Of Materials With Mold | 7920 | Committed | 2025-05-20 | SEC-028000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 7845.84 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 7840 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 7840 | Committed | 2025-07-20 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 7840 | Committed | 2025-09-28 | SEC-096000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 7826.1 | Committed | 2025-10-05 | Mat017100-015SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 7821 | Item actual | 2025-12-31 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000017 | M-015100-009 | Temporary Water | 7820 | Committed | 2025-05-21 | SEC-015000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 7746.48 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 7741.94 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 7720.16 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 7720.16 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 7720.16 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 7696.5 | Committed | 2025-12-20 | SEC-116000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 7696.5 | Committed | 2026-01-12 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116600-001 | Athletic Equipment | 7696.5 | Committed | 2026-01-22 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 7686.8 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 7628.64 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-047 | Raceway And Boxes - Square Box Flat Blank | 7600 | Committed | 2025-11-26 | SEC-120000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000017 | M-015100-009 | Temporary Water | 7565 | Item actual | 2025-10-31 | SEC-015000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | MIDA-000023 | M-015100-009 | Temporary Water | 7540 | Item actual | 2025-11-30 | SEC-015000 | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 7500 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 7500 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 7500 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 7500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 7500 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 7500 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 7500 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 7500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 7500 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 7500 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 7500 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 7500 | Committed | 2025-11-26 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-016 | Labour Accommodation | 7500 | Committed | 2025-10-30 | Mat017100-016SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 7500 | Committed | 2026-01-14 | Mat018500-010SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 7500 | Committed | 2025-12-22 | Mat018500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 7452 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 7452 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 7449.96 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 7431.36 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014100-009 | Employee Food | 7426.16 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 7350 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 7278.24 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 7275 | Expense actual | 2025-03-11 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 7250 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 |  |  | 7225.81 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 7200 | Item actual | 2025-02-28 | Mat018500-010SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000147 | Mat017100-016 | Labour Accommodation | 7200 | Committed | 2025-12-08 | Mat017100-016SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000147 | Services
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 7088.75 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 7088.75 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-310500-011 | Cement And Concrete For Earthwork | 7080 | Committed | 2025-11-13 | SEC-504000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 7000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 7000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 7000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 7000 | Committed | 2025-09-15 | Mat018500-010SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 6956.52 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 6922.5 | Item actual | 2025-03-31 | Mat018500-010SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 6897.4 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) | Mat014100-009 | Employee Food | 6845.22 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 6801.03 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 6800 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 6800 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-009 | Employee Food | 6793.43 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 6774.19 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6774.19 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6774.19 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000138 | Mat014500-007 | Testing Laboratory Services | 6759 | Item actual | 2025-05-31 | Mat014500-007SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000138 | Services
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 6756.54 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000148 | Mat017100-018 | Demobalization | 6750 | Item actual | 2025-02-28 | Mat017100-018SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦MIDA-000148 | Materials / Misc
KSA Project | MIDA-000148 | Mat017100-018 | Demobalization | 6750 | Item actual | 2025-02-28 | Mat017100-018SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦MIDA-000148 | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 6650 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 6615.65 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 6615 | Committed | 2025-11-26 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000144 | Mat014100-009 | Employee Food | 6570.9 | Committed | 2025-05-26 | Mat014100-009SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000144 | Materials / Misc
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 6552 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 6542.61 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 6537.6 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071300-001 | Sheet Waterproofing | 6537.6 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 6537.6 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 6535.72 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6533.34 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 6532 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 6525 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 6500 | Item actual | 2025-03-31 | Mat018500-010SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 6500 | Item actual | 2025-05-31 | Mat018500-010SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 6500 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 6500 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6500 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 6490 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 6440 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 6433.73 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 6409 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 6409 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 6405 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 6375 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000054 | MC-50 10 103-001 | Porous Concrete Blocks | 6375 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 6368 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 6360 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 6332.35 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 6225 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 6193.55 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 6169 | Item actual | 2025-12-24 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 6086.96 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 6080.64 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 6050 | Item actual | 2025-05-31 | Mat014100-017SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 6050 | Committed | 2026-01-17 | Mat017400-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 6030 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 6030 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 6000 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 6000 | Expense actual | 2025-08-13 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 6000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 6000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 6000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 6000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 6000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 6000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 6000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 6000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 6000 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 55-001 | Epoxy Tile Adhesive & Grout | 6000 | Committed | 2025-11-25 | SEC-096000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000056 | MC-50 10 55-001 | Epoxy Tile Adhesive & Grout | 6000 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000056 | Subcontractor / Manpower
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 6000 | Committed | 2025-10-02 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 6000 | Committed | 2025-08-07 | Mat018500-010SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 5950 | Item actual | 2025-09-30 | Mat017400-004SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 5950 | Item actual | 2025-10-31 | Mat017400-004SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5920 | Committed | 2025-11-22 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5920 | Committed | 2025-11-22 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5920 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5920 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5920 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5920 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-036300-001 | Epoxy Grouting | 5904 | Committed | 2025-11-13 | SEC-036000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-036300-001 | Epoxy Grouting | 5904 | Committed | 2025-11-25 | SEC-036000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 5870.96 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5859.35 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000023 | M-015100-009 | Temporary Water | 5850 | Item actual | 2025-11-30 | SEC-015000 | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5850 | Committed | 2025-08-16 | Mat018500-010SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 5849.6 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 5849.6 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 5806.45 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5806.45 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 5800 | Committed | 2025-11-25 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000054 | M-040500-002 | Masonry Mortaring | 5775 | Committed | 2026-01-28 | SEC-040000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 5752.5 | Committed | 2025-11-13 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 5752.5 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5709.99 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5627.4 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5627.4 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5627.4 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5627.4 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5627.4 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5627.4 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) | M-015100-009 | Temporary Water | 5610 | Item actual | 2025-12-31 | SEC-015000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 5603.47 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 5600 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000001 | SC-233400-001 | Hvac Fans | 5600 | Committed | 2025-07-10 | SEC-233000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-233400-001 | Hvac Fans | 5600 | Committed | 2025-07-10 | SEC-233000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 5583.02 | Item actual | 2025-08-31 | Mat014100-017SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 5571.85 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | SC-024100-001 | Demolition | 5569.57 | Item actual | 2025-07-31 | SEC-420000SC | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000138 | Mat014500-007 | Testing Laboratory Services | 5565 | Item actual | 2025-05-31 | Mat014500-007SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000138 | Services
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 5540 | Item actual | 2025-02-28 | Mat014300-012SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦MIDA-000135 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5538.4 | Committed | 2025-10-16 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 |  |  | 5530.65 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat013700-003 | Property Insurance | 5525 | Item actual | 2025-03-31 | Mat013700-003SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 5525 | Committed | 2025-12-20 | SEC-116000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 5525 | Committed | 2026-01-12 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116600-001 | Athletic Equipment | 5525 | Committed | 2026-01-22 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 5520 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5520 | Committed | 2025-05-18 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5519.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5519.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5519.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5507.42 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 5502 | Committed | 2025-08-11 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000144 | Mat014100-009 | Employee Food | 5501.88 | Committed | 2025-05-26 | Mat014100-009SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000144 | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5500 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5500 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 5500 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5500 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5500 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5500 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5500 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 5480 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-005 | Testing And Inspecting Services | 5434.2 | Item actual | 2025-01-31 | Mat014500-005SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000087 | Mat014100-017 | Manpower Rental | 5433.75 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 5433.75 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 5429.6 | Item actual | 2025-11-30 | Mat017100-015SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) |  |  | 5411.82 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-092500-001 | Other Plastering | 5400 | Committed | 2025-11-13 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-003 | Fuel | 5396 | Committed | 2025-11-25 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 5391.4 | Committed | 2025-11-25 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5375 | Committed | 2025-11-22 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5375 | Committed | 2025-11-22 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5375 | Committed | 2025-11-22 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5375 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5375 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 5375 | Committed | 2025-11-27 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 5355 | Committed | 2025-11-26 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 5335 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 5331.82 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 5326.09 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 5326.09 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 5322.58 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5307.6 | Item actual | 2025-05-31 | Mat018500-010SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000001 | SC-052100-001 | Steel Joist Framing | 5273.44 | Committed | 2025-11-19 | SEC-052000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 5273.44 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 5273.44 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) | M-101400-001 | Signage | 5234.4 | Committed | 2025-11-13 | SEC-101000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 5225.8 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5200 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 5187 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 5175 | Committed | 2025-08-11 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5170 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 5160 | Item actual | 2025-02-28 | Mat014300-012SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5104.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5104.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 5104.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000017 | M-015100-009 | Temporary Water | 5100 | Item actual | 2025-10-31 | SEC-015000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-019 | Raceway And Boxes - Liquid Tight Flexible Conduit | 5100 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-048 | Raceway And Boxes - Octagonal Boxes | 5100 | Committed | 2025-11-26 | SEC-120000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 5100 | Committed | 2025-11-26 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-016 | Labour Accommodation | 5100 | Committed | 2025-10-30 | Mat017100-016SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000136 | Mat014100-009 | Employee Food | 5095.48 | Committed | 2026-01-12 | Mat014100-009SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000136 | Materials / Misc
KSA Project | (Blank) | Mat014100-009 | Employee Food | 5081.73 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5076.5 | Item actual | 2025-03-31 | Mat018500-010SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5070 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 5054.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 5050 | Committed | 2025-08-11 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000144 | Mat014100-009 | Employee Food | 5027.26 | Committed | 2025-05-26 | Mat014100-009SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000144 | Materials / Misc
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 5025 | Committed | 2025-12-02 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 5025 | Committed | 2025-12-03 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 5025 | Committed | 2025-12-23 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000019 | M-087100-018 | Threshold | 5017.13 | Committed | 2026-01-28 | SEC-087000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000019 | Subcontractor / Manpower
KSA Project | (Blank) | M-015100-009 | Temporary Water | 5015 | Item actual | 2025-12-31 | SEC-015000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 5012.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 5012.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5000 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 5000 | Item actual | 2025-06-30 | SEC-018000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5000 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5000 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5000 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5000 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 5000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 5000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 5000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 5000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 5000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 5000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 5000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 5000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-092100-001 | Plaster And Gypsum Board Assemblies | 5000 | Committed | 2025-11-25 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 5000 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 5000 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000053 | MC-50 10 103-001 | Porous Concrete Blocks | 5000 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000053 | Subcontractor / Manpower
KSA Project | MIDA-000095 | MC-50 20 00-014 | Supporting System - Anchor Bolt | 5000 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 5000 | Committed | 2025-08-31 | Mat019300-004SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5000 | Committed | 2025-05-12 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 5000 | Committed | 2025-05-12 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4980 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 4970 | Item actual | 2025-05-31 | SEC-014000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 4968 | Item actual | 2025-05-31 | Mat014100-017SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 4968 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 4966.38 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 4966.38 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 4956.54 | Committed | 2025-10-05 | Mat017100-015SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 4950 | Committed | 2025-11-13 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 4950 | Committed | 2025-11-13 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4931.07 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4928.57 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 4900 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) | MC-50 10 126-001 | Epoxy Flooring Coating | 4900 | Committed | 2025-11-25 | SEC-077000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 50-001 | Filler Board | 4900 | Committed | 2025-11-25 | SEC-095000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 4900 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 4900 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4850 | Expense actual | 2025-03-06 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4838.71 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-018500-004 | Diesel | 4835.52 | Committed | 2025-11-25 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4833.33 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-015100-009 | Temporary Water | 4830 | Item actual | 2025-12-31 | SEC-015000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4821.43 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4809.15 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017800-020 | Permits and Licenses | 4800 | Item actual | 2025-01-31 | Mat017800-020SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Permits / Government Fees
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 4800 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000001 | M-072100-001 | Thermal Insulation | 4800 | Committed | 2025-10-27 | SEC-072000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-099100-001 | Painting | 4800 | Committed | 2025-11-25 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 4760 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4750 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4750 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4750 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 4750 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-092100-001 | Plaster And Gypsum Board Assemblies | 4750 | Committed | 2025-11-25 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000053 | MC-50 10 103-001 | Porous Concrete Blocks | 4750 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000053 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 4744.34 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017100-002 | Mobilization | 4725.22 | Committed | 2025-10-28 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 4725 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 4677.42 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 4666.67 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 4657.16 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 4634.4 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 4634.4 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 4631.31 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 4621.2 | Committed | 2025-11-25 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 4621.2 | Committed | 2025-11-25 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-040500-004 | Epoxy Masonry Mortaring | 4620 | Committed | 2025-11-25 | SEC-040000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 4620 | Committed | 2025-08-11 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 4610.4 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 4610.4 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 4610 | Item actual | 2025-05-31 | Mat018500-010SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat017100-016 | Labour Accommodation | 4608.7 | Committed | 2025-11-06 | Mat017100-016SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4606.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4606.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4606.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4606.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4606.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 4606.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4596.77 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 4580.99 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 4567 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-018500-004 | Diesel | 4565.22 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 4565.22 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 4565.22 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 4565.22 | Item actual | 2025-06-30 | SEC-018000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 4565.22 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 4565.22 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 4560 | Committed | 2025-11-22 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 4560 | Committed | 2025-11-22 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-003 | Fuel | 4560 | Committed | 2025-11-22 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-003 | Fuel | 4560 | Committed | 2025-11-22 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 4560 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 4553 | Committed | 2025-08-17 | Mat014000-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | MIDA-000054 | M-015100-009 | Temporary Water | 4550 | Item actual | 2025-09-30 | SEC-015000 | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000023 | M-015100-009 | Temporary Water | 4550 | Item actual | 2025-10-31 | SEC-015000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4505.71 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 4500 | Item actual | 2025-05-31 | Mat018500-010SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-018 | Project Security | 4500 | Item actual | 2025-05-31 | Mat014100-018SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 4500 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 4500 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 4500 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 4500 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 4500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 4500 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 4500 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 4496.44 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 4481.57 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | SC-096800-001 | Carpeting | 4481.4 | Committed | 2025-07-08 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096800-001 | Carpeting | 4481.4 | Committed | 2025-07-23 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096800-001 | Carpeting | 4481.4 | Committed | 2025-07-23 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 4437 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 4398 | Committed | 2025-08-17 | Mat014000-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | (Blank) |  |  | 4357.18 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4354.85 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-018500-003 | Fuel | 4353.28 | Committed | 2025-11-25 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-004 | Site Accommodation | 4350 | Committed | 2025-11-27 | Mat017100-004SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 4347.82 | Committed | 2025-12-24 | Mat018500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 4338.1 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | M-015100-009 | Temporary Water | 4335 | Committed | 2025-05-21 | SEC-015000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 4320.45 | Committed | 2025-08-12 | SEC-075000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-075100-001 | Built-Up Bituminous Roofing | 4320.45 | Committed | 2025-12-04 | SEC-075000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 4320.45 | Committed | 2025-07-20 | SEC-075000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-019 | Raceway And Boxes - Liquid Tight Flexible Conduit | 4320 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-032100-001 | Reinforcement Bars | 4300 | Committed | 2025-10-27 | SEC-030000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4295.86 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 4285.8 | Item actual | 2025-12-31 | Mat017100-003SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 4280 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 4262.61 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 4255.86 | Committed | 2025-12-02 | SEC-221000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4250 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4250 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4250 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 4250 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 4250 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 4250 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 4250 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-018500-003 | Fuel | 4240.57 | Committed | 2025-11-25 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 4212 | Committed | 2025-12-18 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 4212 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 4212 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 4200 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000001 | M-092500-001 | Other Plastering | 4200 | Committed | 2025-11-13 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 4200 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000136 | Mat014100-009 | Employee Food | 4187.28 | Committed | 2026-01-12 | Mat014100-009SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000136 | Materials / Misc
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 4158 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | M-093400-001 | Waterproofing-Membrane Tiling | 4140 | Committed | 2025-11-25 | SEC-093000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 4112.9 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4108.33 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-046 | Raceway And Boxes - Square Boxes | 4100 | Committed | 2025-11-26 | SEC-120000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 4081 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 4080 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 4071.43 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000087 | Mat014100-017 | Manpower Rental | 4053.75 | Item actual | 2025-05-31 | Mat014100-017SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 4053.75 | Item actual | 2025-05-31 | Mat014100-017SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 4053.75 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 4053.75 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 4050 | Committed | 2025-12-18 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 4050 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 4050 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 4012.37 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014100-018 | Project Security | 4000.24 | Item actual | 2025-01-31 | Mat014100-018SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-018 | Project Security | 4000 | Item actual | 2025-06-30 | Mat014100-018SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 4000 | Expense actual | 2025-11-06 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 4000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 4000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 4000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 4000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 4000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 4000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 4000 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 4000 | Committed | 2025-05-29 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 4000 | Committed | 2025-05-12 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 4000 | Committed | 2025-11-26 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 4000 | Committed | 2025-11-24 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3956.52 | Item actual | 2025-03-31 | SEC-018000 | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3952 | Committed | 2025-05-15 | SEC-018000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3950 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-018500-004 | Diesel | 3934.78 | Item actual | 2025-06-30 | SEC-018000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3934.78 | Item actual | 2025-06-30 | SEC-018000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 3913.04 | Committed | 2025-12-24 | Mat018500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | M-039100-001 | Ready-Mix Concrete | 3910 | Committed | 2025-11-26 | SEC-030000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 3902.62 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 3900 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 3899 | Committed | 2025-12-20 | SEC-116000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 3899 | Committed | 2026-01-12 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116600-001 | Athletic Equipment | 3899 | Committed | 2026-01-22 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 3881.25 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 3881.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-018 | Project Security | 3870.97 | Item actual | 2025-01-31 | Mat014100-018SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 3870.97 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3866.67 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 3857.14 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 3850 | Item actual | 2025-08-31 | Mat017400-004SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 3850 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000144 | Mat014100-009 | Employee Food | 3819.13 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000144 | Materials / Misc
KSA Project | (Blank) | M-018500-004 | Diesel | 3804.35 | Item actual | 2025-02-28 | SEC-018000 | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3804.35 | Item actual | 2025-03-31 | SEC-018000 | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3804.35 | Item actual | 2025-04-30 | SEC-018000 | Item transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3804.35 | Item actual | 2025-04-30 | SEC-018000 | Item transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3804.35 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000129 | M-018500-004 | Diesel | 3804.35 | Item actual | 2025-06-30 | SEC-018000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 3804.35 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3800 | Committed | 2025-11-22 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-003 | Facility Water Distribution-Pvc Pipe | 3800 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3800 | Committed | 2025-05-15 | SEC-018000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3800 | Committed | 2025-05-15 | SEC-018000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 3800 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 3774.2 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3764.06 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3760 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3760 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3760 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3760 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3760 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3760 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3760 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3760 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3760 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3760 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-019 | Raceway And Boxes - Liquid Tight Flexible Conduit | 3760 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3750 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3750 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3750 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 3743.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 3742.2 | Committed | 2025-08-12 | SEC-075000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-075100-001 | Built-Up Bituminous Roofing | 3742.2 | Committed | 2025-12-04 | SEC-075000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 3742.2 | Committed | 2025-07-20 | SEC-075000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 3740 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-015100-009 | Temporary Water | 3740 | Item actual | 2025-12-31 | SEC-015000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 3740 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3700 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 3700 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 3700 | Committed | 2025-07-21 | Mat014300-011SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 3697.5 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3677.42 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3667.1 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014100-009 | Employee Food | 3662.62 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 3653.1 | Item actual | 2025-10-31 | Mat014000-003SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 3640.87 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 3618.97 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 3613.5 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) |  |  | 3612.9 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 3600 | Item actual | 2025-05-31 | Mat017400-004SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 3600 | Item actual | 2025-12-22 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) |  |  | 3600 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3600 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3600 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3600 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3600 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000033 | Mat017100-002 | Mobilization | 3600 | Committed | 2025-10-15 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000033 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 3600 | Committed | 2025-09-17 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 3600 | Committed | 2025-09-07 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000131 | Mat017400-004 | Construction Waste Management And Disposal | 3600 | Committed | 2025-05-20 | Mat017400-004SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 3600 | Committed | 2025-11-26 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 3600 | Committed | 2025-12-20 | SEC-116000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 3600 | Committed | 2026-01-12 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116600-001 | Athletic Equipment | 3600 | Committed | 2026-01-22 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 3588 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3571.43 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000115 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 3570 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000115 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 3538.55 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 3538.32 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-009 | Employee Food | 3537.38 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 3524.2 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 3522.38 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | (Blank) | M-099100-001 | Painting | 3504 | Committed | 2025-11-22 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3500 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3500 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3500 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 3500 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 3500 | Committed | 2025-10-02 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 3498 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 3498 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 3498 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3496 | Committed | 2025-05-15 | SEC-018000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3483.87 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3475.28 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3475.28 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3474.99 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-092100-001 | Plaster And Gypsum Board Assemblies | 3465 | Committed | 2025-11-25 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 3461.4 | Committed | 2025-10-16 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 3447.18 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 3447.18 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000018 | Mat014100-017 | Manpower Rental | 3430 | Committed | 2025-11-02 | Mat014100-017SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000018 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 3424.26 | Item actual | 2025-11-30 | Mat014100-017SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-019 | Raceway And Boxes - Liquid Tight Flexible Conduit | 3420 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3396.03 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3387.1 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3387.1 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3385.86 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 153-001 | Polyethylene Sheeting (For Dust Protection) | 3375 | Committed | 2025-11-26 | SEC-084000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 3375 | Committed | 2025-12-07 | SEC-013000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 3375 | Committed | 2025-12-07 | SEC-013000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 3360 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 3339 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071300-001 | Sheet Waterproofing | 3339 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 3339 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 3333.4 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 3333 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3333 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3333 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3333 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3333 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3333 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3333 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3333 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3333 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014100-009 | Employee Food | 3328.7 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | M-072100-001 | Thermal Insulation | 3320 | Committed | 2025-11-25 | SEC-072000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 3320 | Committed | 2025-12-02 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 3320 | Committed | 2025-12-03 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-064100-001 | Architectural Wood Casework | 3320 | Committed | 2025-12-23 | SEC-064000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 3300 | Item actual | 2025-05-31 | Mat018500-010SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 3300 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 3300 | Committed | 2025-11-26 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 3300 | Committed | 2025-09-21 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000133 |  |  | 3299.94 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3278.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3278.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3278.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 3272.75 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 3268.69 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 3254.16 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 3250 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000149 | Mat017400-001 | Cleaning And Waste Management | 3250 | Item actual | 2025-12-31 | Mat017400-001SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) |  |  | 3250 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3250 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3250 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3250 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3250 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3250 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000149 | Mat017400-001 | Cleaning And Waste Management | 3250 | Committed | 2025-08-17 | Mat017400-001SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3240 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 3240 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 3240 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-009 | Employee Food | 3234.78 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 3207.6 | Committed | 2025-10-21 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 3200 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 3200 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 3200 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3200 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3200 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3200 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 3200 | Committed | 2025-05-20 | Mat017400-004SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) |  |  | 3193.6 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 3175.3 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 3175.3 | Committed | 2025-06-21 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000045 | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 3160 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 3157.11 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 3150 | Item actual | 2025-06-30 | SEC-017000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 3150 | Item actual | 2025-07-31 | Mat017400-004SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 3150 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 3150 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 3150 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3145.16 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3142.89 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 3142.44 | Item actual | 2025-12-22 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 3136.09 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3122.58 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 3113.75 | Item actual | 2025-05-31 | Mat014100-017SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 3113.75 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3112.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3112.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3112.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3112.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3112.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3112.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000023 | M-015100-009 | Temporary Water | 3100 | Item actual | 2025-11-30 | SEC-015000 | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-011 | Employee Transportation | 3100 | Item actual | 2025-11-30 | Mat014100-011SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000133 |  |  | 3093.23 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018900-004 | Site Plumbing Utilities Performance Requirements | 3080 | Item actual | 2025-08-31 | Mat018900-004SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 3077.19 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3066.77 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 3045 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 3044.52 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3043.48 | Item actual | 2025-02-28 | SEC-018000 | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3043.48 | Item actual | 2025-03-31 | SEC-018000 | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 3040 | Committed | 2025-05-15 | SEC-018000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 3040 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 3039.84 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 3020 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000023 | M-015100-009 | Temporary Water | 3000 | Item actual | 2025-10-31 | SEC-015000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) | SC-024100-001 | Demolition | 3000 | Item actual | 2025-11-30 | SEC-420000SC | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-03-31 | Mat014100-025 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-04-30 | Mat014100-025 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-05-31 | Mat014100-025 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-06-30 | Mat014100-025 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-06-30 | Mat014100-025 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-02-28 | Mat014100-025 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 3000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 3000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 3000 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000097 | MM-502010-027 | Fixing Brackets | 3000 | Committed | 2026-01-27 | SEC-502000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000097 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-313100-002 | Termite Control | 3000 | Committed | 2025-04-09 | SEC-313000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-313100-002 | Termite Control | 3000 | Committed | 2025-04-09 | SEC-313000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 3000 | Committed | 2025-10-02 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2991.08 | Committed | 2025-10-02 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 2980 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2975.81 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2970.39 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014500-005 | Testing And Inspecting Services | 2943 | Committed | 2025-04-15 | Mat014500-005SEV | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-018 | Project Security | 2933.33 | Item actual | 2025-06-30 | Mat014100-018SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 2928.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2927.42 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2926.14 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2913.54 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 2905 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2903.23 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2903.23 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2903.23 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2903.23 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2903.23 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2903.23 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2900 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2900 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2898.52 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 2895.18 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2892.85 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2890 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | ME-503010-018 | Raceway And Boxes - Flexible Metal Conduit | 2883.9 | Committed | 2025-11-26 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-054500-001 | Metal Support Assemblies | 2880 | Committed | 2025-11-25 | SEC-054000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-050 | Raceway And Boxes - Ring Extension Square Boxes | 2880 | Committed | 2025-11-26 | SEC-121000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2873.39 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 2871 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | M-036100-001 | Cementitious Grouting | 2870 | Committed | 2025-11-13 | SEC-036000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-036100-001 | Cementitious Grouting | 2870 | Committed | 2025-11-25 | SEC-036000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2863.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2863.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2863.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000066 | M-224100-004 | Flush Tank | 2861.5 | Committed | 2026-01-28 | SEC-224000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000066 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 2850.54 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 2850.54 | Committed | 2025-09-17 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | ME-503020-045 | Cable Trays - Straight Cable Ladder | 2849.44 | Committed | 2025-11-26 | SEC-132000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 2832.11 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2823.6 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-018 | Raceway And Boxes - Flexible Metal Conduit | 2820 | Committed | 2025-11-26 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 2814.76 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2811.05 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2806.45 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2801.97 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 2800 | Item actual | 2025-05-31 | Mat017400-004SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 2800 | Item actual | 2025-10-31 | Mat017400-004SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000023 | M-015100-009 | Temporary Water | 2800 | Item actual | 2025-11-30 | SEC-015000 | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | MIDA-000144 |  |  | 2800 | Expense actual | 2025-01-07 | Mat016500-002 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2800 | Expense actual | 2025-01-07 | Mat016500-002 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 2800 | Committed | 2026-01-25 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | MIDA-000001 | SC-030500-001 | Common Work Results For Concrete | 2800 | Committed | 2025-08-16 | SEC-030000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-030500-001 | Common Work Results For Concrete | 2800 | Committed | 2025-08-16 | SEC-030000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2783.12 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000138 | Mat014500-007 | Testing Laboratory Services | 2770 | Item actual | 2025-05-31 | Mat014500-007SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000138 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2769 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 2760 | Item actual | 2025-12-31 | Mat014100-017SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000045 | M-039100-001 | Ready-Mix Concrete | 2760 | Committed | 2026-01-27 | SEC-030000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000045 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2750 | Item actual | 2025-05-31 | SEC-018000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2750 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2750 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2750 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | SC-036300-001 | Epoxy Grouting | 2750 | Committed | 2025-07-14 | SEC-036000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-036300-001 | Epoxy Grouting | 2750 | Committed | 2025-07-14 | SEC-036000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-036300-001 | Epoxy Grouting | 2750 | Committed | 2025-12-22 | SEC-036000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2747.47 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2735.46 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2729.84 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2727.08 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 2722.5 | Item actual | 2025-10-31 | Mat014000-003SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 2721.84 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2720 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2713 | Expense actual | 2025-04-30 | Mat014100-025 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2706.46 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | MC-50 10 103-001 | Porous Concrete Blocks | 2700 | Committed | 2025-10-27 | SEC-072000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 2700 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 89-001 | Wooden Lattice Panels | 2700 | Committed | 2025-11-26 | SEC-102000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-050 | Raceway And Boxes - Ring Extension Square Boxes | 2700 | Committed | 2025-11-26 | SEC-121000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2697.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2691.61 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2683.47 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 2675.6 | Committed | 2025-08-16 | Mat018500-010SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 2675.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 2675.2 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 2670 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2661.29 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 2660 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 2660 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000113 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 2658.8 | Committed | 2025-11-19 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000113 | Subcontractor / Manpower
KSA Project | MIDA-000138 | Mat014500-007 | Testing Laboratory Services | 2656 | Committed | 2025-04-15 | Mat014500-007SEV | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000138 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2642 | Committed | 2025-05-18 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 2641.53 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 2640 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 2640 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-052100-001 | Steel Joist Framing | 2636.72 | Committed | 2025-11-19 | SEC-052000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 2636.72 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 2636.72 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 2626.75 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2620.57 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2612.5 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2610 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 2600 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2600 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2600 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2600 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2600 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2600 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2600 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2600 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2600 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2600 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MC-50 10 55-001 | Epoxy Tile Adhesive & Grout | 2600 | Committed | 2025-11-25 | SEC-096000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000056 | MC-50 10 55-001 | Epoxy Tile Adhesive & Grout | 2600 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000056 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2600 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 2600 | Committed | 2025-09-28 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) |  |  | 2589.06 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2576.68 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2573 | Committed | 2025-10-02 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat014100-018 | Project Security | 2571.43 | Committed | 2025-07-26 | Mat014100-018SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000133 |  |  | 2555.16 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2551.43 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 2550 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000133 |  |  | 2550 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2550 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000017 | MC-50 10 117-001 | Marble Flooring Tiles | 2550 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 2550 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 2531.18 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 2530 | Committed | 2025-10-23 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2525.8 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 2516.53 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 2507.54 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2503.62 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | SC-134800-001 | Sound, Vibration, And Seismic Control | 2500 | Item actual | 2025-05-31 | SEC-134000SC | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-011 | Safety Training | 2500 | Item actual | 2025-06-30 | Mat014300-011SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2500 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2500 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2500 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-262700-054 | Wiring Devices - Double Pole Switch | 2500 | Committed | 2025-04-19 | SEC-262000 | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-262800-009 | Low-Voltage Circuit Protective Devices - Fused Disconnect Sw | 2500 | Committed | 2025-11-13 | SEC-262000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 2500 | Committed | 2025-11-16 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 2500 | Committed | 2025-10-21 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 2489.6 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 2489.6 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 2489.41 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2488.44 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2483.87 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | SC-347700-001 | Transportation Equipment | 2479.87 | Committed | 2025-04-15 | SEC-340000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-347700-001 | Transportation Equipment | 2479.86 | Committed | 2025-04-15 | SEC-340000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 2475 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 2475 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 2475 | Committed | 2025-08-11 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-015100-009 | Temporary Water | 2450 | Item actual | 2025-12-31 | SEC-015000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 2450 | Committed | 2025-11-25 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2449.61 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-019 | Raceway And Boxes - Liquid Tight Flexible Conduit | 2448 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-05 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-06 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-06 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-06 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-06 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-06 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-06 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-11 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-11 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-11 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-03-19 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-10 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-23 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-23 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-23 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-23 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-04-23 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-05-05 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-23 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-01 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-01 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-04 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-04 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-03 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-01-09 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-01-09 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-01-09 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 2425 | Expense actual | 2025-01-09 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-17 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-23 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-23 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-23 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-08-23 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-09-16 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2425 | Expense actual | 2025-10-21 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2425 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2419.36 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2419.36 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2419.35 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2416.66 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000071 | SC-053300-001 | Aluminum Decking | 2412.65 | Committed | 2025-12-09 | SEC-053000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000071 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2410.71 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2410.24 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2400 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2400 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2400 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000001 | M-092500-001 | Other Plastering | 2400 | Committed | 2025-11-13 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-265100-010 | Interior Lighting - Flood Lighting Fixtures | 2400 | Committed | 2025-11-26 | SEC-265000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-047 | Raceway And Boxes - Square Box Flat Blank | 2400 | Committed | 2025-11-26 | SEC-120000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2400 | Committed | 2025-06-02 | SEC-018000 | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000138 | SC-134800-001 | Sound, Vibration, And Seismic Control | 2400 | Committed | 2025-05-21 | SEC-134000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000138 | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat013500-010 | Owner Safety Requirements | 2400 | Committed | 2025-12-29 | Mat013500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 2391.3 | Item actual | 2025-02-28 | Mat017400-004SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat014100-009 | Employee Food | 2381.72 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 2380 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 2380 | Committed | 2025-11-26 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 2380 | Committed | 2025-11-26 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 2370.31 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-504062-001 | Safety Gloves | 2360 | Committed | 2026-01-27 | SEC-504000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2358.29 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2345.28 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 20 00-010 | Supporting System - Threaded Rod | 2342.76 | Committed | 2025-11-26 | SEC-108000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2340 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2340 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2340 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2340 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2340 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2340 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2340 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2340 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2340 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2340 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2340 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2333.38 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 2325 | Expense actual | 2025-05-12 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2325 | Expense actual | 2025-05-12 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2325 | Expense actual | 2025-05-12 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 2320 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 2312.96 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 2310 | Item actual | 2025-10-31 | Mat014100-017SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 2305 | Item actual | 2025-05-31 | Mat018500-010SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | SC-134800-001 | Sound, Vibration, And Seismic Control | 2300 | Item actual | 2025-05-31 | SEC-134000SC | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 2299.44 | Committed | 2025-12-02 | SEC-221000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 2294.25 | Item actual | 2025-06-30 | Mat014100-017SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 2294.25 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 2294.25 | Committed | 2025-08-05 | Mat014100-017SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 2282.61 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | MIDA-000052 | M-079200-001 | Joint Sealants | 2280 | Committed | 2026-01-27 | SEC-079000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000052 | Subcontractor / Manpower
KSA Project | (Blank) | M-018500-004 | Diesel | 2280 | Committed | 2025-05-15 | SEC-018000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2277.63 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 2277 | Item actual | 2025-05-31 | Mat014100-017SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 2277 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2274.73 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2268.47 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2268.15 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2265.27 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 2255.12 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 2255 | Committed | 2025-12-02 | SEC-117000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2250 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000046 | Mat017400-001 | Cleaning And Waste Management | 2250 | Item actual | 2025-10-31 | Mat017400-001SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000046 | Materials / Misc
KSA Project | MIDA-000046 | Mat017400-001 | Cleaning And Waste Management | 2250 | Item actual | 2025-11-30 | Mat017400-001SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000046 | Materials / Misc
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2250 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2250 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2250 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2250 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2250 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2250 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2250 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 153-001 | Polyethylene Sheeting (For Dust Protection) | 2250 | Committed | 2025-11-13 | SEC-084000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018900-004 | Site Plumbing Utilities Performance Requirements | 2240 | Item actual | 2025-07-31 | Mat018900-004SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 2236.09 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 2232.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2223.68 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2216.13 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 2212.5 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-019 | Raceway And Boxes - Liquid Tight Flexible Conduit | 2212.5 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2211.19 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2200 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2200 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2200 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 2200 | Committed | 2025-11-16 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 2200 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2192.4 | Item actual | 2025-12-21 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 2177.42 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2177.41 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 2175 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000133 |  |  | 2174.99 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2173.33 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 2160 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 2138.4 | Committed | 2025-08-12 | SEC-075000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-075100-001 | Built-Up Bituminous Roofing | 2138.4 | Committed | 2025-12-04 | SEC-075000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 2138.4 | Committed | 2025-07-20 | SEC-075000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 78-001 | Rebar Tie Wire | 2130.1 | Committed | 2025-11-25 | SEC-100000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2125 | Expense actual | 2025-07-01 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2125 | Expense actual | 2025-07-04 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2125 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2125 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2125 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2125 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2125 | Expense actual | 2025-07-03 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2123.47 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 2117.5 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 2113.43 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2104.82 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2102.46 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 2102.1 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 2100 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 2100 | Committed | 2025-11-26 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-015100-009 | Temporary Water | 2100 | Committed | 2025-05-21 | SEC-015000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 2100 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2096.78 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2096.77 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2094.21 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2092.08 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2091.81 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2087 | Committed | 2025-10-02 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2087 | Committed | 2025-10-02 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2087 | Committed | 2025-10-02 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2086.8 | Committed | 2025-10-02 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2086.8 | Committed | 2025-10-02 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2086 | Committed | 2025-10-02 | Mat018500-010SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 2082.32 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-015100-009 | Temporary Water | 2080 | Item actual | 2025-12-31 | SEC-015000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 2080 | Committed | 2025-11-26 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2079.13 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 2071.45 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 2071.45 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2065.41 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 2065 | Committed | 2025-11-13 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 2065 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2056.42 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 2050 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2040.18 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 2040 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | MIDA-000001 | MT-505010-001 | Safety Vest | 2040 | Committed | 2025-10-26 | SEC-340000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat013100-003 | Facility Services Coordination | 2040 | Committed | 2025-08-27 | Mat013100-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | M-018500-004 | Diesel | 2038.22 | Item actual | 2025-06-30 | SEC-018000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 2032.34 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2032.26 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2030.65 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2023.72 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2012.9 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2012.12 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2000 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2000 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2000 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 2000 | Item actual | 2025-07-31 | Mat017400-004SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2000 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 2000 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 2000 | Item actual | 2025-09-30 | Mat017400-004SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 2000 | Item actual | 2025-11-30 | Mat017400-004SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | MIDA-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 2000 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-03-02 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-08 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-14 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-025 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-05-31 | Mat014100-025 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-06-30 | Mat014100-025 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-01-20 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-01-20 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-01-26 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-08-18 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-09-28 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-10-29 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 2000 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 2000 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 2000 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 2000 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 2000 | Committed | 2025-12-08 | Mat019300-004SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 2000 | Committed | 2026-01-05 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2000 | Committed | 2025-05-12 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 2000 | Committed | 2026-01-27 | Mat018500-010SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 1995.16 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1983.87 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 1980 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1979.69 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1973.08 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1971.38 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1965.52 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018900-004 | Site Plumbing Utilities Performance Requirements | 1960 | Item actual | 2025-07-31 | Mat018900-004SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1950 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1950 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 1950 | Committed | 2025-11-22 | SEC-117000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1950 | Committed | 2025-08-16 | Mat018500-010SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 1946.98 | Committed | 2025-12-02 | SEC-221000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1946.37 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 1944 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 1944 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1941.33 | Expense actual | 2025-03-31 | Mat014100-025 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1941.25 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1935.49 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1935.49 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1935.48 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1935.48 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1935.48 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1929.86 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 1919.5 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-016 | Labour Accommodation | 1913.04 | Committed | 2025-11-06 | Mat017100-016SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1900.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | MIDA-000023 | M-015100-009 | Temporary Water | 1900 | Item actual | 2025-09-30 | SEC-015000 | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1900 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1900 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1900 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1900 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1900 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1900 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1900 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 1900 | Committed | 2025-11-22 | SEC-117000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 1900 | Committed | 2025-11-22 | SEC-117000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 1900 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000023 | SC-044200-001 | Exterior Stone Cladding | 1900 | Committed | 2025-12-11 | SEC-044000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1899.59 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000053 | MC-50 10 103-001 | Porous Concrete Blocks | 1890 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000053 | Subcontractor / Manpower
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 1890 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1887.1 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-003 | Facility Water Distribution-Pvc Pipe | 1881 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1877.82 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 1875 | Committed | 2025-11-25 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1866.67 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1864.06 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1861.28 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1850.23 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1850 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1850 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1847.28 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1844.37 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1840.62 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1833.33 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1833.32 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1830.52 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1824.9 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1823 | Expense actual | 2025-03-03 | Mat014100-011 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1812.7 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1809.72 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 1807.27 | Committed | 2025-12-02 | SEC-221000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 1800 | Item actual | 2025-08-31 | Mat014100-017SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1800 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000117 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1800 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000117 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 1800 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 1800 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1800 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1800 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1800 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1800 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 1800 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000135 | Services
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 1800 | Committed | 2025-06-28 | Mat019300-004SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat013100-003 | Facility Services Coordination | 1800 | Committed | 2025-08-27 | Mat013100-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000031 | SC-314100-001 | Shoring | 1800 | Committed | 2025-11-24 | SEC-314000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000031 | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 1795 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1794.69 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1791.38 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1790.32 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1790.32 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1790.32 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1790.32 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1790.32 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1790.32 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1790.32 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1790.32 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1790.32 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1790.32 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1790.32 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1788.34 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1788.33 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1788.33 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1788.33 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1788.33 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1785.43 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1780.66 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1780.65 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1775.22 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1770 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 1770 | Committed | 2025-05-26 | SEC-014000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1769.07 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1762.66 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 1761.19 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 1761.19 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 1759.2 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 1759.2 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 1757.64 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1752.57 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 1750 | Item actual | 2025-06-30 | SEC-017000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1750 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1750 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1750 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1750 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1750 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1750 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-462500-001 | Oil And Grease Separation And Removal Equipment | 1750 | Committed | 2026-01-28 | SEC-460000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1750 | Committed | 2026-01-14 | Mat018500-010SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 |  |  | 1749.79 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1748.75 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000107 | SC-092400-001 | Cement Plastering | 1747.5 | Committed | 2025-09-15 | SEC-092000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000107 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1745.33 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1741.93 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1740.3 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1740 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 |  |  | 1738.79 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 1737.45 | Item actual | 2025-10-31 | Mat014000-003SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | MIDA-000144 | Mat014100-009 | Employee Food | 1732.18 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000144 | Materials / Misc
KSA Project | (Blank) |  |  | 1730.64 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1730.64 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1728.65 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1728.65 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1728.65 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1728.2 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 1728.18 | Committed | 2025-08-12 | SEC-075000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-075100-001 | Built-Up Bituminous Roofing | 1728.18 | Committed | 2025-12-04 | SEC-075000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 1728.18 | Committed | 2025-07-20 | SEC-075000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1726.66 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1726.66 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000046 | Mat018500-010 | Equipment Rental | 1725 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Services
KSA Project | (Blank) | M-092100-001 | Plaster And Gypsum Board Assemblies | 1722 | Committed | 2025-11-25 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1719.38 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000107 | SC-092400-001 | Cement Plastering | 1717.5 | Item actual | 2025-12-22 | SEC-092000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000107 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1709.13 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1706.5 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1700 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1700 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 1700 | Committed | 2025-11-22 | SEC-117000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1700 | Committed | 2025-06-02 | SEC-018000 | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 1700 | Committed | 2025-09-09 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000066 | M-224100-001 | Water Closet-Wc | 1697.5 | Committed | 2026-01-28 | SEC-224000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000066 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1695.04 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1694.95 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1694.11 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1691.94 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-015100-004 | Temporary Fuel Oil | 1690 | Committed | 2025-11-13 | SEC-015000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1688.54 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 1687.5 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 1680 | Committed | 2025-10-21 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 1680 | Committed | 2025-09-09 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 1680 | Committed | 2025-09-21 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000133 |  |  | 1678.23 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1677.73 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1677.42 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1670 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1668.28 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1666.98 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 1660 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 1660 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 1660 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1657.1 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1657.08 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1650 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1650 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1650 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1645.68 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1644.08 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1643.08 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1642.86 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1640 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1633.4 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1629.12 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1623.86 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1623.86 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 1623.42 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 1621.5 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 1620.91 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 1620 | Committed | 2025-12-07 | SEC-013000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 1620 | Committed | 2025-12-07 | SEC-013000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 1620 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 1620 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 1620 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 1620 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1612.9 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 1612.72 | Committed | 2025-12-02 | SEC-221000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1611.29 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1611.29 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1611.28 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1611.28 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 1610 | Committed | 2025-12-20 | SEC-116000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 1610 | Committed | 2026-01-12 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116600-001 | Athletic Equipment | 1610 | Committed | 2026-01-22 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1607.17 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1607.14 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1603.33 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1602.23 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1602.22 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1601.54 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 1600 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 1600 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1600 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1600 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1600 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1600 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | MT-505011-001 | Safety Shoes | 1600 | Committed | 2025-10-26 | SEC-340000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-013600-008 | Printers | 1600 | Committed | 2025-11-13 | SEC-013000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1600 | Committed | 2025-11-25 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 1600 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1600 | Committed | 2025-11-26 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 1600 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000054 | MC-50 10 103-001 | Porous Concrete Blocks | 1600 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | (Blank) | Mat015200-001 | Construction Facilities | 1600 | Committed | 2025-08-26 | Mat015200-001SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 1600 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1600 | Committed | 2026-01-12 | Mat018500-010SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1600 | Committed | 2025-12-22 | Mat018500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1600 | Committed | 2025-12-27 | Mat018500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1600 | Committed | 2025-12-27 | Mat018500-010SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 1599 | Committed | 2025-12-29 | Mat014100-017SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1597.42 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1596.77 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 1596 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1593.75 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1593.71 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1592.24 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 1592 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1589.96 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1589.52 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 1584 | Committed | 2025-12-29 | Mat014100-017SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 1575 | Committed | 2025-12-07 | SEC-013000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-002 | Mobilization | 1567.5 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017100-002 | Mobilization | 1567.5 | Item actual | 2025-12-31 | Mat017100-002SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1566.07 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1565.22 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000066 | M-224100-005 | Wash Basin | 1562.67 | Committed | 2026-01-28 | SEC-224000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000066 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1561.93 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221300-002 | Facility Sanitary Sewerage-Hdpe Pipe | 1560 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 1560 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 1557.78 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1557.15 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1550 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1550 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1550 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 1550 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 1550 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1549.88 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1548.39 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1546.67 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1546.58 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1543.54 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1539.2 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1532.26 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | SC-042500-001 | Unit Masonry Panels | 1530 | Item actual | 2025-12-22 | SEC-042000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1530 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1530 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1530 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 1530 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 1530 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 1530 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1529.7 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1527.6 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1525.73 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1521.99 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1520 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 1520 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1518.82 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1518.68 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000009 | M-079200-001 | Joint Sealants | 1515.15 | Committed | 2026-01-28 | SEC-079000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1511.63 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1509.68 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1508.84 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1508.47 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1508.2 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1508.07 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1504.67 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1504.53 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 1503.77 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1500 | Item actual | 2025-01-31 | Mat018500-010SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1500 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1500 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1500 | Item actual | 2025-06-30 | SEC-018000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1500 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1500 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 1500 | Item actual | 2025-09-30 | Mat014300-011SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1500 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1500 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1500 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1500 | Committed | 2025-11-25 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 1500 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1500 | Committed | 2025-11-26 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-265100-010 | Interior Lighting - Flood Lighting Fixtures | 1500 | Committed | 2025-11-26 | SEC-265000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503750-001 | Electrical Accessories | 1500 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 1500 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 1500 | Committed | 2025-06-28 | Mat019300-004SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 1500 | Committed | 2025-08-31 | Mat019300-004SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 1500 | Committed | 2025-09-10 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 1500 | Committed | 2026-01-05 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | (Blank) |  |  | 1498.33 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1496.78 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1496.78 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000046 | Mat018500-010 | Equipment Rental | 1495 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Services
KSA Project | (Blank) |  |  | 1494.06 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1492.5 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014000-004 | Hand Tools | 1492.18 | Committed | 2025-10-28 | Mat014000-004SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | (Blank) |  |  | 1491.9 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1489.93 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 1487.5 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000054 | MC-50 10 103-001 | Porous Concrete Blocks | 1487.5 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1485 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1480 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1478.83 | Expense actual | 2025-01-18 | Mat014100-011 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 1478.75 | Committed | 2025-11-26 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000009 | MC-50 10 172-001 | Civil Accessories | 1478.75 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1476.97 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1470.97 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1470.94 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1464.96 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 1462.5 | Committed | 2025-12-07 | SEC-013000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-002 | Mobilization | 1459.2 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1455.65 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1452.02 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1451.62 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1451.61 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1451.61 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1451.61 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1451.04 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1450 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1450 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1450 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1450 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 1450 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1446.43 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1445.24 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1445.17 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1444.71 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1444 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1442.31 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1440 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-260519-006 | Low-Voltage Cables - Al/Xlpe/Swa/Pvc | 1440 | Committed | 2025-11-25 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 1440 | Committed | 2025-11-26 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1439.9 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1438.95 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1433.94 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1433.27 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1430 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1429.64 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1428.57 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1428.57 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 1425 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000011 | ME-503750-001 | Electrical Accessories | 1422.2 | Item actual | 2025-12-31 | SEC-255000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 1421 | Committed | 2025-12-20 | SEC-116000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 1421 | Committed | 2026-01-12 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116600-001 | Athletic Equipment | 1421 | Committed | 2026-01-22 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 1419.44 | Committed | 2025-06-22 | Mat014100-018SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Services
KSA Project | (Blank) |  |  | 1418.36 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1416.57 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1413.02 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1412.1 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1410.89 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1410.89 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1407.49 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1406.87 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-092100-001 | Plaster And Gypsum Board Assemblies | 1406.3 | Committed | 2025-11-13 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000054 | M-092100-001 | Plaster And Gypsum Board Assemblies | 1406 | Committed | 2026-01-27 | SEC-092000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1404.95 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-019 | Raceway And Boxes - Liquid Tight Flexible Conduit | 1404 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1403.22 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1401.37 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1400.88 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat017800-020 | Permits and Licenses | 1400 | Item actual | 2025-01-31 | Mat017800-020SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Permits / Government Fees
KSA Project | (Blank) | Mat017800-020 | Permits and Licenses | 1400 | Item actual | 2025-01-31 | Mat017800-020SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Permits / Government Fees
KSA Project | (Blank) | Mat017800-020 | Permits and Licenses | 1400 | Item actual | 2025-01-31 | Mat017800-020SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Permits / Government Fees
KSA Project | MIDA-000133 |  |  | 1400 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-265500-001 | Special Purpose Lighting | 1400 | Committed | 2025-11-25 | SEC-265000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-054500-001 | Metal Support Assemblies | 1400 | Committed | 2025-11-25 | SEC-054000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-054500-001 | Metal Support Assemblies | 1400 | Committed | 2025-11-25 | SEC-054000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 1400 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000135 | Services
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 1400 | Committed | 2026-01-14 | Mat019300-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 1396.38 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 10 50-001 | Filler Board | 1395 | Committed | 2025-11-26 | SEC-095000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1392.62 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1391.13 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1390.12 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1388.51 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1388.51 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221400-009 | Roof Drains-Scupper | 1386 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221400-009 | Roof Drains-Scupper | 1386 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 1380 | Committed | 2026-01-05 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | MIDA-000046 | Mat018500-010 | Equipment Rental | 1380 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Services
KSA Project | MIDA-000046 | Mat018500-010 | Equipment Rental | 1380 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000046 | Services
KSA Project | (Blank) |  |  | 1378.99 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1378.2 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1377.6 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1377.6 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1372.57 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1370.57 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1368.75 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1367.7 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1366.62 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1360.07 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 1360 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-504053-001 | Tile Spacers | 1360 | Committed | 2025-11-26 | SEC-333000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1358.79 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 1355.14 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1354.83 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1353.22 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1351.87 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1350 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1350 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1350 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1350 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1350 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1350 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1350 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1350 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1350 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1350 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 1350 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 1350 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 1350 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000009 | MC-50 10 172-001 | Civil Accessories | 1350 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1345.16 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1340.3 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1333 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1333 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1333 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1333 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1333 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1333 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1333 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1333 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 1332 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 1332 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 1325.04 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1325 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1324.6 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1321.41 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1319.41 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1311.95 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1310.19 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1309.37 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1309.11 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1306.45 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1306.45 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1305.65 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1305 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1305 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1304 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1304 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1303.13 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1301.61 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1300 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 1300 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1300 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1300 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1300 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1300 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1300 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1300 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1300 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1300 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1300 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1300 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1300 | Committed | 2025-11-25 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-504022-001 | Sledgehammer | 1300 | Committed | 2025-11-25 | SEC-323000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 1300 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1300 | Committed | 2025-11-26 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 1300 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1300 | Committed | 2025-06-02 | SEC-018000 | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 1300 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1300 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1300 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1300 | Committed | 2025-06-02 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 1299.01 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | M-013600-033 | Network Cables | 1298 | Committed | 2025-04-17 | SEC-013000 | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1290 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1289.39 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1286.86 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-072100-001 | Thermal Insulation | 1280 | Committed | 2025-11-13 | SEC-072000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1275 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1275 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1271.51 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1269.67 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1266.92 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1265.73 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1262.9 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1262.9 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1262.9 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1262.9 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1262.5 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1261.45 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | MC-50 20 00-003 | Supporting System - Flat Washer | 1261.2 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | M-015100-009 | Temporary Water | 1260 | Item actual | 2025-12-31 | SEC-015000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1260 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-018500-004 | Diesel | 1259.13 | Item actual | 2025-02-28 | SEC-018000 | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1258.07 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1258.06 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1258.06 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1258.06 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1258.06 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1256.67 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1256.66 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1250 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1250 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-03-31 | Mat014100-025 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-04-30 | Mat014100-025 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-05-31 | Mat014100-025 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-06-30 | Mat014100-025 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-02-28 | Mat014100-025 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1250 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1250 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1250 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1250 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1250 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1250 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1250 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1250 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1250 | Committed | 2025-11-25 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1250 | Committed | 2025-11-26 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1246.88 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1242.94 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1240.87 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1239.69 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1239.28 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1229.68 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1227.68 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 1221.66 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 1220.87 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000133 |  |  | 1217.9 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1216.45 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1212.71 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1210.03 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 1210 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1210 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1209.67 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1205.65 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1203.22 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 1200 | Item actual | 2025-05-31 | Mat017400-004SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 1200 | Item actual | 2025-08-31 | Mat017400-004SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1200 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 1200 | Item actual | 2025-10-31 | Mat014300-012SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1200 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1200 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 1200 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1200 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 1200 | Item actual | 2025-12-31 | Mat018500-010SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1200 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1200 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1200 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1200 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 1200 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 1200 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1200 | Committed | 2025-11-26 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-028 | Raceway And Boxes - Insulated Emt Bushing | 1200 | Committed | 2025-11-26 | SEC-117000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000090 | MC-50 20 00-002 | Supporting System - Hexa Nut | 1200 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000090 | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 1200 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000135 | Services
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 1200 | Committed | 2025-06-03 | Mat014300-011SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 1200 | Committed | 2025-06-28 | Mat019300-004SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 1200 | Committed | 2025-08-17 | Mat014000-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 1199.01 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 1193.44 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1190.59 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | MC-50 10 103-001 | Porous Concrete Blocks | 1190 | Committed | 2025-10-23 | SEC-072000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-050 | Raceway And Boxes - Ring Extension Square Boxes | 1190 | Committed | 2025-11-26 | SEC-121000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 1188 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1185.65 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1183.27 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 1180 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 1180 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503750-001 | Electrical Accessories | 1177.8 | Item actual | 2025-12-31 | SEC-255000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1177.63 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1176.21 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 1176 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 1176 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1175.8 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1174.18 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1170 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000009 | MC-50 10 172-001 | Civil Accessories | 1170 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 1170 | Committed | 2025-12-07 | SEC-013000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 1168.7 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) |  |  | 1161.29 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1161.29 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1161.28 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1160.01 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1160.01 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1158.88 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-009 | Domestic Water Piping Specialties-Gate Valve | 1157.65 | Committed | 2025-11-22 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1153.13 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 1152 | Committed | 2025-12-18 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 1152 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 1152 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1150 | Expense actual | 2025-03-11 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1150 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1150 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1150 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1150 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1150 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1150 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1150 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1150 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000149 | ME-503750-001 | Electrical Accessories | 1150 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1150 | Committed | 2025-05-18 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1150 | Committed | 2025-05-18 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-092100-001 | Plaster And Gypsum Board Assemblies | 1148 | Committed | 2025-11-25 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1147.47 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1145.37 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1145.16 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 1144.8 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071300-001 | Sheet Waterproofing | 1144.8 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 1144.8 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-052100-001 | Steel Joist Framing | 1142.58 | Committed | 2025-11-19 | SEC-052000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 1142.58 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000009 | SC-052100-001 | Steel Joist Framing | 1142.58 | Committed | 2025-12-27 | SEC-052000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 1140 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 1137.73 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1137.5 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 1137.39 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) |  |  | 1133.07 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1133.04 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1132.87 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1130.8 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1128.7 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1128.04 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1125 | Item actual | 2025-12-31 | Mat017100-003SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1125 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 1125 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1122.58 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1121.3 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1121.3 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 1120.5 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 1120.5 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 1120.5 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000017 | M-015100-009 | Temporary Water | 1120 | Item actual | 2025-10-31 | SEC-015000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | MIDA-000017 | M-015100-009 | Temporary Water | 1120 | Committed | 2025-05-21 | SEC-015000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 1119.95 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1114.5 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1113.75 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1113.53 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1112.5 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 1110 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 1110 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1106.86 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1104.23 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1102.67 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1100 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1100 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 1100 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1100 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 1100 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 1097.9 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 1095.65 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 1095 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 1095 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000133 |  |  | 1089.85 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1089.38 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1089.38 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 1087.61 | Committed | 2025-06-30 | SEC-053000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 1085.92 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 1085.92 | Committed | 2025-09-17 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) |  |  | 1085.22 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1084.98 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1080.03 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1080 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-054500-001 | Metal Support Assemblies | 1080 | Committed | 2025-11-25 | SEC-054000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 1076.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 1076.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 1074.08 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 1074.08 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 1074.01 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 1071 | Committed | 2025-12-29 | Mat014100-017SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1070.54 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1070.53 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1066.01 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1063.33 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1059.55 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1057.69 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 1056.97 | Committed | 2025-07-17 | SEC-053000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 1053.91 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) |  |  | 1050.05 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000149 | Mat017400-004 | Construction Waste Management And Disposal | 1050 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) |  |  | 1050 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1050 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1050 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1050 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1050 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1050 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1050 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1050 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | MC-50 10 103-001 | Porous Concrete Blocks | 1050 | Committed | 2025-10-23 | SEC-072000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | MT-505011-001 | Safety Shoes | 1050 | Committed | 2025-10-26 | SEC-340000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 122-001 | Epoxy Floor Sealant | 1050 | Committed | 2025-11-25 | SEC-076000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1050 | Committed | 2025-11-25 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 1050 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 1050 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 1050 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1050 | Committed | 2025-11-26 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000054 | MC-50 10 122-001 | Epoxy Floor Sealant | 1050 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 1050 | Committed | 2025-10-07 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) |  |  | 1049.85 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1047.5 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1046.68 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 1043.46 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 1043.35 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1041.22 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1040.04 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1040.04 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1040 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 1040 | Committed | 2025-10-09 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000133 |  |  | 1036.21 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1035.08 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1032.97 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1032.93 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1032.25 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1030.15 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1029.34 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 1028.6 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1026.62 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221100-003 | Facility Water Distribution-Pvc Pipe | 1026 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 1026 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1024.14 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 1023.82 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 1021.5 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071300-001 | Sheet Waterproofing | 1021.5 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 1021.5 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1020.09 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 1020 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 1017 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000054 | MC-50 10 103-001 | Porous Concrete Blocks | 1017 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-004 | Raceway And Boxes - Pvc Female Adaptor | 1016.56 | Committed | 2025-11-26 | SEC-112000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 1016.13 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1015 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1007.11 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1000 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1000 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 1000 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 1000 | Item actual | 2025-09-30 | Mat018500-010SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 1000 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 1000 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 1000 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-013600-008 | Printers | 1000 | Committed | 2025-10-11 | SEC-013000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 1000 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 1000 | Committed | 2025-11-13 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-112800-001 | Office Equipment | 1000 | Committed | 2025-11-13 | SEC-112000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1000 | Committed | 2025-11-25 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 1000 | Committed | 2025-11-26 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 1000 | Committed | 2025-11-26 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-013500-028 | Office Furniture | 1000 | Committed | 2025-11-26 | SEC-013000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 1000 | Committed | 2025-04-09 | Mat014300-012SEV | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 1000 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000135 | Services
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 1000 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000135 | Services
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 1000 | Committed | 2025-08-31 | Mat019300-004SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 1000 | Committed | 2025-08-31 | Mat019300-004SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 1000 | Committed | 2025-09-09 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 1000 | Committed | 2025-12-20 | SEC-116000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116800-001 | Play Field Equipment And Structures | 1000 | Committed | 2026-01-12 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | MIDA-000029 | SC-116600-001 | Athletic Equipment | 1000 | Committed | 2026-01-22 | SEC-116000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000029 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 999.41 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 999.01 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 998.79 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 998.18 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 998 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 997.5 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 996 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 996 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 996 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 995.31 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 992.81 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 991.35 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-013600-008 | Printers | 990 | Committed | 2025-10-22 | SEC-013000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-013600-008 | Printers | 990 | Committed | 2025-10-22 | SEC-013000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-013600-008 | Printers | 990 | Committed | 2025-10-22 | SEC-013000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 988.09 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 987.7 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 987.7 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 987.7 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 987.13 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 986.2 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 985.7 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 985.5 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 985 | Item actual | 2025-12-31 | Mat017100-003SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 984.38 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 984 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 982.82 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 981.25 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 981 | Committed | 2025-12-18 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 981 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 981 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 979.84 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 974.87 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 973.58 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 972 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 972 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 972 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 970.43 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 970 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 967.74 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 967.74 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 967.74 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 967.74 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 967.74 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 967.74 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 967.74 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 967.43 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 966.67 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 966.67 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 966.67 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 966.67 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 966.67 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 966.67 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 966.67 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 966.67 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 964.29 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 964.28 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 961.31 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 961.25 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 960.78 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 960 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 958.05 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 954.69 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 954 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 953.33 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 950 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 950 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 950 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 950 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 950 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000054 | MC-50 10 103-001 | Porous Concrete Blocks | 950 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 950 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 942.51 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 942.31 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 940.94 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000144 |  |  | 940 | Expense actual | 2025-02-28 | Mat014100-019 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦MIDA-000144 | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 940 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 938.38 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 937.5 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 935.48 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 935.48 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 935.48 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 935.48 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 935.48 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 935.48 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 935.48 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 935.35 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 934.41 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 934.41 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 934.41 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 934.41 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 934.41 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 933.53 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 933.34 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 933.34 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 933.33 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 933.33 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 932.02 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 930 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 929.75 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 928.85 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 928.49 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-260526-021 | Grounding And Bonding - Bare Copper Cable | 927 | Committed | 2025-11-25 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 925 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 925 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 924.54 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 924.08 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014100-017 | Manpower Rental | 923 | Item actual | 2025-09-30 | Mat014100-017SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 922.27 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 921.99 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 920.91 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 919.35 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 918.6 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 918.6 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 915.23 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 915 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 915 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 914.63 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 914.5 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 912.96 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000129 | M-018500-003 | Fuel | 912 | Committed | 2026-01-27 | SEC-018000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 911.01 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 908.18 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 908.07 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 907.41 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 907.36 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 905.65 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | Mat014100-018 | Project Security | 903.23 | Item actual | 2025-01-31 | Mat014100-018SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000001 | Services
KSA Project | (Blank) |  |  | 903.22 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 903.22 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 903.22 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 903.22 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 903.22 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 903.22 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 902.15 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 901.08 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 900.57 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 900.01 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 900 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-013600-033 | Network Cables | 900 | Committed | 2025-04-17 | SEC-013000 | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 900 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 900 | Committed | 2025-12-07 | SEC-013000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 900 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 900 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 899.27 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat015400-005 | Temporary Scaffolding And Platforms | 898.8 | Committed | 2025-11-26 | Mat015400-005SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 896.18 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 895.37 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 892.84 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 892.56 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 892.5 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 |  |  | 890.33 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 890.23 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 890.03 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 887.7 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 887.09 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 886.96 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) |  |  | 885 | Expense actual | 2025-03-09 | Mat014100-011 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 884.25 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 882.34 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 880.65 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 880 | Committed | 2025-12-08 | Mat019300-004SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000133 |  |  | 879.81 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 878.34 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 878.04 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 875 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000001 | M-013600-008 | Printers | 875 | Committed | 2025-10-11 | SEC-013000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 875 | Committed | 2025-06-21 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 875 | Committed | 2025-06-21 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 |  |  | 874.65 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 873.79 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 873.6 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000066 | M-224100-018 | Hand Spray | 873 | Committed | 2026-01-28 | SEC-224000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000066 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 870.96 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 870.96 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 870.96 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 869.89 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 869.7 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 869.61 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 868.82 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 868.82 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 868.81 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 867.75 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 867.75 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 865 | Item actual | 2025-03-31 | Mat018500-010SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 864.98 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 864.72 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 864.47 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 863.33 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 860 | Item actual | 2025-12-09 | Mat019300-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 858.46 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 857.85 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 856.92 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 855 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 851.41 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 850 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 850 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 850 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 850 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 850 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 850 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 850 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 850 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 850 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 850 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 846.76 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 846.75 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 846 | Committed | 2025-11-25 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 844.33 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 843.62 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018900-004 | Site Plumbing Utilities Performance Requirements | 840 | Item actual | 2025-07-31 | Mat018900-004SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 840 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 840 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 838.9 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 838.72 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 838.71 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 838.3 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 837.63 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 835.59 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 835.59 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 835.51 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 833.87 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 833.35 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) |  |  | 833.34 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 833.33 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 830.5 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 829.39 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 828.7 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 825.81 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000110 | Mat017400-004 | Construction Waste Management And Disposal | 825 | Item actual | 2025-12-31 | Mat017400-004SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Materials / Misc
KSA Project | (Blank) |  |  | 825 | Expense actual | 2025-03-05 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MT-505012-001 | Safety Glasses | 825 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 825 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 825 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 825 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 823.49 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 823.48 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 822.58 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 822.58 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 822.58 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 822.54 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 821.16 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 821.16 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 821.14 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 820 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 819.01 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 817.84 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 816.6 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 816.54 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 816 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 815.18 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 814.95 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 814.44 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 812.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 812.8 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 811.99 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 810 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-093 | Pvc 45 Elbow | 810 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 810 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 808.89 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 808.48 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 807.15 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 806.01 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 804.3 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 800 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 800 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-03-31 | Mat014100-007 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-06-30 | Mat014100-007 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 800 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 800 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 800 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 800 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 800 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 800 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 800 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 800 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 800 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 800 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 800 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 800 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 800 | Committed | 2025-11-22 | SEC-117000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 800 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 800 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 800 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 800 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 800 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 800 | Committed | 2025-04-09 | Mat014300-012SEV | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 800 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 800 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | MIDA-000001 | Mat014100-017 | Manpower Rental | 800 | Committed | 2025-07-15 | Mat014100-017SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 799.17 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 798.67 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 797.33 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 795.46 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000129 | M-462500-001 | Oil And Grease Separation And Removal Equipment | 795 | Committed | 2026-01-28 | SEC-460000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 794.75 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 792.41 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 792 | Item actual | 2025-10-31 | Mat014000-003SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | (Blank) |  |  | 791.6 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 789.52 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 788.71 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 787.5 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 787.5 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 781.2 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 781.05 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 780 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000133 |  |  | 775.73 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 775.07 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 774.21 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 774.19 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 773.12 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 772.5 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 772.04 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 770.05 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000017 | M-015100-009 | Temporary Water | 770 | Item actual | 2025-10-31 | SEC-015000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 769.38 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000113 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 768.4 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000113 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 766.82 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 765.32 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-099100-001 | Painting | 765 | Committed | 2025-11-22 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 764.05 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 762.9 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 760 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000135 | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 760 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000133 |  |  | 758.33 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 756.86 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 756.51 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 756.05 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 754.65 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 754.04 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 754.04 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 753.41 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014000-003 | Electrical Tools | 752.4 | Committed | 2025-08-17 | Mat014000-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Equipment / Plant
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 750 | Item actual | 2025-02-28 | Mat018500-010SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 750 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-04-30 | Mat014100-021 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-05-31 | Mat014100-021 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-08-31 | Mat014100-021 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 750 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 750 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 750 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 750 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-016500-002 | Materials Transportation | 750 | Committed | 2025-11-25 | SEC-016000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-099100-001 | Painting | 750 | Committed | 2025-11-25 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-020 | Raceway And Boxes - Emt Compression Connector | 750 | Committed | 2025-11-26 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 750 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 750 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 750 | Committed | 2025-09-21 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 750 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 749.6 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 749.6 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 749.32 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 747 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 747 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 747 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 745.16 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 745.15 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 741.91 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 740 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 740 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 738.43 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 738.43 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 734.4 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 734.4 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 734.4 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 733.6 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 730.94 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 728.33 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 727.49 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 726.7 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 726.69 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 725.81 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 725.81 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 725.81 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 725.81 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 725.8 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 724.33 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 722.24 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 722.2 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 721.51 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 720 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 720 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-053 | Raceway And Boxes - Utility Rectangular Boxes | 720 | Committed | 2025-11-26 | SEC-121000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 720 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 720 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 720 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 720 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 720 | Committed | 2025-09-21 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000133 |  |  | 718.93 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 718.75 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 717.14 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 716.14 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 715.75 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 715 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 714.95 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 714.72 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 714.29 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 713.41 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 713.41 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 712.53 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 707.52 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 705.95 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 705.52 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 704.28 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 703.57 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 702.42 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 701.52 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 700.81 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 700 | Item actual | 2025-03-31 | Mat017400-004SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 700 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 700 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 700 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 700 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 700 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 700 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 700 | Committed | 2025-11-25 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 23-001 | High Efficiency Curing Compound | 700 | Committed | 2025-11-26 | SEC-088000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 700 | Committed | 2026-01-25 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 700 | Committed | 2026-01-25 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 700 | Committed | 2025-10-07 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat013100-003 | Facility Services Coordination | 700 | Committed | 2025-08-27 | Mat013100-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000133 |  |  | 697.61 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 697.36 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 696.42 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 695.22 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 694.76 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 693.75 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 692.1 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 692.1 | Committed | 2025-12-02 | SEC-221000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 690.32 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-013600-008 | Printers | 690 | Committed | 2025-10-22 | SEC-013000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 690 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 690 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 687.17 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 684.3 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 683.57 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 683.57 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 683.57 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 683.12 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 680.48 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 678.57 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 678.57 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 677.42 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 677.42 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-018 | Raceway And Boxes - Flexible Metal Conduit | 676.8 | Committed | 2025-11-26 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 676.21 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 675 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 675 | Committed | 2025-12-02 | SEC-014000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-284600-003 | Fire Alarm System - Smoke Detector | 675 | Committed | 2026-01-28 | SEC-284000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 672.38 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 672 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 672 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 671.43 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 668.75 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 20 00-010 | Supporting System - Threaded Rod | 667 | Committed | 2025-11-25 | SEC-108000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 666.87 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 666.44 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 665.71 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 664.7 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 662.54 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 660.86 | Committed | 2025-10-05 | Mat017100-015SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 660 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 660 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 660 | Committed | 2025-12-29 | Mat014100-017SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-009 | Domestic Water Piping Specialties-Gate Valve | 659.12 | Committed | 2025-11-22 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 659.01 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 656.46 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 655.55 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 654.71 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 654.5 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 654.5 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 652.5 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-013500-028 | Office Furniture | 652.5 | Item actual | 2025-05-31 | SEC-013000 | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 652.5 | Committed | 2025-12-18 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 652.5 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | MIDA-000043 | SC-101400-001 | Signage | 652.5 | Committed | 2025-12-21 | SEC-101000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000043 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 650 | Item actual | 2025-03-31 | Mat018500-010SEV | Item transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 650 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 650 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 650 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 650 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 650 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 650 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 650 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 650 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 650 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000144 |  |  | 650 | Expense actual | 2025-01-16 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 650 | Expense actual | 2025-11-09 | Mat016500-002 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000144 | Other
KSA Project | (Blank) | M-323100-001 | Fences And Gates | 650 | Committed | 2025-11-25 | SEC-022000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 650 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 648.96 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 648.96 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 645.16 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 642.39 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 641.52 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 640 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 640 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 640 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 640 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 637.93 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 637.93 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 630.69 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 630.28 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 10 103-001 | Porous Concrete Blocks | 630 | Committed | 2025-11-25 | SEC-072000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000054 | MC-50 10 103-001 | Porous Concrete Blocks | 630 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 629.03 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 626.13 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 625 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000133 |  |  | 625 | Expense actual | 2025-01-18 | Mat014100-011 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 625 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 623.33 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 622.29 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 622 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 620 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 618.68 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 617.76 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 617.74 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 617.5 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 617.5 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 616.87 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 616.67 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 615.97 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 615.42 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 615.42 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-099100-001 | Painting | 614 | Committed | 2025-11-22 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 613.39 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 612.9 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 612.9 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 612.9 | Expense actual | 2025-07-31 | Mat014100-007 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 612.9 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 611.93 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 611.68 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 611.31 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 608.81 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 608.4 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 607.44 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 606.22 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 606.2 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 605.47 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 604.48 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 600.79 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 600 | Item actual | 2025-09-30 | Mat014300-011SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 600 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 600 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | MT-504062-001 | Safety Gloves | 600 | Committed | 2025-10-26 | SEC-335000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 600 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 600 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 600 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-013600-009 | Plotters | 600 | Committed | 2025-11-26 | SEC-013000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 600 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 600 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 600 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 600 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-462500-001 | Oil And Grease Separation And Removal Equipment | 600 | Committed | 2026-01-28 | SEC-460000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-280800-001 | Testing And Commissioning | 600 | Committed | 2025-05-01 | SEC-280000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-280800-001 | Testing And Commissioning | 600 | Committed | 2025-05-01 | SEC-280000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat015200-001 | Construction Facilities | 600 | Committed | 2025-08-26 | Mat015200-001SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 600 | Committed | 2025-08-14 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 600 | Committed | 2025-08-14 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 600 | Committed | 2025-08-14 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 600 | Committed | 2025-08-14 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 597.19 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 595 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 594 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 593.56 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-097 | Pvc - Female Tee | 592.8 | Committed | 2025-12-02 | SEC-285000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000113 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 591.6 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000113 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-045 | Cable Trays - Straight Cable Ladder | 590.08 | Committed | 2025-11-26 | SEC-132000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 588 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 587.5 | Committed | 2025-11-26 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 587.34 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 587.06 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 586.51 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 585 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 585 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 581.57 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 581.56 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 580.65 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 580.65 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 580 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 579.85 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 578.86 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-092100-001 | Plaster And Gypsum Board Assemblies | 577.5 | Committed | 2025-11-25 | SEC-092000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 577.5 | Committed | 2025-11-25 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 576 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000017 | MC-50 10 117-001 | Marble Flooring Tiles | 576 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 576 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-019 | Domestic Water Piping Specialties-Wha | 575.52 | Committed | 2025-11-22 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 575 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 573.99 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 573.2 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 570.8 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 570.8 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 570.8 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 570.8 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 570 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 570 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 570 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000135 | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 570 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 570 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 567.5 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 567.3 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 564.52 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 564 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 563.33 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 560.63 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 559.58 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-096 | Pvc Reducing Adapter | 559.5 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-096 | Pvc Reducing Adapter | 559.5 | Committed | 2025-11-26 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 556.56 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 556.25 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 555.3 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 555 | Expense actual | 2025-11-30 | Mat014100-007 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 554.39 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 554.11 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 554.11 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 550 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 550 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 550 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 550 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 550 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 550 | Committed | 2025-04-17 | SEC-255000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 550 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000149 | ME-503370-001 | Emergency Lights | 550 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 550 | Committed | 2026-01-25 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 549.06 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 548.96 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 547.5 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 547.5 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 544 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 542.96 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 540 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 540 | Committed | 2025-11-16 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-323100-001 | Fences And Gates | 540 | Committed | 2025-11-25 | SEC-022000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 540 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 540 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 540 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 540 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 540 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000113 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 539.4 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000113 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 538.4 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 538.4 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 538.4 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 537.42 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 537.11 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 536.72 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 536.49 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 535.71 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 533.33 | Expense actual | 2025-11-30 | Mat014100-021 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 533.07 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 532.88 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 532 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | MIDA-000028 | SC-125100-001 | Office Furniture | 532 | Committed | 2026-01-21 | SEC-125000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000028 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 531.87 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 531.67 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-323100-001 | Fences And Gates | 530 | Committed | 2025-11-25 | SEC-022000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 528.77 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 526.9 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 526.89 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 525.46 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 525.11 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 525 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 525 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 523.5 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 523.06 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 523.06 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 522.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 522.32 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 519.04 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 516.13 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 516.13 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 20 00-008 | Supporting System - U-Strut Channel | 515.92 | Committed | 2025-11-26 | SEC-108000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 512.89 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-013600-033 | Network Cables | 512 | Committed | 2025-04-17 | SEC-013000 | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 512 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 510.1 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 510 | Committed | 2025-11-13 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 508.77 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 506.81 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 506.46 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 506.25 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000066 | M-224100-012 | Shower Mixer | 504.4 | Committed | 2026-01-28 | SEC-224000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000066 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 504.33 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 504 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MM-502010-093 | Pvc 45 Elbow | 503.5 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 503.23 | Expense actual | 2025-06-30 | Mat014100-021 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 503.23 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 502.97 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 500 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat014100-017 | Manpower Rental | 500 | Item actual | 2025-07-31 | Mat014100-017SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat017400-001 | Cleaning And Waste Management | 500 | Item actual | 2025-09-30 | Mat017400-001SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Materials / Misc
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 500 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 500 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000131 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 500 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 500 | Item actual | 2025-12-31 | Mat017100-003SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-03-31 | Mat014100-025 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-04-30 | Mat014100-022 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-05-31 | Mat014100-022 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-05-31 | Mat014100-025 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-06-30 | Mat014100-025 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-07-31 | Mat014100-022 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-02-28 | Mat014100-025 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 500 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 500 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 500 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-099100-001 | Painting | 500 | Committed | 2025-11-22 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 500 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 500 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 500 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-011 | Safety Training | 500 | Committed | 2025-11-06 | Mat014300-011SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat014300-011 | Safety Training | 500 | Committed | 2025-11-06 | Mat014300-011SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 500 | Committed | 2025-10-07 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat014300-011 | Safety Training | 500 | Committed | 2025-10-29 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 500 | Committed | 2025-06-28 | Mat019300-004SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 500 | Committed | 2025-09-09 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 500 | Committed | 2025-09-09 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 500 | Committed | 2025-09-15 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 500 | Committed | 2025-09-25 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 500 | Committed | 2025-09-25 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) | Mat015700-003 | Temporary Pest Control | 500 | Committed | 2025-08-19 | Mat015700-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 500 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 500 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 499.76 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 498.61 | Expense actual | 2025-03-06 | Mat014100-011 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 498 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 498 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 498 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 498 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 498 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 498 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 497.87 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 495.59 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 495.36 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 495 | Committed | 2025-11-26 | SEC-260000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 493.68 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 492.67 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 492.39 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 491.04 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | M-099100-001 | Painting | 490 | Committed | 2025-11-22 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 488.44 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 487.08 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 486.99 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 486.96 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 486 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 483.87 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 483.87 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 483.87 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 483.87 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 483.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 481.61 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat015400-005 | Temporary Scaffolding And Platforms | 480.9 | Committed | 2025-11-26 | Mat015400-005SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 480 | Committed | 2025-11-25 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 480 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 479.5 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 478.63 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 478.26 | Item actual | 2025-02-28 | Mat017400-004SEV | Item transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 478.26 | Item actual | 2025-04-30 | Mat017400-004SEV | Item transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 478.26 | Item actual | 2025-04-30 | Mat017400-004SEV | Item transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 478.26 | Committed | 2025-08-12 | Mat017400-004SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | MM-502010-097 | Pvc - Female Tee | 475.64 | Committed | 2025-12-02 | SEC-285000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 475.6 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 475 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 475 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 474.68 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 472.6 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 469.91 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 469.91 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 468.75 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 467.99 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 467.99 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 467.74 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 467.2 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 467.2 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 467.2 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 466.53 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 466.35 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 466.31 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 465.72 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 465.28 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 463.7 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 460.8 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 460.8 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 460.8 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-046 | Raceway And Boxes - Square Boxes | 460 | Committed | 2025-11-26 | SEC-120000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 459.98 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 458.34 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 457.86 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 456.25 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 456.25 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 455.76 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 455.76 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 454.45 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 453.57 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 452.84 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 452.84 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 452.14 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 451.61 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 451.61 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 451.61 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-004 | Raceway And Boxes - Pvc Female Adaptor | 451.3 | Committed | 2025-11-26 | SEC-112000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-03-31 | Mat014100-025 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-04-30 | Mat014100-025 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-05-31 | Mat014100-025 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-06-30 | Mat014100-025 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-02-28 | Mat014100-025 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 450 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 450 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 450 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-236300-001 | Refrigerant Condensers | 450 | Committed | 2025-11-13 | SEC-236000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 450 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 450 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000053 | MC-50 10 103-001 | Porous Concrete Blocks | 450 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000053 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 450 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 450 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 450 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 450 | Committed | 2025-09-10 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 449.75 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 449.75 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 449.75 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 449.58 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 449.09 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 448.14 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 443.64 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221100-009 | Domestic Water Piping Specialties-Gate Valve | 442.23 | Committed | 2025-11-22 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 440 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 437.8 | Committed | 2025-12-08 | Mat019300-004SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) | MC-50 10 122-001 | Epoxy Floor Sealant | 437.5 | Committed | 2025-11-25 | SEC-076000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000054 | MC-50 10 122-001 | Epoxy Floor Sealant | 437.5 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000054 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 437.5 | Committed | 2025-06-21 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 437.5 | Committed | 2025-06-21 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000133 |  |  | 436.67 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 436.35 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 436.35 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 436.29 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 435 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 435 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 434.44 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 433.33 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 432 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 432 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 431.25 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 427.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 425.79 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 425 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 425 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 425 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 424.19 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-003 | Facility Water Distribution-Pvc Pipe | 424 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 423.92 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 421.94 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 421.2 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 420.09 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 420 | Committed | 2025-11-25 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 420 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | M-262700-033 | Wiring Devices - Lighting Switches | 420 | Committed | 2026-01-28 | SEC-262000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000017 | M-015100-009 | Temporary Water | 420 | Committed | 2025-05-21 | SEC-015000 | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000017 | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 420 | Committed | 2025-09-15 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 420 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | (Blank) |  |  | 419.35 | Expense actual | 2025-08-31 | Mat014100-022 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 419.35 | Expense actual | 2025-12-31 | Mat014100-022 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 418.89 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 418.89 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 418.5 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 418.15 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 418.15 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 417.74 | Expense actual | 2025-10-31 | Mat014100-007 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 417.42 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 417.42 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 417.42 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 415.34 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 413.39 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000144 |  |  | 413 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 413 | Expense actual | 2025-01-13 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 413 | Expense actual | 2025-01-13 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | (Blank) |  |  | 413 | Expense actual | 2025-09-28 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 413 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 413 | Expense actual | 2025-10-08 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 412.82 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 412.1 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 412.1 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 410.5 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 410 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 410 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 410 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 410 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 410 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 410 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 409.94 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 406.56 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 404.3 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 403.05 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 402.22 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 402.21 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 402.01 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 402.01 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 400.14 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 400 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 400 | Item actual | 2025-11-30 | Mat018500-010SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 400 | Item actual | 2025-12-31 | Mat014300-012SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 400 | Item actual | 2025-12-31 | Mat014300-012SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-05-26 | Mat014100-032 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-03-31 | Mat014100-025 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-04-30 | Mat014100-025 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-06-30 | Mat014100-025 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-02-28 | Mat014100-025 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-09-30 | Mat014100-007 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 400 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 400 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 400 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 400 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 400 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 400 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 400 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 400 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | MT-505014-001 | Hard Hat (Helmet) | 400 | Committed | 2025-10-26 | SEC-340000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 400 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 400 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-112800-001 | Office Equipment | 400 | Committed | 2025-11-13 | SEC-112000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 400 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 400 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 400 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 400 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 400 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 400 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 400 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 400 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 400 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 400 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 400 | Committed | 2026-01-25 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 400 | Committed | 2025-04-09 | Mat014300-012SEV | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 400 | Committed | 2025-08-31 | Mat019300-004SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 400 | Committed | 2025-08-31 | Mat019300-004SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 400 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 400 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 400 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 400 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 400 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | (Blank) | Mat015700-003 | Temporary Pest Control | 400 | Committed | 2025-08-19 | Mat015700-003SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 400 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 400 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 400 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 400 | Committed | 2025-09-22 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 400 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | MIDA-000130 | Mat017800-012 | Spare Parts | 400 | Committed | 2025-12-23 | Mat017800-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 400 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 397.81 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 396.43 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000129 | M-462500-001 | Oil And Grease Separation And Removal Equipment | 396 | Committed | 2026-01-28 | SEC-460000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000129 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 395.59 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 395.12 | Committed | 2026-01-05 | Mat019300-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 393.3 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 392.84 | Expense actual | 2025-02-28 | Mat014100-022 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 392.64 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 392.52 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-015100-004 | Temporary Fuel Oil | 392 | Committed | 2025-11-13 | SEC-015000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 390.3 | Item actual | 2025-12-31 | SEC-221000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 390.25 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 390 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 390 | Committed | 2026-01-14 | Mat019300-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 390 | Committed | 2026-01-14 | Mat019300-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 387.5 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 387.1 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 387.1 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 387.1 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 386.67 | Expense actual | 2025-05-31 | Mat014100-025 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 386.67 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 | Mat014100-009 | Employee Food | 386.09 | Item actual | 2025-12-31 | Mat014100-009SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Materials / Misc
KSA Project | (Blank) |  |  | 385.74 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 385.02 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 380 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-097 | Pvc - Female Tee | 380 | Committed | 2025-11-25 | SEC-285000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 380 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 380 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 380 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 380 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 380 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 378 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 378 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 378 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 375 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 375 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 375 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 375 | Committed | 2025-11-25 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 375 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 375 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 375 | Committed | 2025-11-26 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 374.65 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 374 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 373.62 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MM-502010-097 | Pvc - Female Tee | 372.24 | Committed | 2025-11-25 | SEC-285000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 370 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-009 | Domestic Water Piping Specialties-Gate Valve | 368.85 | Committed | 2025-11-22 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat018500-010 | Equipment Rental | 365.3 | Committed | 2025-07-09 | Mat018500-010SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000131 | Services
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 360 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 360 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 360 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 360 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 360 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 360 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000011 | M-262700-033 | Wiring Devices - Lighting Switches | 360 | Committed | 2026-01-28 | SEC-262000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 360 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 360 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 360 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 360 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 360 | Committed | 2025-09-15 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 360 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 360 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000113 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 359.6 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000113 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 357 | Item actual | 2025-06-30 | Mat018500-010SEV | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 356.55 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 356.45 | Item actual | 2025-09-30 | Mat017100-015SEV | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 352.53 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 352.53 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000009 | MC-50 10 172-001 | Civil Accessories | 352.5 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 351.42 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350.57 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat017400-004 | Construction Waste Management And Disposal | 350 | Item actual | 2025-05-31 | Mat017400-004SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 350 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 350 | Item actual | 2025-10-31 | Mat018500-010SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 350 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | M-015100-009 | Temporary Water | 350 | Item actual | 2025-12-31 | SEC-015000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-03-31 | Mat014100-025 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-04-30 | Mat014100-025 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-05-31 | Mat014100-025 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-06-30 | Mat014100-025 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-07-31 | Mat014100-025 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-02-28 | Mat014100-025 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 350 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 350 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 350 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 350 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 350 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 350 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 350 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 350 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 350 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 350 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 350 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 350 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-265200-003 | Safety Lighting - Exit Signs | 350 | Committed | 2026-01-28 | SEC-265000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 350 | Committed | 2026-01-25 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 350 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 350 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 350 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 348.38 | Expense actual | 2025-05-31 | Mat014100-007 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 348.34 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 347.98 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 347.85 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 347.85 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 347.85 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 347.85 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 347.85 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-005 | Testing And Inspecting Services | 345.8 | Item actual | 2025-01-31 | Mat014500-005SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 342 | Expense actual | 2025-09-28 | Mat014100-011 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 341.88 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 341.4 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000113 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 341 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000113 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 340.2 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 340.2 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 340 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 340 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 340 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 340 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 340 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 340 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 340 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000066 | M-224100-011 | Wash Basin Mixer | 339.5 | Committed | 2026-01-28 | SEC-224000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000066 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 339.12 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 338.33 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 337.84 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 337.5 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | MT-504053-001 | Tile Spacers | 336 | Committed | 2025-11-26 | SEC-333000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 335.77 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 335.65 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 335.65 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 335.48 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 335.07 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 332.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 332.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000133 |  |  | 330.03 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 330 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-504053-001 | Tile Spacers | 330 | Committed | 2025-11-26 | SEC-333000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 326.61 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 325.63 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 325.41 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 325 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 325 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 324.53 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 324.53 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 324.01 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 322.58 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 322.58 | Expense actual | 2025-03-31 | Mat014100-021 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 322.58 | Expense actual | 2025-04-30 | Mat014100-025 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 321.24 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 320.34 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 320 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 320 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 317.14 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 316.4 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 315.53 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 314.52 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 314.52 | Expense actual | 2025-12-31 | Mat014100-021 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 313.24 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 310 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 308.84 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 308.33 | Expense actual | 2025-04-30 | Mat014100-007 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 306.45 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 303.75 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-004 | Raceway And Boxes - Pvc Female Adaptor | 302.4 | Committed | 2025-11-26 | SEC-112000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 302.09 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 302.09 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-011 | Safety Training | 300 | Item actual | 2025-05-31 | Mat014300-011SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat014300-011 | Safety Training | 300 | Item actual | 2025-05-31 | Mat014300-011SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 300 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 300 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 300 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 300 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 300 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 300 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 300 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 300 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505048-001 | Breathing Mask (Full Face) | 300 | Committed | 2025-11-13 | SEC-350000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 300 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 300 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-016500-002 | Materials Transportation | 300 | Committed | 2025-11-25 | SEC-016000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 300 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 300 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 300 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 300 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 300 | Committed | 2026-01-28 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-280800-001 | Testing And Commissioning | 300 | Committed | 2025-05-01 | SEC-280000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 300 | Committed | 2025-10-23 | Mat017100-002SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 300 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 300 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 300 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 300 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 299.25 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 297.12 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 297 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 295.65 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 294 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 294 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-001 | Supporting System - Hexa Bolt | 293.76 | Committed | 2025-11-26 | SEC-105000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-014 | Supporting System - Anchor Bolt | 293.76 | Committed | 2025-11-26 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 293.53 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 293.5 | Committed | 2025-12-02 | SEC-221000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 292 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) |  |  | 290.33 | Expense actual | 2025-01-31 | Mat014100-007 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 290.32 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 290.32 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 290.32 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 290.32 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 290.32 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 290 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 290 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 290 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 290 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221100-003 | Facility Water Distribution-Pvc Pipe | 290 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 290 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 289.29 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 288 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 288 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 287.5 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 286.54 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 285.8 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 285.71 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 285.71 | Expense actual | 2025-02-28 | Mat014100-007 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 285.4 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 285.4 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 285.4 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 285.4 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 285.4 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 285.4 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 285.18 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 285.18 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 285 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 282.26 | Expense actual | 2025-01-31 | Mat014100-025 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 281.5 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 281.25 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat018900-004 | Site Plumbing Utilities Performance Requirements | 280 | Item actual | 2025-05-31 | Mat018900-004SEV | Item transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000133 |  |  | 280 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 280 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 280 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 280 | Committed | 2025-07-14 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 280 | Committed | 2025-07-20 | SEC-096000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-096200-001 | Specialty Flooring | 280 | Committed | 2025-09-28 | SEC-096000SC | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 279 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 279 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 279 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 278.28 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 278.28 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 278.28 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 278.28 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 278.28 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 278.28 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 275 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 275 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 275 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 275 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 275 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-045 | Cable Trays - Straight Cable Ladder | 273.96 | Committed | 2025-11-26 | SEC-132000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 272 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 272 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 272 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 270.8 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 270.65 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 270.05 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 270 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 270 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 270 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 270 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 270 | Committed | 2025-10-07 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 270 | Committed | 2025-10-21 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 270 | Committed | 2025-10-21 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 268.23 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 266.67 | Expense actual | 2025-11-30 | Mat014100-022 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 266 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 261 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 260 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 260 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 260 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 258.07 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 258.05 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 257.4 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 257.37 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 256 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 256 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 255 | Committed | 2025-11-13 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-230700-013 | Duct Tape | 255 | Committed | 2025-11-25 | SEC-230000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 255 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 254.14 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 253.36 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 252.88 | Committed | 2025-12-08 | Mat019300-004SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 251.83 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 251.83 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) | M-262700-018 | Wiring Devices - Single Socket Outlet 13A Switched Wheather | 251 | Committed | 2025-04-19 | SEC-262000 | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-045 | Cable Trays - Straight Cable Ladder | 250.5 | Committed | 2025-11-26 | SEC-132000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 250 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 250 | Item actual | 2025-07-31 | Mat014300-012SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 250 | Item actual | 2025-07-31 | Mat014300-012SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 250 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 250 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 250 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 250 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 250 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000009 | MC-50 10 172-001 | Civil Accessories | 250 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 250 | Committed | 2026-01-25 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | (Blank) | Mat014300-011 | Safety Training | 250 | Committed | 2025-11-06 | Mat014300-011SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000046 | Mat017400-001 | Cleaning And Waste Management | 250 | Committed | 2025-08-17 | Mat017400-001SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000046 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 250 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 250 | Committed | 2025-10-21 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 250 | Committed | 2025-10-21 | Mat014300-011SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 250 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 250 | Committed | 2025-09-15 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 250 | Committed | 2025-09-28 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000110 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 249.3 | Item actual | 2025-12-31 | SEC-111000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 248.39 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 247.82 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 247 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 247 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 245.52 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 244.96 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 243 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.94 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 241.94 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 241.94 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 241.94 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 241.94 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 241.94 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 241.94 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 241.67 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 241.67 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 241.67 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 241.67 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 241.67 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 240 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 240 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 240 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 240 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 240 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-323100-001 | Fences And Gates | 240 | Committed | 2025-11-25 | SEC-022000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 240 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 238.7 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 237.53 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | SC-023200-003 | Material Testing | 237.5 | Item actual | 2025-06-30 | SEC-410000SC | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 237.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 235.2 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 235.15 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 235.15 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-045 | Cable Trays - Straight Cable Ladder | 235.04 | Committed | 2025-11-26 | SEC-132000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 234.96 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 234.96 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 234.56 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 234 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 233.88 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.88 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.88 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.88 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.88 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.88 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 233.88 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 233.88 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 233.88 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 233.61 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.61 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.61 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 233.61 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 233.61 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 233.54 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.34 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 233.34 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 233.34 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 233.34 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 232.6 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 232.25 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 230.78 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 230.01 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 230.01 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | MIDA-000149 | Mat017100-002 | Mobilization | 230.01 | Item actual | 2025-11-30 | Mat017100-002SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000149 | Materials / Misc
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 230 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 230 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 229.95 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 229.14 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 228.88 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 228.33 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 225.82 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 225.82 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 225.81 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 225.55 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 225.55 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 225.55 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 225.55 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 225.28 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 225.28 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 225 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 225 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 225 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 225 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 225 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 225 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000133 |  |  | 224.13 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 224.08 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 223.18 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 222.36 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 221.88 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 221.56 | Committed | 2026-01-05 | Mat019300-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 221.36 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 221 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 220 | Committed | 2025-07-31 | SEC-255000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 220 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 220 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 219.44 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 219.15 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 219 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 218.27 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 218.27 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 218.27 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 218.27 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 217.76 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 217.75 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 217.75 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 217.74 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 217.74 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 217.39 | Item actual | 2025-06-30 | SEC-014000 | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-003 | Facility Water Distribution-Pvc Pipe | 217 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 216.95 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 216.95 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 216.95 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 216.81 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 216.67 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 216 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 216 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 215.71 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 213.78 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 213.75 | Committed | 2025-09-17 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 212.5 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 212.3 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-016500-002 | Materials Transportation | 212 | Committed | 2025-11-13 | SEC-016000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 211.2 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 210 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 210 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221400-009 | Roof Drains-Scupper | 210 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 210 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 210 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 209.42 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 208.71 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 208.71 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 208.71 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 208.71 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 208.71 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 208.71 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 208.71 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 208.59 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 208.33 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 207.25 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 207.2 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 206.45 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 206.33 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 206.25 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 206.12 | Committed | 2025-12-08 | Mat019300-004SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 205.92 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat015400-005 | Temporary Scaffolding And Platforms | 205.8 | Committed | 2025-11-26 | Mat015400-005SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 205.5 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 205.2 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 205.2 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-014 | Supporting System - Anchor Bolt | 204 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 204 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 204 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 204 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 203.55 | Item actual | 2025-11-30 | Mat017100-015SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 203.44 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 203.22 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 202.2 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 201.68 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 201.63 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 201.37 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200.56 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 200 | Item actual | 2025-07-31 | Mat014300-012SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000023 | M-015100-009 | Temporary Water | 200 | Item actual | 2025-10-31 | SEC-015000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 200 | Item actual | 2025-12-31 | Mat014300-012SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 200 | Item actual | 2025-12-31 | Mat014300-012SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 200 | Item actual | 2025-12-31 | Mat014300-012SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 200 | Item actual | 2025-12-31 | Mat014300-012SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 200 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-14 | Mat014100-032 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-03-31 | Mat014100-023 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-022 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-08-31 | Mat014100-025 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 200 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 200 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | MT-505048-001 | Breathing Mask (Full Face) | 200 | Committed | 2025-10-26 | SEC-350000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-230700-013 | Duct Tape | 200 | Committed | 2025-11-13 | SEC-230000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 200 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-002 | Facility Sanitary Sewerage-Hdpe Pipe | 200 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 200 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 200 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 200 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 200 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 200 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 200 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 200 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-280800-001 | Testing And Commissioning | 200 | Committed | 2025-05-01 | SEC-280000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-280800-001 | Testing And Commissioning | 200 | Committed | 2025-05-01 | SEC-280000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-280800-001 | Testing And Commissioning | 200 | Committed | 2025-05-01 | SEC-280000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-280800-001 | Testing And Commissioning | 200 | Committed | 2025-05-01 | SEC-280000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 200 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 200 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 200 | Committed | 2025-06-03 | Mat014300-012SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 200 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 200 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 200 | Committed | 2025-09-22 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 200 | Committed | 2025-09-22 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 200 | Committed | 2025-09-22 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 200 | Committed | 2025-09-22 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 200 | Committed | 2025-09-22 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 200 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 200 | Committed | 2025-07-21 | Mat014300-011SEV | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 200 | Committed | 2026-01-05 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | (Blank) |  |  | 199.97 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 199.5 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 199.5 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 199.2 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 198.8 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 198.66 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 198 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 198 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 196 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 196 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 195.03 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 195 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 194.88 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 193.76 | Committed | 2026-01-05 | Mat019300-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 193.57 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.55 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 193.55 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.55 | Expense actual | 2025-12-31 | Mat014100-007 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.55 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.55 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.55 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 193.33 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.33 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 193.33 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 193.33 | Expense actual | 2025-11-30 | Mat014100-025 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 192.86 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 192.75 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000110 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 192 | Item actual | 2025-12-31 | SEC-111000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 190.4 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 190 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000135 | Mat014300-012 | Safety 3rd Party Testing | 190 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000135 | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 190 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 190 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 190 | Committed | 2025-08-11 | Mat014300-012SEV | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 189 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-092 | Pvc Male Adapter | 189 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 189 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 187.5 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 187.1 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 187.1 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 187.1 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 187.1 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 187.1 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 187.1 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 187.1 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 187.1 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 186.88 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 186.88 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 186.88 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 186.88 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 186.88 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 186.88 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 186.88 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 186.66 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 186.66 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 186.41 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 185.49 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 185.48 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 185.25 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 184.7 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 184.7 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 184.1 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 182.88 | Committed | 2025-11-25 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 182.5 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 182.5 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) | MM-502010-093 | Pvc 45 Elbow | 182.25 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | ME-503010-012 | Raceway And Boxes - Pvc Bend Heavy Gauge | 180.9 | Item actual | 2025-12-31 | SEC-114000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 180.65 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 180.65 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 180.65 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 180.65 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 180.65 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 180.65 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 180.43 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 180.21 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503480-001 | Cable Sleeving | 180 | Committed | 2025-04-17 | SEC-237000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 180 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 180 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 180 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 180 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 180 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 180 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 180 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 179.99 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 179.99 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 179.99 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 178.8 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 178.7 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 178.58 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 177.6 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 177.45 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 175.2 | Committed | 2025-11-25 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 175 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 175 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 175 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 175 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 175 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 174.6 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 174.2 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 173.98 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 173.9 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 173.9 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 173.9 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 173.77 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 173.76 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 173.76 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 173.54 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 173.54 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 173.33 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 173.32 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 173.32 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 173.32 | Expense actual | 2025-09-30 | Mat014100-025 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 171.5 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MT-504053-001 | Tile Spacers | 171 | Committed | 2025-11-26 | SEC-333000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 171 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 171 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 171 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 170.63 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 170 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 170 | Expense actual | 2025-06-30 | Mat014100-023 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 170 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 170 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 170 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 170 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 170 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 170 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 170 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505011-001 | Safety Shoes | 170 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 170 | Committed | 2026-01-28 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000133 | Mat014100-017 | Manpower Rental | 169.65 | Item actual | 2025-11-30 | Mat014100-017SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 169.36 | Expense actual | 2025-01-31 | Mat014100-021 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 169.36 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 168.74 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 168.66 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 168.4 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 168.4 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 168 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 168 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 167.74 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 167.74 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 167.64 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 167.53 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 166.68 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 166.67 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 166.66 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 165 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 165 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 165 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 164.25 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 164.05 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 163.96 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-05 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-05 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-11 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-11 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-11 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-19 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-03-05 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-10 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-23 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-23 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-23 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-27 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-05-11 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-05-11 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-05-11 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-05-11 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-01-02 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-07-23 | Mat003100-048 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-01-05 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 163 | Expense actual | 2025-01-09 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-08-23 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-08-23 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-08-23 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-09-16 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 163 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 163 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 162.5 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-03-05 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-03-05 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-03-05 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-03-16 | Mat003100-048 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-04-10 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-04-28 | Mat003100-048 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-05-11 | Mat003100-048 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-06-29 | Mat003100-048 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-09-07 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-02-28 | Mat003100-048 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-04 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-05 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-09-09 | Mat003100-048 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-01-05 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-01-05 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-01-05 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-01-05 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-01-09 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-01-09 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000144 |  |  | 162 | Expense actual | 2025-01-09 | Mat003100-048 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦MIDA-000144 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-08-20 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-08-23 | Mat003100-048 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-10-04 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-10-21 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 162 | Expense actual | 2025-10-19 | Mat003100-048 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-04 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 162 | Expense actual | 2025-11-06 | Mat003100-048 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000001 | MC-50 10 165-001 | Warning Tape | 162 | Committed | 2025-10-26 | SEC-086000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 162 | Committed | 2025-11-25 | SEC-101000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 161.69 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 161.69 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 161.29 | Expense actual | 2025-08-31 | Mat014100-023 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 160.86 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 160.56 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 160 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 160 | Committed | 2025-11-25 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 160 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505010-001 | Safety Vest | 160 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-280800-001 | Testing And Commissioning | 160 | Committed | 2025-05-01 | SEC-280000SC | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 160 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 160 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 159.6 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 159.12 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000009 | MC-50 10 172-001 | Civil Accessories | 156 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000009 | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 155.36 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 155.36 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 155.32 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 154.83 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 154.83 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 154.62 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 154.58 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 154.5 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 154.41 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 154 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 154 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 154 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 153.3 | Committed | 2025-06-28 | Mat018500-010SEV | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 153.23 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 153.23 | Expense actual | 2025-07-31 | Mat014100-021 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 152 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 152 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 152 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 152 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 152 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 151.91 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 151.91 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 150 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | Mat014300-012 | Safety 3rd Party Testing | 150 | Item actual | 2025-07-31 | Mat014300-012SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 150 | Item actual | 2025-11-30 | Mat017100-003SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 150 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 150 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 150 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 150 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 150 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 150 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 150 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 150 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 150 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 150 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 150 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 150 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 150 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 150 | Committed | 2025-09-25 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 150 | Committed | 2025-09-25 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 150 | Committed | 2025-09-25 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 150 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 148.5 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 148.48 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 148.41 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 145.4 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 145.2 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 145.16 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 145.16 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 144.57 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 144.36 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 144 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 144 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 144 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 143.43 | Expense actual | 2025-03-31 | Mat014100-022 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | SC-023200-003 | Material Testing | 142.5 | Item actual | 2025-06-30 | SEC-410000SC | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | SC-023200-003 | Material Testing | 142.5 | Item actual | 2025-06-30 | SEC-410000SC | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | SC-023200-003 | Material Testing | 142.5 | Item actual | 2025-06-30 | SEC-410000SC | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | SC-023200-003 | Material Testing | 142.5 | Item actual | 2025-06-30 | SEC-410000SC | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | SC-023200-003 | Material Testing | 142.5 | Item actual | 2025-06-30 | SEC-410000SC | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 142.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 142.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 142.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 142.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 142.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 141.9 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 140 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 140 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 140 | Committed | 2025-11-25 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 140 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 140 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 140 | Committed | 2025-11-26 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 140 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 140 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | Mat017100-003 | Site Mobilization | 140 | Committed | 2025-09-02 | Mat017100-003SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 139.86 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 139.14 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 139.14 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 139.14 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 139.14 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 139.14 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-013 | Safety Protective Equipment | 139.14 | Committed | 2025-11-25 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 139.14 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 139.14 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 139.14 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 139.14 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 139.06 | Committed | 2026-01-26 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 138 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 137.16 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 136.09 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 135.74 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 135.7 | Item actual | 2025-11-30 | Mat017100-015SEV | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 135 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 135 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 134.38 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 133 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 133 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-099100-001 | Painting | 131.5 | Committed | 2025-11-22 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-099100-001 | Painting | 131.5 | Committed | 2025-11-25 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 131.32 | Committed | 2025-12-08 | Mat019300-004SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 131.19 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-096 | Pvc Reducing Adapter | 130.68 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-096 | Pvc Reducing Adapter | 130.68 | Committed | 2025-11-26 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 130.04 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 130.04 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 130 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 130 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000149 | ME-503750-001 | Electrical Accessories | 130 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 129.85 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 129.85 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 129.85 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 129.85 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 129.68 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | Mat015400-005 | Temporary Scaffolding And Platforms | 129.15 | Committed | 2025-11-26 | Mat015400-005SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 128.59 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 128.5 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 128 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 128 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 128 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 128 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000110 | ME-503010-012 | Raceway And Boxes - Pvc Bend Heavy Gauge | 127.8 | Item actual | 2025-12-31 | SEC-114000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-045 | Cable Trays - Straight Cable Ladder | 126.44 | Committed | 2025-11-26 | SEC-132000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 126 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 126 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 126 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 126 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 126 | Committed | 2025-11-04 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 125.04 | Committed | 2025-12-02 | SEC-283000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 125 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503010-025 | Raceway And Boxes - Emt Strap Clamp 1-Hole ( C Clamp) | 125 | Committed | 2025-11-16 | SEC-116000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 125 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 125 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 124.8 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 124.8 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 124.8 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 122.58 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 122.58 | Expense actual | 2025-07-31 | Mat014100-023 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-093 | Pvc 45 Elbow | 121.16 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-093 | Pvc 45 Elbow | 121.16 | Committed | 2025-11-26 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 120 | Item actual | 2025-08-31 | Mat018500-010SEV | Item transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 120 | Expense actual | 2025-09-30 | Mat014100-023 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 120 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 120 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 120 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 120 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 120 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 120 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 120 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 120 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 120 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-230700-016 | Duct Glue | 120 | Committed | 2025-11-26 | SEC-230000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 120 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 120 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505014-001 | Hard Hat (Helmet) | 120 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | M-014300-014 | Saftey Tools | 120 | Committed | 2026-01-27 | SEC-014000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 120 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 120 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 120 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 118.75 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 118.32 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 118.32 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 117 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 116.67 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 116.48 | Committed | 2025-12-02 | SEC-283000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 116.48 | Committed | 2026-01-05 | Mat019300-004SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | (Blank) |  |  | 116.43 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 116.13 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 116.13 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 116.12 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 116.12 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 116 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 115.74 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 115.2 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 115.2 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 115 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-014 | Sanitary Drains-Ci Cleanout | 113.4 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-014 | Sanitary Drains-Ci Cleanout | 113.4 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 112.8 | Committed | 2025-11-25 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 112.8 | Committed | 2025-12-02 | SEC-283000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 112.5 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 112.48 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 112.32 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 112 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 112 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000095 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000095 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 111.44 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 111.36 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 111.12 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000117 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 110 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000117 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 170-001 | Construction Waste Bags | 110 | Committed | 2025-11-13 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 110 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 109.25 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 108.87 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 108.33 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 108.33 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-004 | Raceway And Boxes - Pvc Female Adaptor | 108.03 | Committed | 2025-11-26 | SEC-112000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-009 | Domestic Water Piping Specialties-Gate Valve | 107.72 | Committed | 2025-11-22 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 107.25 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 106.66 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 106.66 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 106.66 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 106.66 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000149 | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 106.25 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 105.87 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 105.87 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 105 | Committed | 2025-04-17 | SEC-255000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 105 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 104.84 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221100-022 | Domestic Water Piping Specialties-Hose Bib | 104.82 | Committed | 2025-11-22 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 104.34 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 104.34 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 104.34 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 104.34 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 104.34 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 104 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 104 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 104 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 103.23 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 102.7 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 102.6 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 102.6 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 102.59 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 102.3 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 102.2 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 102 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 102 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 102 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 102 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-092 | Pvc Male Adapter | 101.25 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 100 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) |  |  | 100 | Expense actual | 2025-05-31 | Mat014100-025 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 100 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 100 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 100 | Expense actual | 2025-09-30 | Mat014100-021 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 100 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 100 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 100 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | MT-504062-001 | Safety Gloves | 100 | Committed | 2025-10-26 | SEC-335000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 100 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 100 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-504017-001 | Handsaw | 100 | Committed | 2025-11-25 | SEC-321000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 100 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 100 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 100 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-224100-020 | Water Flexible Hose | 100 | Committed | 2025-11-25 | SEC-224000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 100 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-011 | Safety Training | 100 | Committed | 2026-01-25 | Mat014300-011SEV | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Materials / Misc
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 100 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | (Blank) |  |  | 99.8 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 99.74 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 99.74 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 99.39 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 99.2 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 98.8 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 97.6 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 97.6 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 96.77 | Expense actual | 2025-01-31 | Mat014100-022 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 96.77 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 96.77 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 96 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 95.68 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | SC-023200-003 | Material Testing | 95 | Item actual | 2025-06-30 | SEC-410000SC | Item transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 94.5 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 94.5 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 94.25 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 93.33 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 93.32 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 93.02 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 93.02 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 93.02 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 93.02 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 92 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 92 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 92 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 92 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 91.67 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 91.2 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-097 | Pvc - Female Tee | 91.2 | Committed | 2025-11-25 | SEC-285000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 91 | Item actual | 2025-12-31 | Mat014300-014SEV | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 91 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 90.45 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 90.35 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 90.32 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 90 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | ME-503010-017 | Raceway And Boxes - Emt Conduit | 90 | Committed | 2025-11-22 | SEC-115000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 90 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 90 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 90 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 90 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 90 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-284600-004 | Fire Alarm System - Heat Detector | 90 | Committed | 2026-01-28 | SEC-284000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000091 | MM-502010-079 | Cpvc Male Adapter | 90 | Committed | 2026-01-28 | SEC-502000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 90 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 90 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 90 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 90 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 90 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 88.74 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 88.71 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 88.71 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 88.26 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 88 | Committed | 2025-04-17 | SEC-255000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-059 | Raceway And Boxes - Wearther Proof Boxes | 88 | Committed | 2025-11-26 | SEC-122000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 86.98 | Expense actual | 2025-10-31 | Mat014100-024 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 86.62 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 86.4 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 86.4 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 85.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 85 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 85 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505010-001 | Safety Vest | 85 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 85 | Committed | 2025-11-22 | SEC-117000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 85 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 85 | Committed | 2026-01-28 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000093 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 84.48 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 84 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 83.87 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | 83.87 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 83.16 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 83 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 83 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 83 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 81.65 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 80.65 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 80.5 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 80 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 80 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | MT-504066-001 | Dust Mask | 80 | Committed | 2025-10-26 | SEC-336000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 80 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 80 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 80 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 80 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 80 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 80 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 80 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 80 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 80 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | MIDA-000135 | Mat014300-011 | Safety Training | 80 | Committed | 2025-09-22 | Mat014300-011SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000135 | Materials / Misc
KSA Project | MIDA-000110 | ME-503010-012 | Raceway And Boxes - Pvc Bend Heavy Gauge | 79.5 | Item actual | 2025-12-31 | SEC-114000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 79.2 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 77.34 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 77.28 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 76.2 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 76.2 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 76 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 76 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 76 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 76 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 75.6 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 75 | Expense actual | 2025-11-30 | Mat014100-023 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 75 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-262800-014 | Enclosed Switches | 75 | Committed | 2025-11-25 | SEC-262000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 75 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-008 | Sanitary Drains-Ci Floor Drain | 75 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 75 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 75 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 75 | Committed | 2025-11-27 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 74.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 74.25 | Committed | 2025-11-25 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 74.25 | Committed | 2025-11-26 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 73 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | MIDA-000011 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 72 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 72 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 72 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | (Blank) |  |  | 71.43 | Expense actual | 2025-02-28 | Mat014100-021 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 71.26 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 71.26 | Committed | 2025-09-17 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 71.25 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 71.25 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 70.31 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 70 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 70 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-054500-001 | Metal Support Assemblies | 70 | Committed | 2025-11-25 | SEC-054000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-092 | Pvc Male Adapter | 70 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 70 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 69.12 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 69 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 69 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 68.2 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 68 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 68 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 68 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-014300-014 | Saftey Tools | 68 | Committed | 2025-11-26 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 67.74 | Expense actual | 2025-10-31 | Mat014100-023 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 67.5 | Committed | 2025-11-25 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 67.5 | Committed | 2025-11-26 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 67.2 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 67.2 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-002 | Supporting System - Hexa Nut | 66.58 | Committed | 2025-11-26 | SEC-105000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 66.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 66.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 66.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 66.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 66.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 66.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-015100-004 | Temporary Fuel Oil | 66 | Committed | 2025-11-13 | SEC-015000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-003 | Supporting System - Flat Washer | 65.88 | Committed | 2025-11-26 | SEC-105000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 65.02 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | MIDA-000087 | SC-078400-001 | Firestopping | 65.02 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000087 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 65 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 65 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 65 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 65 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 64.8 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 64.52 | Expense actual | 2025-05-31 | Mat014100-023 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 64.52 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 63.42 | Committed | 2025-12-02 | SEC-283000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 63.36 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-045 | Cable Trays - Straight Cable Ladder | 63.22 | Committed | 2025-11-26 | SEC-132000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 63 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 63 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 62.64 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 62.23 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 62 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 62 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 61.9 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 61.6 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000113 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 61.2 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000113 | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 60.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | SC-078400-001 | Firestopping | 60.61 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-097 | Pvc - Female Tee | 60.32 | Committed | 2025-11-25 | SEC-285000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-097 | Pvc - Female Tee | 60.32 | Committed | 2025-11-26 | SEC-285000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 60 | Expense actual | 2025-10-31 | Mat014100-025 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 60 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 60 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 60 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 60 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-002 | Facility Sanitary Sewerage-Hdpe Pipe | 60 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-224100-018 | Hand Spray | 60 | Committed | 2025-11-25 | SEC-224000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 60 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 60 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-323100-001 | Fences And Gates | 60 | Committed | 2025-11-25 | SEC-022000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-224100-020 | Water Flexible Hose | 60 | Committed | 2025-11-25 | SEC-224000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 60 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 60 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 60 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 60 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 60 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | MT-505014-001 | Hard Hat (Helmet) | 60 | Committed | 2026-01-27 | SEC-505000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000140 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 60 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 60 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 59.8 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-099100-001 | Painting | 59 | Committed | 2025-11-22 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-099100-001 | Painting | 59 | Committed | 2025-11-25 | SEC-099000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-233700-010 | Exhaust Air Louver | 58.5 | Committed | 2025-04-19 | SEC-233000 | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 58.4 | Committed | 2025-11-26 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 58.14 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 58.06 | Expense actual | 2025-01-31 | Mat014100-023 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 57.6 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 57.22 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 57.14 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 57 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 57 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 57 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 57 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 56.28 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 56.24 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 56.2 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 56.2 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 56 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 55.43 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | MIDA-000103 | SC-078400-001 | Firestopping | 55.43 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000103 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 55.04 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 55 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 55 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 55 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 55 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 54.76 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 54.44 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 54 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 |  |  | 53.33 | Expense actual | 2025-12-31 | Mat014100-025 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | 53.03 | Expense actual | 2025-08-31 | Mat014100-007 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 52.8 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 52.8 | Committed | 2025-11-26 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 52.5 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 52.5 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 52.25 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) |  |  | 51.88 | Expense actual | 2025-09-30 | Mat014100-024 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | 51.61 | Expense actual | 2025-12-31 | Mat014100-023 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 51.3 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 51.3 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 50 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 50 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 50 | Expense actual | 2025-09-30 | Mat014100-022 | Expense transactions | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 50 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 50 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 50 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-505018-001 | Knee Pads | 50 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 50 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 50 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 50 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 50 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 50 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 50 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | Mat019300-004 | Maintenance Fees | 50 | Committed | 2025-09-09 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦(Blank) | Materials / Misc
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 50 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | MIDA-000130 | Mat019300-004 | Maintenance Fees | 50 | Committed | 2025-09-25 | Mat019300-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000130 | Materials / Misc
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 49.51 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 48 | Item actual | 2025-12-31 | SEC-115000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | M-230700-013 | Duct Tape | 48 | Committed | 2025-11-13 | SEC-230000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 48 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000015 | SC-081400-001 | Wood Doors | 48 | Committed | 2026-01-22 | SEC-081000SC | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000015 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 47.52 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 47.5 | Committed | 2025-12-02 | SEC-282000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 47.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 47.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 47.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 47.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 47.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 47.47 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 46.84 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 46.64 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 46.35 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 46.33 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 45.6 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 45.4 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 45.36 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 45.3 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 45.24 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 45.24 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 45.12 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000114 | Subcontractor / Manpower
KSA Project | (Blank) | M-013600-033 | Network Cables | 45 | Committed | 2025-04-17 | SEC-013000 | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | MT-504032-001 | Clamps | 45 | Committed | 2025-10-26 | SEC-328000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 45 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 45 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | Mat014000-004 | Hand Tools | 45 | Committed | 2025-09-17 | Mat014000-004SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000046 | Equipment / Plant
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 44.8 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 44.8 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 44 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 44 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 44 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 43.2 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 42.9 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 42.86 | Expense actual | 2025-02-28 | Mat014100-023 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 42.8 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 42.75 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 42.75 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 41.67 | Expense actual | 2025-04-30 | Mat014100-023 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 41.21 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 41.2 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 41.04 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 40.83 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | 40.32 | Expense actual | 2025-10-31 | Mat014100-021 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000131 | Mat015400-005 | Temporary Scaffolding And Platforms | 40.15 | Committed | 2025-12-25 | Mat015400-005SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000131 | Materials / Misc
KSA Project | (Blank) | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 40 | Committed | 2025-11-22 | SEC-117000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-002 | Facility Sanitary Sewerage-Hdpe Pipe | 40 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 40 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 40 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-224100-020 | Water Flexible Hose | 40 | Committed | 2025-11-25 | SEC-224000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 40 | Committed | 2025-11-26 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 40 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 40 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 40 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | MM-502010-095 | Pvc Reducing Tee | 39.6 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 39.32 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 38.4 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 38.4 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 38.4 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-014 | U-Bolts | 38.4 | Committed | 2025-11-26 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 38.11 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 38 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503060-001 | Cable Connectors | 37.5 | Committed | 2025-04-17 | SEC-230000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 37.44 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 37.4 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 37.32 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 37.28 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 37 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 36.83 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 36.81 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 36.24 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 36 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 10 172-001 | Civil Accessories | 36 | Committed | 2025-11-25 | SEC-087000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 36 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 36 | Committed | 2025-11-25 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 36 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000149 | M-262200-001 | Low-Voltage Transformers | 36 | Committed | 2026-01-28 | SEC-262000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-012 | Safety 3rd Party Testing | 36 | Committed | 2025-12-15 | Mat014300-012SEV | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000140 | Services
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 35.88 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 35.4 | Item actual | 2025-12-31 | SEC-111000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 35 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 35 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 35 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 35 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505011-001 | Safety Shoes | 34.78 | Committed | 2025-11-13 | SEC-340000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-093 | Pvc 45 Elbow | 34 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000149 | ME-503030-007 | Underground Ducts And Raceways - Upvc Bell End Coupling | 34 | Committed | 2026-01-28 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000149 | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-017 | Supporting System - C Clamp | 33.6 | Committed | 2025-11-25 | SEC-110000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 33.27 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 32.2 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 32.2 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 32 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-092 | Pvc Male Adapter | 31.6 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 31.5 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 31.5 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 31.5 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 30.8 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 30.8 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 30.54 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 30.4 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 30.2 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 30.2 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-265500-001 | Special Purpose Lighting | 30 | Committed | 2025-11-25 | SEC-265000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-003 | Supporting System - Flat Washer | 30 | Committed | 2025-11-25 | SEC-105000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 30 | Committed | 2025-11-25 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 30 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 30 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-002 | Supporting System - Hexa Nut | 30 | Committed | 2025-11-26 | SEC-105000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 30 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 30 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 30 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 30 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 30 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 30 | Committed | 2025-11-26 | SEC-221000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 29.6 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 29.6 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 29.5 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 29.26 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-082 | Cpvc Reducing Tee | 29.12 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 28.8 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 28.8 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 28.6 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 28.6 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 28.5 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 28.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 28.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 28.5 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 27.76 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 27.36 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 27.36 | Committed | 2025-11-26 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 27.16 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 27.16 | Committed | 2025-09-17 | Mat017100-015SEV | Committed costs | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000011 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 27 | Committed | 2026-01-27 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | MIDA-000091 | MM-502010-079 | Cpvc Male Adapter | 26.25 | Committed | 2026-01-28 | SEC-502000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 26 | Committed | 2025-10-23 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 26 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 26 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 25.2 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505048-001 | Breathing Mask (Full Face) | 25 | Committed | 2025-11-13 | SEC-350000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 25 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 25 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 25 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-224100-020 | Water Flexible Hose | 25 | Committed | 2025-11-25 | SEC-224000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 25 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-096 | Pvc Reducing Adapter | 24.8 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-096 | Pvc Reducing Adapter | 24.8 | Committed | 2025-11-26 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 24.5 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 24.46 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 24.2 | Committed | 2025-12-02 | SEC-282000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 24.19 | Expense actual | 2025-10-31 | Mat014100-022 | Expense transactions | 2025 | 10 | 2025-10 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MT-505048-001 | Breathing Mask (Full Face) | 24 | Committed | 2025-11-13 | SEC-350000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-230700-013 | Duct Tape | 24 | Committed | 2025-11-13 | SEC-230000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 24 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 24 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 24 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 24 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 24 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 23.8 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 23.8 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 23.75 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 23.75 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 23.75 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 23.68 | Committed | 2025-12-02 | SEC-282000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 23.3 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 22.8 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 22.5 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075200-001 | Modified Bituminous Membrane Roofing | 22.5 | Committed | 2025-08-12 | SEC-075000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 22.5 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 22.5 | Committed | 2025-08-12 | SEC-071000SC | Committed costs | 2025 | 8 | 2025-08 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-075200-001 | Modified Bituminous Membrane Roofing | 22.5 | Committed | 2025-12-04 | SEC-075000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071300-001 | Sheet Waterproofing | 22.5 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 22.5 | Committed | 2025-12-04 | SEC-071000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000041 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-075200-001 | Modified Bituminous Membrane Roofing | 22.5 | Committed | 2025-07-20 | SEC-075000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-071300-001 | Sheet Waterproofing | 22.5 | Committed | 2025-07-20 | SEC-071000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 22 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-018600-003 | Plumbing Performance Requirements | 22 | Committed | 2025-11-26 | SEC-018000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 21.6 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 21.6 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 21.06 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 21.04 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 21.04 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 20.48 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 20.34 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 20 | Committed | 2025-04-17 | SEC-255000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-002 | Supporting System - Hexa Nut | 20 | Committed | 2025-11-25 | SEC-105000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 20 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 20 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 20 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 20 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MC-50 20 00-003 | Supporting System - Flat Washer | 20 | Committed | 2025-11-26 | SEC-105000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 20 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 20 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) |  |  | 19.96 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 19.84 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 19.2 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 19.12 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 19.12 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 19 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 19 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | Mat014500-007 | Testing Laboratory Services | 19 | Committed | 2025-11-05 | Mat014500-007SEV | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Services
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 18.24 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 18.04 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 18 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 18 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 17.7 | Item actual | 2025-12-31 | SEC-111000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 17.5 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 17.2 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 17 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 17 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 16.36 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 16.36 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 16.2 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 16 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 16 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 16 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 16 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 15.44 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 15.44 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 15.44 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 15.22 | Committed | 2025-11-25 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 15.2 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 15 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-082 | Cpvc Reducing Tee | 15 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 14.4 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 14.4 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 14.4 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 14.3 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 14 | Committed | 2025-04-17 | SEC-255000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 14 | Committed | 2025-04-17 | SEC-255000SC | Committed costs | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 14 | Committed | 2025-11-25 | SEC-271000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-093 | Pvc 45 Elbow | 14 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 13.63 | Committed | 2025-11-26 | SEC-111000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 13.56 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 13.5 | Committed | 2025-11-25 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 13.5 | Committed | 2025-11-26 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-016 | Pipe Clamps | 13.44 | Committed | 2025-11-22 | SEC-260000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 13.2 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 13.2 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 13.2 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 12.92 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 12.08 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 12.08 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 12 | Committed | 2025-10-27 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 11.76 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 11.28 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 11 | Committed | 2025-11-25 | SEC-055000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 10.8 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 10.75 | Committed | 2025-10-26 | SEC-014000 | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 10.5 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 10.5 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 10.38 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 10.38 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 10.32 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 10.08 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 10 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-082 | Cpvc Reducing Tee | 10 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000140 | Mat014300-014 | Saftey Tools | 10 | Committed | 2025-10-12 | Mat014300-014SEV | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000140 | Equipment / Plant
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 9.99 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 9.86 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 9.6 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-094 | Pvc 90 Elbow | 9.6 | Committed | 2025-11-26 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-081 | Cpvc 90 Elbow | 9.52 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 9.52 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 9.48 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 9.24 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 9.12 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-080 | Cpvc 45 Elbow | 9.1 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) |  |  | 9.07 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 9 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 8.1 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 8 | Committed | 2025-11-25 | SEC-123000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 8 | Committed | 2026-01-26 | SEC-503000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000011 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 7.68 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 7.25 | Committed | 2025-11-25 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-013 | Anchor Bolt | 7.25 | Committed | 2025-11-26 | SEC-259000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 7.2 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 7.2 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000030 | Mat018500-010 | Equipment Rental | 7 | Item actual | 2025-07-31 | Mat018500-010SEV | Item transactions | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000030 | Services
KSA Project | (Blank) | ME-503750-001 | Electrical Accessories | 7 | Committed | 2025-11-26 | SEC-255000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 6.88 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 6.84 | Committed | 2025-12-02 | SEC-282000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 6.72 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 6.72 | Committed | 2025-11-26 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 6.48 | Committed | 2025-12-02 | SEC-282000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | ME-503010-007 | Raceway And Boxes - Pvc Pound Spring Clips | 6 | Committed | 2025-11-25 | SEC-112000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 6 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-079 | Cpvc Male Adapter | 6 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-505056-001 | Hand Tools | 6 | Committed | 2025-11-26 | SEC-400000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 6 | Committed | 2025-11-26 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 5.72 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 5.16 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 5.16 | Committed | 2025-11-26 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 5 | Committed | 2025-11-25 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-086 | Cpvc - Equal Tee | 5 | Committed | 2025-11-25 | SEC-283000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 4.92 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 4.86 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 4.86 | Committed | 2025-11-25 | SEC-221000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 4.86 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 4.7 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 4.62 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-078 | Cpvc Union | 4.48 | Committed | 2025-11-25 | SEC-281000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 4 | Committed | 2026-01-08 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 4 | Committed | 2026-01-10 | SEC-221000 | Committed costs | 2026 | 1 | 2026-01 | KSA Project¦MIDA-000091 | Subcontractor / Manpower
KSA Project | MIDA-000147 | Mat017100-015 | Staff Accommodation | 3.39 | Item actual | 2025-10-31 | Mat017100-015SEV | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000147 | Materials / Misc
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 3.38 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 2.46 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-091 | Pvc Union | 2.4 | Committed | 2025-11-25 | SEC-284000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MM-502010-083 | Cpvc Reducing Adapter | 2 | Committed | 2025-11-25 | SEC-282000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000110 | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 0.47 | Item actual | 2025-12-31 | SEC-111000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000110 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 0 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | SC-053300-001 | Aluminum Decking | 0 | Item actual | 2025-12-31 | SEC-053000SC | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 0 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | MIDA-000001 | M-014300-014 | Saftey Tools | 0 | Committed | 2025-11-13 | SEC-014000 | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000001 | Subcontractor / Manpower
KSA Project | (Blank) | MT-504062-001 | Safety Gloves | 0 | Committed | 2025-11-13 | SEC-335000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | (Blank) | MT-504062-001 | Safety Gloves | 0 | Committed | 2025-11-13 | SEC-335000SC | Committed costs | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000046 | M-032100-001 | Reinforcement Bars | 0 | Committed | 2025-12-08 | SEC-030000 | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000046 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 0 | Committed | 2025-06-02 | SEC-081000SC | Committed costs | 2025 | 6 | 2025-06 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 0 | Committed | 2025-12-17 | SEC-081000SC | Committed costs | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | MIDA-000013 | SC-081400-001 | Wood Doors | 0 | Committed | 2025-07-19 | SEC-081000SC | Committed costs | 2025 | 7 | 2025-07 | KSA Project¦MIDA-000013 | Subcontractor / Manpower
KSA Project | (Blank) | Mat018500-010 | Equipment Rental | 0 | Committed | 2025-05-21 | Mat018500-010SEV | Committed costs | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000053 | SC-078400-001 | Firestopping | 0 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000053 | Subcontractor / Manpower
KSA Project | MIDA-000053 | SC-078400-001 | Firestopping | 0 | Committed | 2025-10-16 | SEC-078000SC | Committed costs | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000053 | Subcontractor / Manpower
KSA Project | (Blank) |  |  | -35 | Expense actual | 2025-01-31 | Mat014100-024 | Expense transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | -35 | Expense actual | 2025-03-31 | Mat014100-024 | Expense transactions | 2025 | 3 | 2025-03 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | -35 | Expense actual | 2025-04-30 | Mat014100-024 | Expense transactions | 2025 | 4 | 2025-04 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | -35 | Expense actual | 2025-05-31 | Mat014100-024 | Expense transactions | 2025 | 5 | 2025-05 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | -35 | Expense actual | 2025-06-30 | Mat014100-024 | Expense transactions | 2025 | 6 | 2025-06 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | -35 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | -35 | Expense actual | 2025-08-31 | Mat014100-024 | Expense transactions | 2025 | 8 | 2025-08 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | -35 | Expense actual | 2025-02-28 | Mat014100-024 | Expense transactions | 2025 | 2 | 2025-02 | KSA Project¦(Blank) | Other
KSA Project | MIDA-000133 |  |  | -35 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | -35 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | -35 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | -35 | Expense actual | 2025-11-30 | Mat014100-024 | Expense transactions | 2025 | 11 | 2025-11 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | -35 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | MIDA-000133 |  |  | -35 | Expense actual | 2025-12-31 | Mat014100-024 | Expense transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Other
KSA Project | (Blank) |  |  | -70 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) |  |  | -70 | Expense actual | 2025-07-31 | Mat014100-024 | Expense transactions | 2025 | 7 | 2025-07 | KSA Project¦(Blank) | Other
KSA Project | (Blank) | Mat014100-018 | Project Security | -4000.24 | Item actual | 2025-01-31 | Mat014100-018SEV | Item transactions | 2025 | 1 | 2025-01 | KSA Project¦(Blank) | Services
KSA Project | MIDA-000023 | M-014100-017 | Manpower Rental | -53563 | Item actual | 2025-10-09 | SEC-014000 | Item transactions | 2025 | 10 | 2025-10 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | MIDA-000023 | M-014100-017 | Manpower Rental | -224825 | Item actual | 2025-09-30 | SEC-014000 | Item transactions | 2025 | 9 | 2025-09 | KSA Project¦MIDA-000023 | Subcontractor / Manpower
KSA Project | (Blank) | M-014100-017 | Manpower Rental | -360947 | Item actual | 2025-11-20 | SEC-014000 | Item transactions | 2025 | 11 | 2025-11 | KSA Project¦(Blank) | Subcontractor / Manpower
KSA Project | MIDA-000133 | M-014100-017 | Manpower Rental | -369957 | Item actual | 2025-12-08 | SEC-014000 | Item transactions | 2025 | 12 | 2025-12 | KSA Project¦MIDA-000133 | Subcontractor / Manpower

## Agg_ByItem
Project | Cost Code | Item code | Item name | Actual | Committed | Total | Transactions Count
KSA Project | KSA-000084 | SC-212100-001 | Gas-Based Fire-Extinguishing Systems | 0 | 15303365.08 | 15303365.08 | 66
KSA Project | KSA-000084 | Subtotal |  | 0 | 15303365.08 | 15303365.08 | 66
KSA Project | Cost-000001 | Subtotal |  | 1990974.22 | 9916028.26 | 11907002.48 | 312
KSA Project | KSA-000084 | Subtotal |  | 4385321.82 | 4923085.98 | 9308407.8 | 1607
KSA Project | Cost-000133 | Subtotal |  | 2752370.83 | 975713.49 | 3728084.32 | 45
KSA Project | Cost-000001 | SC-053300-001 | Aluminum Decking | 1444557.35 | 2210516.59 | 3655073.94 | 44
KSA Project | Cost-000133 | SEV-014100-017 | Manpower Rental | 2663050.6 | 853605 | 3516655.6 | 21
KSA Project | KSA-000084 | SEV-014100-017 | Manpower Rental | 2802725.39 | 694534.75 | 3497260.14 | 66
KSA Project | Cost-000046 | Subtotal |  | 1364768.5 | 1057936 | 2422704.5 | 65
KSA Project | Cost-000046 | SEV-014100-017 | Manpower Rental | 1359768.5 | 1005046 | 2364814.5 | 39
KSA Project | Cost-000001 | SC-233100-001 | Hvac Ducts And Casings | 361350 | 1727600 | 2088950 | 6
KSA Project | Cost-000071 | SC-053300-001 | Aluminum Decking | 0 | 1825238.94 | 1825238.94 | 15
KSA Project | Cost-000071 | Subtotal |  | 0 | 1825238.94 | 1825238.94 | 15
KSA Project | Cost-000131 | Subtotal |  | 787388.29 | 343063.27 | 1130451.56 | 142
KSA Project | Cost-000131 | SEV-018500-010 | Equipment Rental | 787388.29 | 306411.18 | 1093799.47 | 120
KSA Project | Cost-000001 | SC-034100-001 | Precast Structural Concrete | 0 | 1008630 | 1008630 | 8
KSA Project | Cost-000117 | Subtotal |  | 1910 | 990306.78 | 992216.78 | 8
KSA Project | Cost-000117 | SC-284600-001 | Fire Alarm System | 0 | 990306.78 | 990306.78 | 6
KSA Project | KSA-000084 | SEV-018500-010 | Equipment Rental | 674137.12 | 199334.18 | 873471.3 | 138
KSA Project | KSA-000084 | M-032100-001 | Reinforcement Bars | 0 | 809560 | 809560 | 29
KSA Project | Cost-000001 | M-310500-003 | Aggregates For Earthwork | 0 | 767080 | 767080 | 3
KSA Project | Cost-000028 | SC-125100-001 | Office Furniture | 0 | 696379.2 | 696379.2 | 50
KSA Project | Cost-000028 | Subtotal |  | 0 | 696379.2 | 696379.2 | 50
KSA Project | KSA-000084 | M-039100-001 | Ready-Mix Concrete | 0 | 625424.02 | 625424.02 | 10
KSA Project | Cost-000001 | SC-096200-001 | Specialty Flooring | 0 | 578040 | 578040 | 22
KSA Project | Cost-000001 | SC-064100-001 | Architectural Wood Casework | 0 | 536322.5 | 536322.5 | 4
KSA Project | Cost-000069 | SC-064100-001 | Architectural Wood Casework | 0 | 536322.5 | 536322.5 | 4
KSA Project | Cost-000069 | Subtotal |  | 0 | 536322.5 | 536322.5 | 4
KSA Project | Cost-000147 | Subtotal |  | 53843.87 | 477542.13 | 531386 | 44
KSA Project | Cost-000022 | SC-064100-001 | Architectural Wood Casework | 0 | 526822.5 | 526822.5 | 3
KSA Project | Cost-000022 | Subtotal |  | 0 | 526822.5 | 526822.5 | 3
KSA Project | Cost-000001 | SC-096800-001 | Carpeting | 0 | 445346.01 | 445346.01 | 6
KSA Project | Cost-000015 | SC-081400-001 | Wood Doors | 0 | 400485.9 | 400485.9 | 77
KSA Project | Cost-000015 | Subtotal |  | 0 | 400485.9 | 400485.9 | 77
KSA Project | Cost-000013 | Subtotal |  | 0 | 399016.5 | 399016.5 | 105
KSA Project | Cost-000036 | SC-321100-001 | Base Courses | 0 | 378005 | 378005 | 2
KSA Project | Cost-000036 | Subtotal |  | 0 | 378005 | 378005 | 2
KSA Project | KSA-000084 | MC-50 10 117-001 | Marble Flooring Tiles | 0 | 366274.8 | 366274.8 | 6
KSA Project | Cost-000013 | SC-081400-001 | Wood Doors | 0 | 346981.5 | 346981.5 | 96
KSA Project | Cost-000147 | SEV-017100-015 | Staff Accommodation | 53843.87 | 262692.13 | 316536 | 38
KSA Project | Cost-000001 | M-039100-001 | Ready-Mix Concrete | 0 | 314022.31 | 314022.31 | 3
KSA Project | KSA-000084 | M-018500-004 | Diesel | 75232.16 | 235628.72 | 310860.88 | 33
KSA Project | Cost-000041 | Subtotal |  | 0 | 293936.05 | 293936.05 | 50
KSA Project | Cost-000001 | SC-237300-001 | Air-Handling Units | 0 | 288800 | 288800 | 4
KSA Project | Cost-000009 | Subtotal |  | 0 | 275872.4 | 275872.4 | 22
KSA Project | Cost-000040 | Subtotal |  | 0 | 272040 | 272040 | 6
KSA Project | Cost-000126 | SC-142800-001 | Elevator Equipment And Controls | 224600 | 39400 | 264000 | 4
KSA Project | Cost-000126 | Subtotal |  | 224600 | 39400 | 264000 | 4
KSA Project | Cost-000001 | SC-054100-001 | Structural Metal Stud Framing | 0 | 261670.5 | 261670.5 | 3
KSA Project | Cost-000024 | Subtotal |  | 0 | 253590 | 253590 | 3
KSA Project | Cost-000009 | SC-052100-001 | Steel Joist Framing | 0 | 250000 | 250000 | 14
KSA Project | Cost-000129 | Subtotal |  | 126851.05 | 96626.24 | 223477.29 | 17
KSA Project | Cost-000045 | Subtotal |  | 0 | 223057.68 | 223057.68 | 10
KSA Project | Cost-000045 | M-039100-001 | Ready-Mix Concrete | 0 | 219897.68 | 219897.68 | 9
KSA Project | KSA-000084 | MC-50 10 172-001 | Civil Accessories | 0 | 217886.37 | 217886.37 | 33
KSA Project | Cost-000001 | SC-237500-001 | Custom-Packaged Outdoor Hvac Equipment | 0 | 211200 | 211200 | 4
KSA Project | KSA-000084 | M-260519-031 | Low-Voltage Cables - Wires - Cu/Xlpe/Pvc | 0 | 203310 | 203310 | 20
KSA Project | Cost-000040 | SC-054100-001 | Structural Metal Stud Framing | 0 | 195000 | 195000 | 3
KSA Project | Cost-000149 | Subtotal |  | 118225.95 | 72487.65 | 190713.6 | 55
KSA Project | Cost-000129 | SEV-018500-004 | Diesel | 123046.7 | 65831.01 | 188877.71 | 5
KSA Project | KSA-000084 | SEV-017800-020 | Permits and Licenses | 188052 | 0 | 188052 | 5
KSA Project | Cost-000001 | SC-075100-001 | Built-Up Bituminous Roofing | 0 | 184579.2 | 184579.2 | 14
KSA Project | Cost-000041 | SC-071200-001 | Built-Up Bituminous Waterproofing | 0 | 177183.55 | 177183.55 | 36
KSA Project | Cost-000001 | SC-030500-001 | Common Work Results For Concrete | 0 | 171080 | 171080 | 6
KSA Project | Cost-000024 | SC-098100-001 | Acoustic Insulation | 0 | 167990 | 167990 | 2
KSA Project | Cost-000043 | SC-101400-001 | Signage | 0 | 165955.5 | 165955.5 | 21
KSA Project | Cost-000043 | Subtotal |  | 0 | 165955.5 | 165955.5 | 21
KSA Project | Cost-000031 | SC-314100-001 | Shoring | 0 | 163234.99 | 163234.99 | 9
KSA Project | Cost-000031 | Subtotal |  | 0 | 163234.99 | 163234.99 | 9
KSA Project | Cost-000110 | Subtotal |  | 129538.37 | 24213.63 | 153752 | 24
KSA Project | Cost-000110 | SEV-017400-004 | Construction Waste Management And Disposal | 128265 | 24200 | 152465 | 14
KSA Project | Cost-000030 | SEV-018500-010 | Equipment Rental | 119589.9 | 30830.1 | 150420 | 47
KSA Project | Cost-000030 | Subtotal |  | 119589.9 | 30830.1 | 150420 | 47
KSA Project | Cost-000001 | SC-036300-001 | Epoxy Grouting | 0 | 142662 | 142662 | 6
KSA Project | Cost-000001 | SEV-014100-017 | Manpower Rental | 104776.5 | 33700 | 138476.5 | 5
KSA Project | Cost-000001 | SC-142800-001 | Elevator Equipment And Controls | 0 | 136000 | 136000 | 1
KSA Project | Cost-000107 | SC-092400-001 | Cement Plastering | 120341.1 | 13123.9 | 133465 | 8
KSA Project | Cost-000107 | Subtotal |  | 120341.1 | 13123.9 | 133465 | 8
KSA Project | KSA-000084 | SC-096200-001 | Specialty Flooring | 0 | 131040 | 131040 | 1
KSA Project | KSA-000084 | SEV-014100-009 | Employee Food | 126628.82 | 0 | 126628.82 | 22
KSA Project | Cost-000054 | Subtotal |  | 49700 | 75328 | 125028 | 17
KSA Project | Cost-000001 | SC-052100-001 | Steel Joist Framing | 0 | 125000 | 125000 | 7
KSA Project | Cost-000140 | Subtotal |  | 62549.9 | 57867.73 | 120417.63 | 126
KSA Project | KSA-000084 | SEV-014100-018 | Project Security | 87304.3 | 32571.43 | 119875.73 | 14
KSA Project | KSA-000084 | SEV-017100-016 | Labour Accommodation | 0 | 117721.74 | 117721.74 | 8
KSA Project | Cost-000133 | SEV-014100-018 | Project Security | 12480 | 100800 | 113280 | 3
KSA Project | Cost-000138 | Subtotal |  | 102949 | 5056 | 108005 | 8
KSA Project | Cost-000147 | SEV-014100-008 | Employee Accommodation | 0 | 107750 | 107750 | 3
KSA Project | Cost-000001 | SEV-014100-018 | Project Security | 69760.37 | 37419.44 | 107179.81 | 11
KSA Project | Cost-000147 | SEV-017100-016 | Labour Accommodation | 0 | 107100 | 107100 | 3
KSA Project | Cost-000138 | SEV-014500-007 | Testing Laboratory Services | 102949 | 2656 | 105605 | 7
KSA Project | Cost-000047 | SEV-014100-017 | Manpower Rental | 103344.75 | 0 | 103344.75 | 2
KSA Project | Cost-000047 | Subtotal |  | 103344.75 | 0 | 103344.75 | 2
KSA Project | Cost-000011 | Subtotal |  | 14787.72 | 84177.35 | 98965.07 | 105
KSA Project | Cost-000133 | SEV-014100-009 | Employee Food | 76840.23 | 21308.49 | 98148.72 | 19
KSA Project | Cost-000041 | SC-075100-001 | Built-Up Bituminous Roofing | 0 | 92289.6 | 92289.6 | 7
KSA Project | Cost-000001 | SC-077700-001 | Wall Specialties | 0 | 90000 | 90000 | 1
KSA Project | KSA-000084 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 0 | 87753.5 | 87753.5 | 27
KSA Project | Cost-000054 | SC-092300-001 | Gypsum Plastering | 45150 | 42350 | 87500 | 5
KSA Project | Cost-000024 | M-230700-012 | Acoustic Insulation | 0 | 85600 | 85600 | 1
KSA Project | Cost-000001 | SC-071200-001 | Built-Up Bituminous Waterproofing | 0 | 84497.4 | 84497.4 | 12
KSA Project | Cost-000149 | M-013500-028 | Office Furniture | 69265.92 | 15097.5 | 84363.42 | 19
KSA Project | KSA-000084 | SEV-014000-003 | Electrical Tools | 62503.65 | 21559.4 | 84063.05 | 12
KSA Project | KSA-000084 | M-036100-001 | Cementitious Grouting | 0 | 81043.6 | 81043.6 | 6
KSA Project | KSA-000084 | SEV-017100-003 | Site Mobilization | 43855.8 | 36216.16 | 80071.96 | 38
KSA Project | Cost-000001 | SC-132200-001 | Office Shelters And Booths | 0 | 80000 | 80000 | 1
KSA Project | Cost-000011 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 0 | 77626.35 | 77626.35 | 86
KSA Project | Cost-000017 | Subtotal |  | 14555 | 62668.43 | 77223.43 | 12
KSA Project | Cost-000040 | M-032100-001 | Reinforcement Bars | 0 | 77040 | 77040 | 3
KSA Project | Cost-000029 | Subtotal |  | 0 | 74254.5 | 74254.5 | 21
KSA Project | KSA-000084 | MC-50 10 103-001 | Porous Concrete Blocks | 0 | 71759.5 | 71759.5 | 10
KSA Project | Cost-000001 | SC-102100-001 | Compartments And Cubicles | 0 | 69360 | 69360 | 3
KSA Project | Cost-000001 | SC-092400-001 | Cement Plastering | 9000 | 60000 | 69000 | 2
KSA Project | KSA-000084 | SEV-018500-004 | Diesel | 63338.26 | 0 | 63338.26 | 2
KSA Project | Cost-000053 | Subtotal |  | 0 | 61190.86 | 61190.86 | 8
KSA Project | KSA-000084 | M-092100-001 | Plaster And Gypsum Board Assemblies | 0 | 59537.5 | 59537.5 | 7
KSA Project | Cost-000132 | Subtotal |  | 0 | 59044 | 59044 | 3
KSA Project | Cost-000001 | MC-50 10 103-001 | Porous Concrete Blocks | 0 | 56490 | 56490 | 5
KSA Project | Cost-000091 | Subtotal |  | 0 | 55094.79 | 55094.79 | 55
KSA Project | KSA-000084 | SEV-017400-004 | Construction Waste Management And Disposal | 54126.08 | 478.26 | 54604.34 | 22
KSA Project | Cost-000001 | SC-233400-001 | Hvac Fans | 0 | 54400 | 54400 | 4
KSA Project | KSA-000084 | M-260519-001 | Low-Voltage Cables - Cu/Xlpe/Pvc | 0 | 52252.72 | 52252.72 | 10
KSA Project | Cost-000013 | SC-064100-001 | Architectural Wood Casework | 0 | 52035 | 52035 | 9
KSA Project | KSA-000084 | SEV-011100-001 | Summary Of Work | 50000 | 0 | 50000 | 2
KSA Project | Cost-000023 | Subtotal |  | 47940 | 1900 | 49840 | 14
KSA Project | Cost-000132 | M-310500-003 | Aggregates For Earthwork | 0 | 49544 | 49544 | 2
KSA Project | Cost-000029 | SC-116800-001 | Play Field Equipment And Structures | 0 | 49503 | 49503 | 14
KSA Project | Cost-000053 | SC-078400-001 | Firestopping | 0 | 49100.86 | 49100.86 | 4
KSA Project | Cost-000001 | SC-071300-001 | Sheet Waterproofing | 0 | 48880.8 | 48880.8 | 12
KSA Project | Cost-000135 | Subtotal |  | 7640 | 40550 | 48190 | 46
KSA Project | Cost-000001 | SC-337900-001 | Site Grounding | 0 | 47040.35 | 47040.35 | 2
KSA Project | KSA-000084 | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 0 | 46156 | 46156 | 10
KSA Project | Cost-000017 | MC-50 10 117-001 | Marble Flooring Tiles | 0 | 45318.43 | 45318.43 | 4
KSA Project | Cost-000140 | SEV-014100-018 | Project Security | 45000 | 0 | 45000 | 3
KSA Project | Cost-000148 | SEV-017100-018 | Demobalization | 24300 | 20700 | 45000 | 4
KSA Project | Cost-000148 | Subtotal |  | 24300 | 20700 | 45000 | 4
KSA Project | Cost-000149 | SEV-017400-004 | Construction Waste Management And Disposal | 30550 | 14050 | 44600 | 9
KSA Project | KSA-000084 | SEV-014100-011 | Employee Transportation | 24401.65 | 19000 | 43401.65 | 4
KSA Project | KSA-000084 | SC-024100-001 | Demolition | 40160 | 0 | 40160 | 4
KSA Project | KSA-000084 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 0 | 38725.7 | 38725.7 | 26
KSA Project | KSA-000084 | SC-101400-001 | Signage | 0 | 38000 | 38000 | 3
KSA Project | Cost-000114 | ME-503020-001 | Cable Trays - Hdg Steel Cable Tray | 0 | 37602.28 | 37602.28 | 29
KSA Project | Cost-000114 | Subtotal |  | 0 | 37602.28 | 37602.28 | 29
KSA Project | KSA-000084 | SEV-014500-007 | Testing Laboratory Services | 0 | 36111.9 | 36111.9 | 72
KSA Project | Cost-000149 | SEV-017100-002 | Mobilization | 15160.03 | 19577.6 | 34737.63 | 15
KSA Project | Cost-000087 | Subtotal |  | 31423 | 3259.84 | 34682.84 | 18
KSA Project | Cost-000046 | M-032100-001 | Reinforcement Bars | 0 | 34200 | 34200 | 2
KSA Project | Cost-000144 | SEV-014100-009 | Employee Food | 16288.78 | 17100.04 | 33388.82 | 6
KSA Project | Cost-000144 | Subtotal |  | 16288.78 | 17100.04 | 33388.82 | 6
KSA Project | KSA-000084 | ME-503750-001 | Electrical Accessories | 0 | 32719.16 | 32719.16 | 47
KSA Project | Cost-000001 | M-014300-014 | Saftey Tools | 0 | 32653.13 | 32653.13 | 67
KSA Project | Cost-000135 | SEV-014300-011 | Safety Training | 2100 | 30230 | 32330 | 36
KSA Project | Cost-000017 | M-015100-009 | Temporary Water | 14555 | 17350 | 31905 | 8
KSA Project | KSA-000084 | M-015100-009 | Temporary Water | 25335 | 6435 | 31770 | 10
KSA Project | Cost-000087 | SEV-014100-017 | Manpower Rental | 31423 | 0 | 31423 | 4
KSA Project | KSA-000084 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 0 | 31387.53 | 31387.53 | 57
KSA Project | KSA-000084 | SEV-014300-012 | Safety 3rd Party Testing | 9027.39 | 21700 | 30727.39 | 40
KSA Project | Cost-000091 | M-221100-004 | Facility Water Distribution-Cpvc Pipe | 0 | 30685 | 30685 | 22
KSA Project | KSA-000084 | SEV-014500-005 | Testing And Inspecting Services | 5780 | 24679.8 | 30459.8 | 4
KSA Project | Cost-000001 | M-092100-001 | Plaster And Gypsum Board Assemblies | 0 | 30071.3 | 30071.3 | 2
KSA Project | Cost-000059 | M-032100-001 | Reinforcement Bars | 0 | 29960 | 29960 | 1
KSA Project | Cost-000059 | Subtotal |  | 0 | 29960 | 29960 | 1
KSA Project | Cost-000129 | M-018500-003 | Fuel | 0 | 29604.23 | 29604.23 | 9
KSA Project | KSA-000084 | MC-50 10 79-001 | Copper Wire | 0 | 29560.5 | 29560.5 | 2
KSA Project | KSA-000084 | MC-50 10 89-001 | Wooden Lattice Panels | 0 | 29400 | 29400 | 2
KSA Project | Cost-000023 | M-015100-009 | Temporary Water | 28940 | 0 | 28940 | 8
KSA Project | Cost-000038 | SC-099100-001 | Painting | 19879.3 | 8120.7 | 28000 | 2
KSA Project | Cost-000038 | Subtotal |  | 19879.3 | 8120.7 | 28000 | 2
KSA Project | KSA-000084 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 0 | 27762.55 | 27762.55 | 10
KSA Project | KSA-000084 | SEV-019300-004 | Maintenance Fees | 8300 | 19200 | 27500 | 20
KSA Project | Cost-000035 | SC-042200-001 | Concrete Unit Masonry | 0 | 27500 | 27500 | 1
KSA Project | Cost-000035 | Subtotal |  | 0 | 27500 | 27500 | 1
KSA Project | Cost-000056 | Subtotal |  | 0 | 27360 | 27360 | 3
KSA Project | Cost-000018 | SEV-014100-017 | Manpower Rental | 23700 | 3430 | 27130 | 2
KSA Project | Cost-000018 | Subtotal |  | 23700 | 3430 | 27130 | 2
KSA Project | Cost-000029 | SC-116600-001 | Athletic Equipment | 0 | 24751.5 | 24751.5 | 7
KSA Project | Cost-000131 | SEV-015400-005 | Temporary Scaffolding And Platforms | 0 | 24652.09 | 24652.09 | 20
KSA Project | Cost-000041 | SC-071300-001 | Sheet Waterproofing | 0 | 24440.4 | 24440.4 | 6
KSA Project | Cost-000140 | SEV-014300-014 | Saftey Tools | 17549.9 | 6890 | 24439.9 | 37
KSA Project | Cost-000090 | Subtotal |  | 0 | 24080 | 24080 | 2
KSA Project | KSA-000084 | M-018500-003 | Fuel | 0 | 23109.85 | 23109.85 | 5
KSA Project | Cost-000095 | Subtotal |  | 0 | 22949.48 | 22949.48 | 47
KSA Project | Cost-000090 | SC-467600-001 | Residuals Dewatering Equipment | 0 | 22880 | 22880 | 1
KSA Project | KSA-000084 | ME-503010-019 | Raceway And Boxes - Liquid Tight Flexible Conduit | 0 | 22664.5 | 22664.5 | 7
KSA Project | Cost-000140 | M-014300-014 | Saftey Tools | 0 | 22410.2 | 22410.2 | 42
KSA Project | Cost-000099 | MM-502010-027 | Fixing Brackets | 0 | 21963.28 | 21963.28 | 1
KSA Project | Cost-000099 | Subtotal |  | 0 | 21963.28 | 21963.28 | 1
KSA Project | Cost-000142 | SEV-014000-004 | Hand Tools | 21600 | 0 | 21600 | 1
KSA Project | Cost-000142 | Subtotal |  | 21600 | 0 | 21600 | 1
KSA Project | Cost-000023 | SC-044200-001 | Exterior Stone Cladding | 19000 | 1900 | 20900 | 2
KSA Project | Cost-000009 | M-061300-001 | Heavy Timber Construction | 0 | 19600 | 19600 | 1
KSA Project | KSA-000084 | M-051200-001 | Structural Steel Framing | 0 | 19200 | 19200 | 1
KSA Project | Cost-000056 | MC-50 10 126-001 | Epoxy Flooring Coating | 0 | 18760 | 18760 | 1
KSA Project | Cost-000130 | Subtotal |  | 860 | 17315.04 | 18175.04 | 34
KSA Project | Cost-000095 | SC-078400-001 | Firestopping | 0 | 17949.48 | 17949.48 | 46
KSA Project | Cost-000130 | SEV-019300-004 | Maintenance Fees | 860 | 16915.04 | 17775.04 | 33
KSA Project | Cost-000149 | SC-132200-001 | Office Shelters And Booths | 0 | 17391.3 | 17391.3 | 1
KSA Project | Cost-000091 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 0 | 17061.96 | 17061.96 | 18
KSA Project | KSA-000084 | SEV-016500-001 | Product Delivery Requirements | 16950 | 0 | 16950 | 1
KSA Project | KSA-000084 | MC-50 10 23-001 | High Efficiency Curing Compound | 0 | 16800 | 16800 | 14
KSA Project | KSA-000084 | SEV-017100-015 | Staff Accommodation | 0 | 16695.65 | 16695.65 | 1
KSA Project | KSA-000084 | M-014300-014 | Saftey Tools | 0 | 15964 | 15964 | 45
KSA Project | KSA-000084 | MC-50 10 126-001 | Epoxy Flooring Coating | 0 | 15435 | 15435 | 2
KSA Project | Cost-000140 | SEV-014300-011 | Safety Training | 0 | 14830 | 14830 | 14
KSA Project | Cost-000001 | M-072100-001 | Thermal Insulation | 0 | 14800 | 14800 | 2
KSA Project | KSA-000084 | M-072100-001 | Thermal Insulation | 0 | 14600 | 14600 | 3
KSA Project | Cost-000093 | Subtotal |  | 0 | 14559.1 | 14559.1 | 13
KSA Project | Cost-000046 | SEV-018500-010 | Equipment Rental | 0 | 14260 | 14260 | 5
KSA Project | Cost-000011 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 12187.72 | 2050 | 14237.72 | 8
KSA Project | Cost-000054 | M-092100-001 | Plaster And Gypsum Board Assemblies | 0 | 13656 | 13656 | 2
KSA Project | KSA-000084 | MT-505010-001 | Safety Vest | 0 | 13629.95 | 13629.95 | 30
KSA Project | KSA-000084 | M-221300-001 | Facility Sanitary Sewerage-Pvc Pipe | 0 | 13525.64 | 13525.64 | 61
KSA Project | Cost-000135 | SEV-014300-012 | Safety 3rd Party Testing | 5540 | 7920 | 13460 | 9
KSA Project | KSA-000084 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 0 | 13318.7 | 13318.7 | 16
KSA Project | Cost-000093 | M-221300-008 | Sanitary Drains-Ci Floor Drain | 0 | 13059.7 | 13059.7 | 11
KSA Project | KSA-000084 | SEV-016500-002 | Materials Transportation | 0 | 12900 | 12900 | 1
KSA Project | Cost-000058 | M-032100-001 | Reinforcement Bars | 0 | 12840 | 12840 | 1
KSA Project | Cost-000058 | Subtotal |  | 0 | 12840 | 12840 | 1
KSA Project | Cost-000053 | MC-50 10 103-001 | Porous Concrete Blocks | 0 | 12090 | 12090 | 4
KSA Project | Cost-000054 | MC-50 10 103-001 | Porous Concrete Blocks | 0 | 12059.5 | 12059.5 | 6
KSA Project | KSA-000084 | M-452900-001 | Petroleum And Coal Products Manufacturing Equipment | 0 | 12051 | 12051 | 35
KSA Project | Cost-000001 | M-092500-001 | Other Plastering | 0 | 12000 | 12000 | 3
KSA Project | Cost-000131 | SEV-017400-004 | Construction Waste Management And Disposal | 0 | 12000 | 12000 | 2
KSA Project | KSA-000084 | M-036300-001 | Epoxy Grouting | 0 | 11808 | 11808 | 2
KSA Project | KSA-000084 | M-099100-001 | Painting | 0 | 11804 | 11804 | 11
KSA Project | Cost-000094 | MC-50 20 00-014 | Supporting System - Anchor Bolt | 0 | 11000 | 11000 | 1
KSA Project | Cost-000094 | Subtotal |  | 0 | 11000 | 11000 | 1
KSA Project | KSA-000084 | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 0 | 10937.14 | 10937.14 | 18
KSA Project | KSA-000084 | ME-503010-032 | Raceway And Boxes - Rigid Steel Conduit (Rgs Conduit) | 0 | 10630 | 10630 | 8
KSA Project | Cost-000001 | M-310500-011 | Cement And Concrete For Earthwork | 0 | 10620 | 10620 | 1
KSA Project | KSA-000084 | SEV-013500-023 | Period Treatment Procedures | 0 | 10500 | 10500 | 1
KSA Project | Cost-000112 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 10400 | 0 | 10400 | 1
KSA Project | Cost-000112 | Subtotal |  | 10400 | 0 | 10400 | 1
KSA Project | KSA-000084 | ME-503010-047 | Raceway And Boxes - Square Box Flat Blank | 0 | 10000 | 10000 | 2
KSA Project | Cost-000100 | SEV-014500-007 | Testing Laboratory Services | 9504 | 0 | 9504 | 1
KSA Project | Cost-000100 | Subtotal |  | 9504 | 0 | 9504 | 1
KSA Project | Cost-000132 | SC-064100-001 | Architectural Wood Casework | 0 | 9500 | 9500 | 1
KSA Project | KSA-000084 | SEV-017100-002 | Mobilization | 4594.2 | 4725.22 | 9319.42 | 4
KSA Project | Cost-000136 | SEV-014100-009 | Employee Food | 0 | 9282.76 | 9282.76 | 2
KSA Project | Cost-000136 | Subtotal |  | 0 | 9282.76 | 9282.76 | 2
KSA Project | KSA-000084 | MC-50 10 55-001 | Epoxy Tile Adhesive & Grout | 0 | 8600 | 8600 | 2
KSA Project | Cost-000056 | MC-50 10 55-001 | Epoxy Tile Adhesive & Grout | 0 | 8600 | 8600 | 2
KSA Project | Cost-000060 | M-032100-001 | Reinforcement Bars | 0 | 8560 | 8560 | 1
KSA Project | Cost-000060 | Subtotal |  | 0 | 8560 | 8560 | 1
KSA Project | KSA-000084 | SEV-018900-004 | Site Plumbing Utilities Performance Requirements | 8400 | 0 | 8400 | 5
KSA Project | Cost-000001 | M-016500-002 | Materials Transportation | 0 | 8400 | 8400 | 1
KSA Project | Cost-000140 | MT-505010-001 | Safety Vest | 0 | 8177.53 | 8177.53 | 17
KSA Project | Cost-000001 | SC-028700-006 | Removal And Disposal Of Materials With Mold | 0 | 7920 | 7920 | 1
KSA Project | Cost-000066 | Subtotal |  | 0 | 7838.57 | 7838.57 | 6
KSA Project | KSA-000084 | M-221100-003 | Facility Water Distribution-Pvc Pipe | 0 | 7638 | 7638 | 6
KSA Project | KSA-000084 | M-310500-011 | Cement And Concrete For Earthwork | 0 | 7080 | 7080 | 1
KSA Project | KSA-000084 | M-054500-001 | Metal Support Assemblies | 0 | 6830 | 6830 | 5
KSA Project | KSA-000084 | ME-503010-050 | Raceway And Boxes - Ring Extension Square Boxes | 0 | 6770 | 6770 | 3
KSA Project | Cost-000149 | SEV-017400-001 | Cleaning And Waste Management | 3250 | 3250 | 6500 | 2
KSA Project | KSA-000084 | ME-503010-018 | Raceway And Boxes - Flexible Metal Conduit | 0 | 6380.7 | 6380.7 | 3
KSA Project | KSA-000084 | MC-50 10 50-001 | Filler Board | 0 | 6295 | 6295 | 2
KSA Project | Cost-000001 | SC-313100-002 | Termite Control | 0 | 6000 | 6000 | 2
KSA Project | Cost-000091 | SC-078400-001 | Firestopping | 0 | 5970.38 | 5970.38 | 12
KSA Project | Cost-000054 | M-040500-002 | Masonry Mortaring | 0 | 5775 | 5775 | 1
KSA Project | KSA-000084 | M-014300-013 | Safety Protective Equipment | 0 | 5770.65 | 5770.65 | 13
KSA Project | KSA-000084 | M-018600-003 | Plumbing Performance Requirements | 0 | 5741 | 5741 | 24
KSA Project | KSA-000084 | MC-50 10 153-001 | Polyethylene Sheeting (For Dust Protection) | 0 | 5625 | 5625 | 2
KSA Project | Cost-000001 | M-013600-008 | Printers | 0 | 5535 | 5535 | 6
KSA Project | KSA-000084 | SEV-013700-003 | Property Insurance | 5525 | 0 | 5525 | 1
KSA Project | Cost-000113 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 2661.2 | 2658.8 | 5320 | 7
KSA Project | Cost-000113 | Subtotal |  | 2661.2 | 2658.8 | 5320 | 7
KSA Project | Cost-000046 | SEV-017400-001 | Cleaning And Waste Management | 5000 | 250 | 5250 | 4
KSA Project | KSA-000084 | M-101400-001 | Signage | 0 | 5234.4 | 5234.4 | 1
KSA Project | KSA-000084 | ME-503010-048 | Raceway And Boxes - Octagonal Boxes | 0 | 5100 | 5100 | 1
KSA Project | Cost-000019 | M-087100-018 | Threshold | 0 | 5017.13 | 5017.13 | 1
KSA Project | Cost-000019 | Subtotal |  | 0 | 5017.13 | 5017.13 | 1
KSA Project | Cost-000095 | MC-50 20 00-014 | Supporting System - Anchor Bolt | 0 | 5000 | 5000 | 1
KSA Project | Cost-000001 | SC-347700-001 | Transportation Equipment | 0 | 4959.73 | 4959.73 | 2
KSA Project | KSA-000084 | SEV-014300-011 | Safety Training | 3100 | 1750 | 4850 | 7
KSA Project | KSA-000084 | MT-505056-001 | Hand Tools | 0 | 4827 | 4827 | 20
KSA Project | KSA-000084 | SC-134800-001 | Sound, Vibration, And Seismic Control | 4800 | 0 | 4800 | 2
KSA Project | Cost-000009 | MC-50 10 172-001 | Civil Accessories | 0 | 4757.25 | 4757.25 | 6
KSA Project | KSA-000084 | M-040500-004 | Epoxy Masonry Mortaring | 0 | 4620 | 4620 | 1
KSA Project | KSA-000084 | ME-503010-046 | Raceway And Boxes - Square Boxes | 0 | 4560 | 4560 | 2
KSA Project | Cost-000054 | M-015100-009 | Temporary Water | 4550 | 0 | 4550 | 1
KSA Project | KSA-000084 | SEV-013100-003 | Facility Services Coordination | 0 | 4540 | 4540 | 3
KSA Project | KSA-000084 | ME-503020-045 | Cable Trays - Straight Cable Ladder | 0 | 4388.68 | 4388.68 | 7
KSA Project | KSA-000084 | SEV-017100-004 | Site Accommodation | 0 | 4350 | 4350 | 1
KSA Project | KSA-000084 | MM-502010-078 | Cpvc Union | 0 | 4292.44 | 4292.44 | 30
KSA Project | Cost-000046 | SEV-014000-004 | Hand Tools | 0 | 4180 | 4180 | 15
KSA Project | KSA-000084 | M-093400-001 | Waterproofing-Membrane Tiling | 0 | 4140 | 4140 | 1
KSA Project | Cost-000011 | ME-503750-001 | Electrical Accessories | 2600 | 1500 | 4100 | 3
KSA Project | KSA-000084 | M-265100-010 | Interior Lighting - Flood Lighting Fixtures | 0 | 3900 | 3900 | 2
KSA Project | Cost-000129 | M-018500-004 | Diesel | 3804.35 | 0 | 3804.35 | 1
KSA Project | Cost-000103 | SC-078400-001 | Firestopping | 0 | 3719.44 | 3719.44 | 40
KSA Project | Cost-000103 | Subtotal |  | 0 | 3719.44 | 3719.44 | 40
KSA Project | Cost-000033 | SEV-017100-002 | Mobilization | 0 | 3600 | 3600 | 1
KSA Project | Cost-000033 | Subtotal |  | 0 | 3600 | 3600 | 1
KSA Project | Cost-000115 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 3570 | 0 | 3570 | 1
KSA Project | Cost-000115 | Subtotal |  | 3570 | 0 | 3570 | 1
KSA Project | Cost-000087 | SC-078400-001 | Firestopping | 0 | 3259.84 | 3259.84 | 14
KSA Project | Cost-000045 | MC-50 10 83-001 | Plywood Sheets (Marine Grade) | 0 | 3160 | 3160 | 1
KSA Project | KSA-000084 | M-271100-007 | Communications Cabinets, Racks, Frames, And Enclosures - Mai | 0 | 3079.5 | 3079.5 | 16
KSA Project | KSA-000084 | MC-50 20 00-010 | Supporting System - Threaded Rod | 0 | 3009.76 | 3009.76 | 2
KSA Project | Cost-000097 | MM-502010-027 | Fixing Brackets | 0 | 3000 | 3000 | 1
KSA Project | Cost-000097 | Subtotal |  | 0 | 3000 | 3000 | 1
KSA Project | Cost-000066 | M-224100-004 | Flush Tank | 0 | 2861.5 | 2861.5 | 1
KSA Project | Cost-000140 | SEV-014300-012 | Safety 3rd Party Testing | 0 | 2850 | 2850 | 9
KSA Project | KSA-000084 | M-013600-033 | Network Cables | 0 | 2755 | 2755 | 4
KSA Project | KSA-000084 | M-221100-009 | Domestic Water Piping Specialties-Gate Valve | 0 | 2735.57 | 2735.57 | 5
KSA Project | Cost-000001 | MT-505011-001 | Safety Shoes | 0 | 2650 | 2650 | 2
KSA Project | KSA-000084 | MM-502010-016 | Pipe Clamps | 0 | 2646.78 | 2646.78 | 29
KSA Project | KSA-000084 | M-262700-054 | Wiring Devices - Double Pole Switch | 0 | 2500 | 2500 | 1
KSA Project | KSA-000084 | M-262800-009 | Low-Voltage Circuit Protective Devices - Fused Disconnect Sw | 0 | 2500 | 2500 | 1
KSA Project | Cost-000001 | SC-280800-001 | Testing And Commissioning | 0 | 2460 | 2460 | 8
KSA Project | Cost-000138 | SC-134800-001 | Sound, Vibration, And Seismic Control | 0 | 2400 | 2400 | 1
KSA Project | Cost-000135 | SEV-013500-010 | Owner Safety Requirements | 0 | 2400 | 2400 | 1
KSA Project | Cost-000140 | MT-504062-001 | Safety Gloves | 0 | 2360 | 2360 | 1
KSA Project | Cost-000001 | M-462500-001 | Oil And Grease Separation And Removal Equipment | 0 | 2350 | 2350 | 2
KSA Project | Cost-000052 | M-079200-001 | Joint Sealants | 0 | 2280 | 2280 | 1
KSA Project | Cost-000052 | Subtotal |  | 0 | 2280 | 2280 | 1
KSA Project | KSA-000084 | MM-502010-079 | Cpvc Male Adapter | 0 | 2245.74 | 2245.74 | 29
KSA Project | KSA-000084 | SEV-015200-001 | Construction Facilities | 0 | 2200 | 2200 | 2
KSA Project | KSA-000084 | MT-504053-001 | Tile Spacers | 0 | 2197 | 2197 | 4
KSA Project | KSA-000084 | M-015100-004 | Temporary Fuel Oil | 0 | 2148 | 2148 | 3
KSA Project | KSA-000084 | MC-50 10 78-001 | Rebar Tie Wire | 0 | 2130.1 | 2130.1 | 1
KSA Project | Cost-000001 | MT-505010-001 | Safety Vest | 0 | 2040 | 2040 | 1
KSA Project | KSA-000084 | MM-502010-097 | Pvc - Female Tee | 0 | 2032.52 | 2032.52 | 7
KSA Project | KSA-000084 | M-323100-001 | Fences And Gates | 0 | 2020 | 2020 | 5
KSA Project | Cost-000117 | ME-503010-017 | Raceway And Boxes - Emt Conduit | 1910 | 0 | 1910 | 2
KSA Project | KSA-000084 | ME-503010-004 | Raceway And Boxes - Pvc Female Adaptor | 0 | 1878.29 | 1878.29 | 4
KSA Project | KSA-000084 | M-221300-002 | Facility Sanitary Sewerage-Hdpe Pipe | 0 | 1860 | 1860 | 4
KSA Project | KSA-000084 | MM-502010-093 | Pvc 45 Elbow | 0 | 1786.07 | 1786.07 | 7
KSA Project | KSA-000084 | SEV-015400-005 | Temporary Scaffolding And Platforms | 0 | 1714.65 | 1714.65 | 4
KSA Project | Cost-000066 | M-224100-001 | Water Closet-Wc | 0 | 1697.5 | 1697.5 | 1
KSA Project | KSA-000084 | MC-50 20 00-017 | Supporting System - C Clamp | 0 | 1678.64 | 1678.64 | 14
KSA Project | KSA-000084 | M-013600-008 | Printers | 0 | 1600 | 1600 | 1
KSA Project | KSA-000084 | M-221400-009 | Roof Drains-Scupper | 0 | 1596 | 1596 | 2
KSA Project | Cost-000066 | M-224100-005 | Wash Basin | 0 | 1562.67 | 1562.67 | 1
KSA Project | KSA-000084 | MM-502010-095 | Pvc Reducing Tee | 0 | 1542.34 | 1542.34 | 9
KSA Project | Cost-000001 | SC-042500-001 | Unit Masonry Panels | 1530 | 0 | 1530 | 1
KSA Project | Cost-000009 | M-079200-001 | Joint Sealants | 0 | 1515.15 | 1515.15 | 1
KSA Project | KSA-000084 | MM-502010-083 | Cpvc Reducing Adapter | 0 | 1495.5 | 1495.5 | 43
KSA Project | KSA-000084 | SEV-014000-004 | Hand Tools | 0 | 1492.18 | 1492.18 | 1
KSA Project | KSA-000084 | MC-50 10 122-001 | Epoxy Floor Sealant | 0 | 1487.5 | 1487.5 | 2
KSA Project | Cost-000054 | MC-50 10 122-001 | Epoxy Floor Sealant | 0 | 1487.5 | 1487.5 | 2
KSA Project | KSA-000084 | MM-502010-086 | Cpvc - Equal Tee | 0 | 1452.24 | 1452.24 | 15
KSA Project | KSA-000084 | M-260519-006 | Low-Voltage Cables - Al/Xlpe/Swa/Pvc | 0 | 1440 | 1440 | 1
KSA Project | KSA-000084 | M-265500-001 | Special Purpose Lighting | 0 | 1430 | 1430 | 2
KSA Project | KSA-000084 | MM-502010-096 | Pvc Reducing Adapter | 0 | 1429.96 | 1429.96 | 6
KSA Project | Cost-000001 | M-112800-001 | Office Equipment | 0 | 1400 | 1400 | 2
KSA Project | Cost-000093 | M-221400-009 | Roof Drains-Scupper | 0 | 1386 | 1386 | 1
KSA Project | KSA-000084 | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 0 | 1331.72 | 1331.72 | 4
KSA Project | Cost-000011 | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 0 | 1306 | 1306 | 2
KSA Project | KSA-000084 | MT-504022-001 | Sledgehammer | 0 | 1300 | 1300 | 1
KSA Project | Cost-000149 | ME-503750-001 | Electrical Accessories | 0 | 1280 | 1280 | 2
KSA Project | KSA-000084 | M-016500-002 | Materials Transportation | 0 | 1262 | 1262 | 3
KSA Project | Cost-000091 | MC-50 20 00-003 | Supporting System - Flat Washer | 0 | 1261.2 | 1261.2 | 1
KSA Project | KSA-000084 | MT-505011-001 | Safety Shoes | 0 | 1219.28 | 1219.28 | 11
KSA Project | KSA-000084 | MM-502010-081 | Cpvc 90 Elbow | 0 | 1218.82 | 1218.82 | 19
KSA Project | KSA-000084 | ME-503010-028 | Raceway And Boxes - Insulated Emt Bushing | 0 | 1200 | 1200 | 1
KSA Project | Cost-000090 | MC-50 20 00-002 | Supporting System - Hexa Nut | 0 | 1200 | 1200 | 1
KSA Project | Cost-000129 | M-462500-001 | Oil And Grease Separation And Removal Equipment | 0 | 1191 | 1191 | 2
KSA Project | KSA-000084 | MM-502010-094 | Pvc 90 Elbow | 0 | 1186.34 | 1186.34 | 11
KSA Project | KSA-000084 | SC-023200-003 | Material Testing | 1045 | 0 | 1045 | 7
KSA Project | KSA-000084 | M-013500-028 | Office Furniture | 0 | 1000 | 1000 | 1
KSA Project | KSA-000084 | M-260526-021 | Grounding And Bonding - Bare Copper Cable | 0 | 927 | 927 | 1
KSA Project | Cost-000011 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 0 | 915 | 915 | 4
KSA Project | KSA-000084 | MM-502010-013 | Anchor Bolt | 0 | 902.5 | 902.5 | 9
KSA Project | KSA-000084 | SEV-015700-003 | Temporary Pest Control | 0 | 900 | 900 | 2
KSA Project | Cost-000066 | M-224100-018 | Hand Spray | 0 | 873 | 873 | 1
KSA Project | KSA-000084 | MT-505012-001 | Safety Glasses | 0 | 825 | 825 | 1
KSA Project | Cost-000011 | M-262700-033 | Wiring Devices - Lighting Switches | 0 | 780 | 780 | 2
KSA Project | KSA-000084 | MM-502010-080 | Cpvc 45 Elbow | 0 | 771.26 | 771.26 | 14
KSA Project | KSA-000084 | ME-503010-020 | Raceway And Boxes - Emt Compression Connector | 0 | 750 | 750 | 1
KSA Project | KSA-000084 | ME-503010-053 | Raceway And Boxes - Utility Rectangular Boxes | 0 | 720 | 720 | 1
KSA Project | Cost-000001 | MT-504062-001 | Safety Gloves | 0 | 700 | 700 | 2
KSA Project | Cost-000149 | M-284600-003 | Fire Alarm System - Smoke Detector | 0 | 675 | 675 | 1
KSA Project | KSA-000084 | M-013600-009 | Plotters | 0 | 600 | 600 | 1
KSA Project | KSA-000084 | M-221100-019 | Domestic Water Piping Specialties-Wha | 0 | 575.52 | 575.52 | 1
KSA Project | Cost-000149 | ME-503370-001 | Emergency Lights | 0 | 550 | 550 | 1
KSA Project | KSA-000084 | MC-50 20 00-008 | Supporting System - U-Strut Channel | 0 | 515.92 | 515.92 | 1
KSA Project | Cost-000066 | M-224100-012 | Shower Mixer | 0 | 504.4 | 504.4 | 1
KSA Project | KSA-000084 | MC-50 20 00-014 | Supporting System - Anchor Bolt | 0 | 497.76 | 497.76 | 2
KSA Project | KSA-000084 | M-236300-001 | Refrigerant Condensers | 0 | 450 | 450 | 1
KSA Project | Cost-000110 | ME-503010-001 | Raceway And Boxes - Pvc Conduit | 441.3 | 0 | 441.3 | 2
KSA Project | Cost-000001 | MT-505014-001 | Hard Hat (Helmet) | 0 | 400 | 400 | 1
KSA Project | Cost-000130 | SEV-017800-012 | Spare Parts | 0 | 400 | 400 | 1
KSA Project | KSA-000084 | MM-502010-092 | Pvc Male Adapter | 0 | 391.85 | 391.85 | 4
KSA Project | Cost-000110 | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 390.3 | 0 | 390.3 | 1
KSA Project | Cost-000110 | ME-503010-012 | Raceway And Boxes - Pvc Bend Heavy Gauge | 388.2 | 0 | 388.2 | 3
KSA Project | Cost-000149 | M-265200-003 | Safety Lighting - Exit Signs | 0 | 350 | 350 | 1
KSA Project | KSA-000084 | MT-505048-001 | Breathing Mask (Full Face) | 0 | 349 | 349 | 3
KSA Project | Cost-000066 | M-224100-011 | Wash Basin Mixer | 0 | 339.5 | 339.5 | 1
KSA Project | KSA-000084 | M-230700-013 | Duct Tape | 0 | 327 | 327 | 3
KSA Project | KSA-000084 | MC-50 20 00-001 | Supporting System - Hexa Bolt | 0 | 293.76 | 293.76 | 1
KSA Project | KSA-000084 | M-262700-018 | Wiring Devices - Single Socket Outlet 13A Switched Wheather | 0 | 251 | 251 | 1
KSA Project | KSA-000084 | M-224100-020 | Water Flexible Hose | 0 | 225 | 225 | 4
KSA Project | Cost-000001 | M-230700-013 | Duct Tape | 0 | 200 | 200 | 1
KSA Project | Cost-000001 | MT-505048-001 | Breathing Mask (Full Face) | 0 | 200 | 200 | 1
KSA Project | KSA-000084 | ME-503480-001 | Cable Sleeving | 0 | 180 | 180 | 1
KSA Project | Cost-000140 | MT-505014-001 | Hard Hat (Helmet) | 0 | 180 | 180 | 2
KSA Project | Cost-000140 | MT-505011-001 | Safety Shoes | 0 | 170 | 170 | 1
KSA Project | Cost-000001 | MC-50 10 165-001 | Warning Tape | 0 | 162 | 162 | 1
KSA Project | KSA-000084 | ME-503010-025 | Raceway And Boxes - Emt Strap Clamp 1-Hole ( C Clamp) | 0 | 125 | 125 | 1
KSA Project | KSA-000084 | M-230700-016 | Duct Glue | 0 | 120 | 120 | 1
KSA Project | KSA-000084 | MC-50 20 00-002 | Supporting System - Hexa Nut | 0 | 116.58 | 116.58 | 3
KSA Project | Cost-000091 | MM-502010-079 | Cpvc Male Adapter | 0 | 116.25 | 116.25 | 2
KSA Project | KSA-000084 | MC-50 20 00-003 | Supporting System - Flat Washer | 0 | 115.88 | 115.88 | 3
KSA Project | KSA-000084 | M-221300-014 | Sanitary Drains-Ci Cleanout | 0 | 113.4 | 113.4 | 1
KSA Project | Cost-000093 | M-221300-014 | Sanitary Drains-Ci Cleanout | 0 | 113.4 | 113.4 | 1
KSA Project | KSA-000084 | MC-50 10 170-001 | Construction Waste Bags | 0 | 110 | 110 | 1
KSA Project | Cost-000149 | ME-503030-001 | Underground Ducts And Raceways - Upvc Pipes | 0 | 106.25 | 106.25 | 1
KSA Project | KSA-000084 | M-221100-022 | Domestic Water Piping Specialties-Hose Bib | 0 | 104.82 | 104.82 | 1
KSA Project | KSA-000084 | MT-504017-001 | Handsaw | 0 | 100 | 100 | 1
KSA Project | Cost-000149 | M-284600-004 | Fire Alarm System - Heat Detector | 0 | 90 | 90 | 1
KSA Project | KSA-000084 | ME-503010-059 | Raceway And Boxes - Wearther Proof Boxes | 0 | 88 | 88 | 1
KSA Project | Cost-000001 | MT-504066-001 | Dust Mask | 0 | 80 | 80 | 1
KSA Project | KSA-000084 | M-262800-014 | Enclosed Switches | 0 | 75 | 75 | 1
KSA Project | Cost-000110 | ME-503010-002 | Raceway And Boxes - Pvc Coupling | 53.57 | 13.63 | 67.2 | 4
KSA Project | KSA-000084 | M-224100-018 | Hand Spray | 0 | 60 | 60 | 1
KSA Project | KSA-000084 | M-233700-010 | Exhaust Air Louver | 0 | 58.5 | 58.5 | 1
KSA Project | KSA-000084 | MM-502010-082 | Cpvc Reducing Tee | 0 | 54.12 | 54.12 | 3
KSA Project | KSA-000084 | MT-505018-001 | Knee Pads | 0 | 50 | 50 | 1
KSA Project | Cost-000001 | MT-504032-001 | Clamps | 0 | 45 | 45 | 1
KSA Project | Cost-000001 | SC-075200-001 | Modified Bituminous Membrane Roofing | 0 | 45 | 45 | 2
KSA Project | KSA-000084 | MM-502010-014 | U-Bolts | 0 | 38.4 | 38.4 | 1
KSA Project | KSA-000084 | ME-503060-001 | Cable Connectors | 0 | 37.5 | 37.5 | 1
KSA Project | Cost-000149 | M-262200-001 | Low-Voltage Transformers | 0 | 36 | 36 | 1
KSA Project | Cost-000149 | ME-503030-007 | Underground Ducts And Raceways - Upvc Bell End Coupling | 0 | 34 | 34 | 1
KSA Project | Cost-000041 | SC-075200-001 | Modified Bituminous Membrane Roofing | 0 | 22.5 | 22.5 | 1
KSA Project | KSA-000084 | ME-503010-007 | Raceway And Boxes - Pvc Pound Spring Clips | 0 | 6 | 6 | 1
KSA Project | KSA-000084 | MM-502010-091 | Pvc Union | 0 | 2.4 | 2.4 | 1
KSA Project | KSA-000084 | M-014100-017 | Manpower Rental | 0 | 0 | 0 | 2
KSA Project | KSA-000084 | MT-504062-001 | Safety Gloves | 0 | 0 | 0 | 2
KSA Project | Cost-000133 | M-014100-017 | Manpower Rental | 0 | 0 | 0 | 2
KSA Project | Cost-000023 | M-014100-017 | Manpower Rental | 0 | 0 | 0 | 4