## README
Cost Control / WBS — Demo Workbook
PORTFOLIO DEMO · ILLUSTRATIVE SAMPLE · Hamza Fayz Fathy
Purpose
Shows committed / received / invoiced / accrual / actual / forecast at activity level, rolled up the same way at BOQ, WBS, Project — with full traceability from activity cost back to the originating PO line.
Sheets
WBS_Hierarchy · Activity_Cost_Facts · Summary_by_Project · Daily_Signals · Traceability
What this demo proves
1) A single fact model for committed vs actual, read at every level. 2) Daily signals are produced per priority with clear owner — not a month-end report. 3) Any posted value traces back through allocation and tax base to the source document.
Integrity checks
• Committed ≤ Budget per activity. • Received ≤ Committed. Invoiced ≤ Received. • Accrual = Received − Invoiced. • Roll-up totals match bottom-up activity sums.
Context for the portfolio
Supports flagship case 'D365 Project Cost Control Engine'. Uses the same projects (Aurora · Dune · Delta · Mesa) shown in the portfolio hero terminal.
Not for production use. Data is synthetic. Structure, logic, and relationships are realistic for illustration.

## WBS_Hierarchy
DEMO · WBS hierarchy — Project → WBS → BOQ → Activity
Level | Project | WBS | BOQ | Activity | Code
Project | Aurora |  |  |  | PRJ-AUR
WBS | Aurora | W1 · Civil works |  |  | PRJ-AUR · W1
BOQ | Aurora | W1 · Civil works | BOQ-1.1 · Foundations |  | PRJ-AUR · BOQ-1.1
Activity | Aurora | W1 · Civil works | BOQ-1.1 · Foundations | A1.1.1 · Excavation | PRJ-AUR · A1.1.1
Activity | Aurora | W1 · Civil works | BOQ-1.1 · Foundations | A1.1.2 · Blinding | PRJ-AUR · A1.1.2
Activity | Aurora | W1 · Civil works | BOQ-1.1 · Foundations | A1.1.3 · Rebar | PRJ-AUR · A1.1.3
BOQ | Aurora | W1 · Civil works | BOQ-1.2 · Structural |  | PRJ-AUR · BOQ-1.2
Activity | Aurora | W1 · Civil works | BOQ-1.2 · Structural | A1.2.1 · Columns | PRJ-AUR · A1.2.1
Activity | Aurora | W1 · Civil works | BOQ-1.2 · Structural | A1.2.2 · Slabs | PRJ-AUR · A1.2.2
WBS | Aurora | W2 · MEP |  |  | PRJ-AUR · W2
BOQ | Aurora | W2 · MEP | BOQ-2.1 · Electrical |  | PRJ-AUR · BOQ-2.1
Activity | Aurora | W2 · MEP | BOQ-2.1 · Electrical | A2.1.1 · Panels | PRJ-AUR · A2.1.1
Activity | Aurora | W2 · MEP | BOQ-2.1 · Electrical | A2.1.2 · Cabling | PRJ-AUR · A2.1.2
BOQ | Aurora | W2 · MEP | BOQ-2.2 · HVAC |  | PRJ-AUR · BOQ-2.2
Activity | Aurora | W2 · MEP | BOQ-2.2 · HVAC | A2.2.1 · Ducting | PRJ-AUR · A2.2.1
Activity | Aurora | W2 · MEP | BOQ-2.2 · HVAC | A2.2.2 · AHU | PRJ-AUR · A2.2.2
Project | Dune |  |  |  | PRJ-DUN
WBS | Dune | W1 · Earthworks |  |  | PRJ-DUN · W1
BOQ | Dune | W1 · Earthworks | BOQ-1.1 · Site prep |  | PRJ-DUN · BOQ-1.1
Activity | Dune | W1 · Earthworks | BOQ-1.1 · Site prep | A1.1.1 · Clearing | PRJ-DUN · A1.1.1
Activity | Dune | W1 · Earthworks | BOQ-1.1 · Site prep | A1.1.2 · Grading | PRJ-DUN · A1.1.2
WBS | Dune | W2 · Civil works |  |  | PRJ-DUN · W2
BOQ | Dune | W2 · Civil works | BOQ-2.1 · Foundations |  | PRJ-DUN · BOQ-2.1
Activity | Dune | W2 · Civil works | BOQ-2.1 · Foundations | A2.1.1 · Excavation | PRJ-DUN · A2.1.1
Activity | Dune | W2 · Civil works | BOQ-2.1 · Foundations | A2.1.2 · Rebar | PRJ-DUN · A2.1.2
BOQ | Dune | W2 · Civil works | BOQ-2.2 · Walls |  | PRJ-DUN · BOQ-2.2
Activity | Dune | W2 · Civil works | BOQ-2.2 · Walls | A2.2.1 · Blockwork | PRJ-DUN · A2.2.1
Project | Delta |  |  |  | PRJ-DLT
WBS | Delta | W1 · Structural |  |  | PRJ-DLT · W1
BOQ | Delta | W1 · Structural | BOQ-1.1 · Steel frame |  | PRJ-DLT · BOQ-1.1
Activity | Delta | W1 · Structural | BOQ-1.1 · Steel frame | A1.1.1 · Fabrication | PRJ-DLT · A1.1.1
Activity | Delta | W1 · Structural | BOQ-1.1 · Steel frame | A1.1.2 · Erection | PRJ-DLT · A1.1.2
WBS | Delta | W2 · Finishing |  |  | PRJ-DLT · W2
BOQ | Delta | W2 · Finishing | BOQ-2.1 · Flooring |  | PRJ-DLT · BOQ-2.1
Activity | Delta | W2 · Finishing | BOQ-2.1 · Flooring | A2.1.1 · Screed | PRJ-DLT · A2.1.1
Activity | Delta | W2 · Finishing | BOQ-2.1 · Flooring | A2.1.2 · Tiling | PRJ-DLT · A2.1.2
Project | Mesa |  |  |  | PRJ-MSA
WBS | Mesa | W1 · Utilities |  |  | PRJ-MSA · W1
BOQ | Mesa | W1 · Utilities | BOQ-1.1 · Water |  | PRJ-MSA · BOQ-1.1
Activity | Mesa | W1 · Utilities | BOQ-1.1 · Water | A1.1.1 · Piping | PRJ-MSA · A1.1.1
Activity | Mesa | W1 · Utilities | BOQ-1.1 · Water | A1.1.2 · Pumps | PRJ-MSA · A1.1.2
BOQ | Mesa | W1 · Utilities | BOQ-1.2 · Drainage |  | PRJ-MSA · BOQ-1.2
Activity | Mesa | W1 · Utilities | BOQ-1.2 · Drainage | A1.2.1 · Trenching | PRJ-MSA · A1.2.1
Activity | Mesa | W1 · Utilities | BOQ-1.2 · Drainage | A1.2.2 · Backfill | PRJ-MSA · A1.2.2

## Activity_Cost_Facts
DEMO · Activity-level cost facts — committed · received · invoiced · accrual · actual · forecast
Project | WBS | BOQ | Activity | Budget (SAR) | Committed | Received | Invoiced | Accrual | Actual | Forecast | Variance · Budget − Forecast | Variance % | Status
Aurora | W1 · Civil works | BOQ-1.1 · Foundations | A1.1.1 · Excavation | 114968 | 62082.72 | 52885.28 | 50585.92 | 2299.36 | 52885.28 | 67049.34 | 47918.66 | 41.68% | On track
Aurora | W1 · Civil works | BOQ-1.1 · Foundations | A1.1.2 · Blinding | 124339 | 83307.13 | 78333.57 | 78333.57 | 0 | 78333.57 | 86639.42 | 37699.58 | 30.32% | On track
Aurora | W1 · Civil works | BOQ-1.1 · Foundations | A1.1.3 · Rebar | 133710 | 106968 | 106968 | 20056.5 | 86911.5 | 106968 | 106968 | 26742 | 20% | On track
Aurora | W1 · Civil works | BOQ-1.2 · Structural | A1.2.1 · Columns | 143081 | 133065.33 | 52939.97 | 52939.97 | 0 | 52939.97 | 127742.72 | 15338.28 | 10.72% | On track
Aurora | W1 · Civil works | BOQ-1.2 · Structural | A1.2.2 · Slabs | 152452 | 85373.12 | 82324.08 | 82324.08 | 0 | 82324.08 | 91349.24 | 61102.76 | 40.08% | On track
Aurora | W2 · MEP | BOQ-2.1 · Electrical | A2.1.1 · Panels | 161823 | 111657.87 | 111657.87 | 111657.87 | 0 | 111657.87 | 115007.61 | 46815.39 | 28.93% | On track
Aurora | W2 · MEP | BOQ-2.1 · Electrical | A2.1.2 · Cabling | 171194 | 140379.08 | 140379.08 | 54782.08 | 85597 | 140379.08 | 138975.29 | 32218.71 | 18.82% | On track
Aurora | W2 · MEP | BOQ-2.2 · HVAC | A2.2.1 · Ducting | 180565 | 171536.75 | 81254.25 | 81254.25 | 0 | 81254.25 | 162959.91 | 17605.09 | 9.75% | On track
Aurora | W2 · MEP | BOQ-2.2 · HVAC | A2.2.2 · AHU | 189936 | 110162.88 | 110162.88 | 110162.88 | 0 | 110162.88 | 116772.65 | 73163.35 | 38.52% | On track
Dune | W1 · Earthworks | BOQ-1.1 · Site prep | A1.1.1 · Clearing | 199307 | 141507.97 | 141507.97 | 51819.82 | 89688.15 | 141507.97 | 144338.13 | 54968.87 | 27.58% | On track
Dune | W1 · Earthworks | BOQ-1.1 · Site prep | A1.1.2 · Grading | 208678 | 175289.52 | 75124.08 | 75124.08 | 0 | 75124.08 | 171783.73 | 36894.27 | 17.68% | On track
Dune | W2 · Civil works | BOQ-2.1 · Foundations | A2.1.1 · Excavation | 218049 | 211507.53 | 115565.97 | 115565.97 | 0 | 115565.97 | 230543.21 | -12494.21 | -5.73% | Over
Dune | W2 · Civil works | BOQ-2.1 · Foundations | A2.1.2 · Rebar | 227420 | 136452 | 136452 | 45484 | 90968 | 136452 | 143274.6 | 84145.4 | 37% | On track
Dune | W2 · Civil works | BOQ-2.2 · Walls | A2.2.1 · Blockwork | 236791 | 172857.43 | 172857.43 | 101820.13 | 71037.3 | 172857.43 | 174586 | 62205 | 26.27% | On track
Delta | W1 · Structural | BOQ-1.1 · Steel frame | A1.1.1 · Fabrication | 246162 | 211699.32 | 108311.28 | 108311.28 | 0 | 108311.28 | 205348.34 | 40813.66 | 16.58% | On track
Delta | W1 · Structural | BOQ-1.1 · Steel frame | A1.1.2 · Erection | 255533 | 252977.67 | 155875.13 | 35774.62 | 120100.51 | 155875.13 | 273215.88 | -17682.88 | -6.92% | Over
Delta | W2 · Finishing | BOQ-2.1 · Flooring | A2.1.1 · Screed | 44904 | 27840.48 | 27840.48 | 16614.48 | 11226 | 27840.48 | 28954.1 | 15949.9 | 35.52% | On track
Delta | W2 · Finishing | BOQ-2.1 · Flooring | A2.1.2 · Tiling | 54275 | 40706.25 | 18996.25 | 18996.25 | 0 | 18996.25 | 40706.25 | 13568.75 | 25% | On track
Mesa | W1 · Utilities | BOQ-1.1 · Water | A1.1.1 · Piping | 63646 | 56008.48 | 33095.92 | 33095.92 | 0 | 33095.92 | 53768.14 | 9877.86 | 15.52% | On track
Mesa | W1 · Utilities | BOQ-1.1 · Water | A1.1.2 · Pumps | 73017 | 37238.67 | 37238.67 | 22635.27 | 14603.4 | 37238.67 | 39845.38 | 33171.62 | 45.43% | On track
Mesa | W1 · Utilities | BOQ-1.2 · Drainage | A1.2.1 · Trenching | 82388 | 52728.32 | 52728.32 | 44489.52 | 8238.8 | 52728.32 | 54310.17 | 28077.83 | 34.08% | On track
Mesa | W1 · Utilities | BOQ-1.2 · Drainage | A1.2.2 · Backfill | 91759 | 70654.43 | 39456.37 | 39456.37 | 0 | 39456.37 | 69947.89 | 21811.11 | 23.77% | On track

## Summary_by_Project
DEMO · Portfolio roll-up by project — same logic, higher level
Project | Activities | Budget | Committed | Invoiced | Forecast | Variance | Committed % | Invoiced % | Status
Aurora | 9 | 1372068 | 1004532.88 | 642097.12 | 1013464.18 | 358603.82 | 73.21% | 46.8% | On track
Dune | 5 | 1090245 | 837614.45 | 389814 | 864525.67 | 225719.33 | 76.83% | 35.75% | On track
Delta | 4 | 600874 | 533223.72 | 179696.63 | 548224.57 | 52649.43 | 88.74% | 29.91% | On track
Mesa | 4 | 310810 | 216629.9 | 139677.08 | 217871.58 | 92938.42 | 69.7% | 44.94% | On track

## Daily_Signals
DEMO · Daily signals — what PMs, Procurement, and Finance see before the day starts
Priority | Signal | Project · WBS · Activity | Variance | Owner | Age | Action
P1 | Forecast > Budget > 10% | Aurora · W1 · A1.1.3 Rebar | -14% | PM · Aurora | 1d | Review BOQ qty; possible scope slip
P1 | Committed jumped 22% d/d | Dune · W2 · A2.1.1 Excavation | +22% | Procurement | 0d | Investigate PO-10437 charge basis
P2 | Invoiced lagging receipts | Delta · W1 · A1.1.2 Erection | -12% | AP | 3d | Raise GRN retro; chase invoice
P2 | Accrual > threshold | Mesa · W1 · A1.2.1 Trenching | +18% | Finance Ops | 2d | Validate month-end accrual basis
P3 | Low committed · late start | Aurora · W2 · A2.2.2 AHU | -4% | PM · Aurora | 4d | Baseline schedule slip — confirm
P3 | Tax base drift > 2% | Delta · W2 · A2.1.1 Screed | -3% | Finance Ops | 1d | Recompute tax base; rule v14 check

## Traceability
Activity cost · traceability
A posted value at the Activity level traces back to the originating PO line and its allocation.
Step | Source | Value | Note
1 | PR raised | PR-7341 | Tied to BOQ-1.1.3 Rebar · Aurora
2 | PO committed | PO-10421 · line 2 | Vendor: Gulf Metalworks
3 | Header delta allocated | -2% × (line/Σ) = -486 SAR | Rule 01 · allocation (catalog v14)
4 | Tax base | line_value − disc + chg
5 | Tax (15%) | 3,572 SAR | KSA standard rate
6 | Line net | 27,386 SAR | Posted to Activity A1.1.3 · Aurora
7 | Committed roll-up | 27,386 SAR | Appears in Aurora → W1 → BOQ-1.1 → A1.1.3
8 | Invoiced (status) | pending · 3-way match | Awaiting receipt qty reconciliation