## README
Procurement Truth Model — Demo Workbook
PORTFOLIO DEMO · ILLUSTRATIVE SAMPLE · Hamza Fayz Fathy
Purpose
Shows how header-level discounts, charges, and tax base are governed down to the line and reconciled against receipts and invoices — so WBS-level cost is trustworthy.
Sheets
PO_Summary · PO_Lines · Allocation_Rule · Reconciliation_WBS · Exceptions
What this demo proves
1) Header deltas (discount + charge) are allocated to lines by a governed rule with traceable formula. 2) Tax base follows the allocated line, not the raw line value. 3) Committed / received / invoiced roll up cleanly at WBS level. 4) Exceptions are routed to the role that can act — severity scoped, not generic.
Integrity checks
• Σ line_value per PO = header sum · verified on generation. • Σ discount_allocated per PO ≈ header_discount_pct × Σ line_value. • Σ charge_allocated per PO = header_charge. • line_net = tax_base + tax_amount · by row.
Context for the portfolio
Supports the flagship case 'D365 Project Cost Control Engine' and Tier-2 'Procurement Truth Model'. Not production data — synthetic and anonymized.
Not for production use. Data is synthetic. Structure, logic, and relationships are realistic for illustration.

## PO_Summary
DEMO · Procurement truth — PO header summary after governed allocation
PO No. | Project | Vendor | Lines | Header · discount % | Header · charge (SAR) | Sum line value | Allocated discount | Allocated charges | Tax base | Tax (15%) | PO net (SAR) | Status | Currency
PO-10401 | PRJ-AUR | Gulf Metalworks | 3 | 2% | 0 | 22740 | -454.8 | 0 | 22285.2 | 3342.78 | 25627.98 | Open | SAR
PO-10402 | PRJ-AUR | Delta Electrical Co. | 4 | 3% | 450 | 19800 | -594 | 450 | 19656 | 2948.39 | 22604.39 | Open | SAR
PO-10403 | PRJ-AUR | Prime Fabrication | 5 | 5% | 800 | 30040 | -1502 | 800 | 29338 | 4400.7 | 33738.7 | Open | SAR
PO-10404 | PRJ-AUR | Arcadia Industrial | 3 | 0% | 1200 | 9120 | 0 | 1200 | 10320 | 1548 | 11868 | In-progress | SAR
PO-10405 | PRJ-AUR | Sable Supplies | 4 | 2% | 0 | 26320 | -526.4 | 0 | 25793.6 | 3869.04 | 29662.64 | Open | SAR
PO-10406 | PRJ-DUN | Northbay Trading | 5 | 3% | 0 | 41130 | -1233.9 | 0 | 39896.1 | 5984.41 | 45880.51 | Open | SAR
PO-10407 | PRJ-DUN | Gulf Metalworks | 3 | 5% | 450 | 22740 | -1137 | 450 | 22053 | 3307.95 | 25360.95 | Open | SAR
PO-10408 | PRJ-DUN | Delta Electrical Co. | 4 | 0% | 800 | 19800 | 0 | 800 | 20600 | 3090 | 23690 | Open | SAR
PO-10409 | PRJ-DUN | Prime Fabrication | 5 | 2% | 1200 | 30040 | -600.8 | 1200 | 30639.2 | 4595.88 | 35235.08 | Open | SAR
PO-10410 | PRJ-DUN | Arcadia Industrial | 3 | 3% | 0 | 9120 | -273.6 | 0 | 8846.4 | 1326.96 | 10173.36 | In-progress | SAR
PO-10411 | PRJ-DLT | Sable Supplies | 4 | 5% | 0 | 26320 | -1316 | 0 | 25004 | 3750.6 | 28754.6 | Open | SAR
PO-10412 | PRJ-DLT | Northbay Trading | 5 | 0% | 450 | 41130 | 0 | 450 | 41580 | 6237 | 47817 | Open | SAR
PO-10413 | PRJ-DLT | Gulf Metalworks | 3 | 2% | 800 | 22740 | -454.8 | 800.01 | 23085.21 | 3462.78 | 26547.99 | Open | SAR
PO-10414 | PRJ-DLT | Delta Electrical Co. | 4 | 3% | 1200 | 19800 | -594 | 1200 | 20406 | 3060.9 | 23466.9 | In-progress | SAR
PO-10415 | PRJ-DLT | Prime Fabrication | 5 | 5% | 0 | 30040 | -1502 | 0 | 28538 | 4280.7 | 32818.7 | Open | SAR
PO-10416 | PRJ-MSA | Arcadia Industrial | 3 | 0% | 0 | 9120 | 0 | 0 | 9120 | 1368 | 10488 | Open | SAR
PO-10417 | PRJ-MSA | Sable Supplies | 4 | 2% | 450 | 26320 | -526.4 | 450 | 26243.6 | 3936.53 | 30180.13 | Open | SAR
PO-10418 | PRJ-MSA | Northbay Trading | 5 | 3% | 800 | 41130 | -1233.9 | 800 | 40696.1 | 6104.41 | 46800.51 | Open | SAR
PO-10419 | PRJ-MSA | Gulf Metalworks | 3 | 5% | 1200 | 22740 | -1137 | 1200 | 22803 | 3420.45 | 26223.45 | In-progress | SAR
PO-10420 | PRJ-MSA | Delta Electrical Co. | 4 | 0% | 0 | 19800 | 0 | 0 | 19800 | 2970 | 22770 | Open | SAR

## PO_Lines
DEMO · PO lines — traceable line-level cost after allocation (header charges & tax base mapped)
PO No. | Line | Project | WBS | Item | Qty | Unit price | Line value | Disc. allocated | Charge allocated | Tax base | Tax (15%) | Line net (SAR) | Status
PO-10401 | 1 | PRJ-AUR | PRJ-AUR-W2.1 | Insulation roll · 50mm | 12 | 120 | 1440 | -28.8 | 0 | 1411.2 | 211.68 | 1622.88 | Committed
PO-10401 | 2 | PRJ-AUR | PRJ-AUR-W3.2 | Steel rebar · 12mm | 20 | 340 | 6800 | -136 | 0 | 6664 | 999.6 | 7663.6 | Received
PO-10401 | 3 | PRJ-AUR | PRJ-AUR-W4.3 | Cable · XLPE 16mm² | 25 | 580 | 14500 | -290 | 0 | 14210 | 2131.5 | 16341.5 | Invoiced
PO-10402 | 1 | PRJ-AUR | PRJ-AUR-W3.2 | Steel rebar · 12mm | 20 | 120 | 2400 | -72 | 112.5 | 2440.5 | 366.07 | 2806.57 | Invoiced
PO-10402 | 2 | PRJ-AUR | PRJ-AUR-W4.3 | Cable · XLPE 16mm² | 25 | 340 | 8500 | -255 | 112.5 | 8357.5 | 1253.62 | 9611.12 | Closed
PO-10402 | 3 | PRJ-AUR | PRJ-AUR-W1.1 | Formwork plywood | 5 | 580 | 2900 | -87 | 112.5 | 2925.5 | 438.82 | 3364.32 | Committed
PO-10402 | 4 | PRJ-AUR | PRJ-AUR-W2.2 | Scaffold frame | 8 | 750 | 6000 | -180 | 112.5 | 5932.5 | 889.88 | 6822.38 | Received
PO-10403 | 1 | PRJ-AUR | PRJ-AUR-W4.3 | Cable · XLPE 16mm² | 25 | 120 | 3000 | -150 | 160 | 3010 | 451.5 | 3461.5 | Invoiced
PO-10403 | 2 | PRJ-AUR | PRJ-AUR-W1.1 | Formwork plywood | 5 | 340 | 1700 | -85 | 160 | 1775 | 266.25 | 2041.25 | Invoiced
PO-10403 | 3 | PRJ-AUR | PRJ-AUR-W2.2 | Scaffold frame | 8 | 580 | 4640 | -232 | 160 | 4568 | 685.2 | 5253.2 | Closed
PO-10403 | 4 | PRJ-AUR | PRJ-AUR-W3.3 | Breaker · 3P 63A | 10 | 750 | 7500 | -375 | 160 | 7285 | 1092.75 | 8377.75 | Committed
PO-10403 | 5 | PRJ-AUR | PRJ-AUR-W4.1 | Pump · centrifugal 5HP | 12 | 1100 | 13200 | -660 | 160 | 12700 | 1905 | 14605 | Received
PO-10404 | 1 | PRJ-AUR | PRJ-AUR-W1.1 | Formwork plywood | 5 | 120 | 600 | 0 | 400 | 1000 | 150 | 1150 | Invoiced
PO-10404 | 2 | PRJ-AUR | PRJ-AUR-W2.2 | Scaffold frame | 8 | 340 | 2720 | 0 | 400 | 3120 | 468 | 3588 | Invoiced
PO-10404 | 3 | PRJ-AUR | PRJ-AUR-W3.3 | Breaker · 3P 63A | 10 | 580 | 5800 | 0 | 400 | 6200 | 930 | 7130 | Closed
PO-10405 | 1 | PRJ-AUR | PRJ-AUR-W2.2 | Scaffold frame | 8 | 120 | 960 | -19.2 | 0 | 940.8 | 141.12 | 1081.92 | Committed
PO-10405 | 2 | PRJ-AUR | PRJ-AUR-W3.3 | Breaker · 3P 63A | 10 | 340 | 3400 | -68 | 0 | 3332 | 499.8 | 3831.8 | Received
PO-10405 | 3 | PRJ-AUR | PRJ-AUR-W4.1 | Pump · centrifugal 5HP | 12 | 580 | 6960 | -139.2 | 0 | 6820.8 | 1023.12 | 7843.92 | Invoiced
PO-10405 | 4 | PRJ-AUR | PRJ-AUR-W1.2 | Insulation roll · 50mm | 20 | 750 | 15000 | -300 | 0 | 14700 | 2205 | 16905 | Invoiced
PO-10406 | 1 | PRJ-DUN | PRJ-DUN-W3.3 | Breaker · 3P 63A | 10 | 120 | 1200 | -36 | 0 | 1164 | 174.6 | 1338.6 | Closed
PO-10406 | 2 | PRJ-DUN | PRJ-DUN-W4.1 | Pump · centrifugal 5HP | 12 | 340 | 4080 | -122.4 | 0 | 3957.6 | 593.64 | 4551.24 | Committed
PO-10406 | 3 | PRJ-DUN | PRJ-DUN-W1.2 | Insulation roll · 50mm | 20 | 580 | 11600 | -348 | 0 | 11252 | 1687.8 | 12939.8 | Received
PO-10406 | 4 | PRJ-DUN | PRJ-DUN-W2.3 | Steel rebar · 12mm | 25 | 750 | 18750 | -562.5 | 0 | 18187.5 | 2728.12 | 20915.62 | Invoiced
PO-10406 | 5 | PRJ-DUN | PRJ-DUN-W3.1 | Cable · XLPE 16mm² | 5 | 1100 | 5500 | -165 | 0 | 5335 | 800.25 | 6135.25 | Invoiced
PO-10407 | 1 | PRJ-DUN | PRJ-DUN-W4.1 | Pump · centrifugal 5HP | 12 | 120 | 1440 | -72 | 150 | 1518 | 227.7 | 1745.7 | Closed
PO-10407 | 2 | PRJ-DUN | PRJ-DUN-W1.2 | Insulation roll · 50mm | 20 | 340 | 6800 | -340 | 150 | 6610 | 991.5 | 7601.5 | Committed
PO-10407 | 3 | PRJ-DUN | PRJ-DUN-W2.3 | Steel rebar · 12mm | 25 | 580 | 14500 | -725 | 150 | 13925 | 2088.75 | 16013.75 | Received
PO-10408 | 1 | PRJ-DUN | PRJ-DUN-W1.2 | Insulation roll · 50mm | 20 | 120 | 2400 | 0 | 200 | 2600 | 390 | 2990 | Invoiced
PO-10408 | 2 | PRJ-DUN | PRJ-DUN-W2.3 | Steel rebar · 12mm | 25 | 340 | 8500 | 0 | 200 | 8700 | 1305 | 10005 | Invoiced
PO-10408 | 3 | PRJ-DUN | PRJ-DUN-W3.1 | Cable · XLPE 16mm² | 5 | 580 | 2900 | 0 | 200 | 3100 | 465 | 3565 | Closed
PO-10408 | 4 | PRJ-DUN | PRJ-DUN-W4.2 | Formwork plywood | 8 | 750 | 6000 | 0 | 200 | 6200 | 930 | 7130 | Committed
PO-10409 | 1 | PRJ-DUN | PRJ-DUN-W2.3 | Steel rebar · 12mm | 25 | 120 | 3000 | -60 | 240 | 3180 | 477 | 3657 | Received
PO-10409 | 2 | PRJ-DUN | PRJ-DUN-W3.1 | Cable · XLPE 16mm² | 5 | 340 | 1700 | -34 | 240 | 1906 | 285.9 | 2191.9 | Invoiced
PO-10409 | 3 | PRJ-DUN | PRJ-DUN-W4.2 | Formwork plywood | 8 | 580 | 4640 | -92.8 | 240 | 4787.2 | 718.08 | 5505.28 | Invoiced
PO-10409 | 4 | PRJ-DUN | PRJ-DUN-W1.3 | Scaffold frame | 10 | 750 | 7500 | -150 | 240 | 7590 | 1138.5 | 8728.5 | Closed
PO-10409 | 5 | PRJ-DUN | PRJ-DUN-W2.1 | Breaker · 3P 63A | 12 | 1100 | 13200 | -264 | 240 | 13176 | 1976.4 | 15152.4 | Committed
PO-10410 | 1 | PRJ-DUN | PRJ-DUN-W3.1 | Cable · XLPE 16mm² | 5 | 120 | 600 | -18 | 0 | 582 | 87.3 | 669.3 | Received
PO-10410 | 2 | PRJ-DUN | PRJ-DUN-W4.2 | Formwork plywood | 8 | 340 | 2720 | -81.6 | 0 | 2638.4 | 395.76 | 3034.16 | Invoiced
PO-10410 | 3 | PRJ-DUN | PRJ-DUN-W1.3 | Scaffold frame | 10 | 580 | 5800 | -174 | 0 | 5626 | 843.9 | 6469.9 | Invoiced
PO-10411 | 1 | PRJ-DLT | PRJ-DLT-W4.2 | Formwork plywood | 8 | 120 | 960 | -48 | 0 | 912 | 136.8 | 1048.8 | Closed
PO-10411 | 2 | PRJ-DLT | PRJ-DLT-W1.3 | Scaffold frame | 10 | 340 | 3400 | -170 | 0 | 3230 | 484.5 | 3714.5 | Committed
PO-10411 | 3 | PRJ-DLT | PRJ-DLT-W2.1 | Breaker · 3P 63A | 12 | 580 | 6960 | -348 | 0 | 6612 | 991.8 | 7603.8 | Received
PO-10411 | 4 | PRJ-DLT | PRJ-DLT-W3.2 | Pump · centrifugal 5HP | 20 | 750 | 15000 | -750 | 0 | 14250 | 2137.5 | 16387.5 | Invoiced
PO-10412 | 1 | PRJ-DLT | PRJ-DLT-W1.3 | Scaffold frame | 10 | 120 | 1200 | 0 | 90 | 1290 | 193.5 | 1483.5 | Invoiced
PO-10412 | 2 | PRJ-DLT | PRJ-DLT-W2.1 | Breaker · 3P 63A | 12 | 340 | 4080 | 0 | 90 | 4170 | 625.5 | 4795.5 | Closed
PO-10412 | 3 | PRJ-DLT | PRJ-DLT-W3.2 | Pump · centrifugal 5HP | 20 | 580 | 11600 | 0 | 90 | 11690 | 1753.5 | 13443.5 | Committed
PO-10412 | 4 | PRJ-DLT | PRJ-DLT-W4.3 | Insulation roll · 50mm | 25 | 750 | 18750 | 0 | 90 | 18840 | 2826 | 21666 | Received
PO-10412 | 5 | PRJ-DLT | PRJ-DLT-W1.1 | Steel rebar · 12mm | 5 | 1100 | 5500 | 0 | 90 | 5590 | 838.5 | 6428.5 | Invoiced
PO-10413 | 1 | PRJ-DLT | PRJ-DLT-W2.1 | Breaker · 3P 63A | 12 | 120 | 1440 | -28.8 | 266.67 | 1677.87 | 251.68 | 1929.55 | Invoiced
PO-10413 | 2 | PRJ-DLT | PRJ-DLT-W3.2 | Pump · centrifugal 5HP | 20 | 340 | 6800 | -136 | 266.67 | 6930.67 | 1039.6 | 7970.27 | Closed
PO-10413 | 3 | PRJ-DLT | PRJ-DLT-W4.3 | Insulation roll · 50mm | 25 | 580 | 14500 | -290 | 266.67 | 14476.67 | 2171.5 | 16648.17 | Committed
PO-10414 | 1 | PRJ-DLT | PRJ-DLT-W3.2 | Pump · centrifugal 5HP | 20 | 120 | 2400 | -72 | 300 | 2628 | 394.2 | 3022.2 | Received
PO-10414 | 2 | PRJ-DLT | PRJ-DLT-W4.3 | Insulation roll · 50mm | 25 | 340 | 8500 | -255 | 300 | 8545 | 1281.75 | 9826.75 | Invoiced
PO-10414 | 3 | PRJ-DLT | PRJ-DLT-W1.1 | Steel rebar · 12mm | 5 | 580 | 2900 | -87 | 300 | 3113 | 466.95 | 3579.95 | Invoiced
PO-10414 | 4 | PRJ-DLT | PRJ-DLT-W2.2 | Cable · XLPE 16mm² | 8 | 750 | 6000 | -180 | 300 | 6120 | 918 | 7038 | Closed
PO-10415 | 1 | PRJ-DLT | PRJ-DLT-W4.3 | Insulation roll · 50mm | 25 | 120 | 3000 | -150 | 0 | 2850 | 427.5 | 3277.5 | Committed
PO-10415 | 2 | PRJ-DLT | PRJ-DLT-W1.1 | Steel rebar · 12mm | 5 | 340 | 1700 | -85 | 0 | 1615 | 242.25 | 1857.25 | Received
PO-10415 | 3 | PRJ-DLT | PRJ-DLT-W2.2 | Cable · XLPE 16mm² | 8 | 580 | 4640 | -232 | 0 | 4408 | 661.2 | 5069.2 | Invoiced
PO-10415 | 4 | PRJ-DLT | PRJ-DLT-W3.3 | Formwork plywood | 10 | 750 | 7500 | -375 | 0 | 7125 | 1068.75 | 8193.75 | Invoiced
PO-10415 | 5 | PRJ-DLT | PRJ-DLT-W4.1 | Scaffold frame | 12 | 1100 | 13200 | -660 | 0 | 12540 | 1881 | 14421 | Closed
PO-10416 | 1 | PRJ-MSA | PRJ-MSA-W1.1 | Steel rebar · 12mm | 5 | 120 | 600 | 0 | 0 | 600 | 90 | 690 | Committed
PO-10416 | 2 | PRJ-MSA | PRJ-MSA-W2.2 | Cable · XLPE 16mm² | 8 | 340 | 2720 | 0 | 0 | 2720 | 408 | 3128 | Received
PO-10416 | 3 | PRJ-MSA | PRJ-MSA-W3.3 | Formwork plywood | 10 | 580 | 5800 | 0 | 0 | 5800 | 870 | 6670 | Invoiced
PO-10417 | 1 | PRJ-MSA | PRJ-MSA-W2.2 | Cable · XLPE 16mm² | 8 | 120 | 960 | -19.2 | 112.5 | 1053.3 | 157.99 | 1211.29 | Invoiced
PO-10417 | 2 | PRJ-MSA | PRJ-MSA-W3.3 | Formwork plywood | 10 | 340 | 3400 | -68 | 112.5 | 3444.5 | 516.67 | 3961.17 | Closed
PO-10417 | 3 | PRJ-MSA | PRJ-MSA-W4.1 | Scaffold frame | 12 | 580 | 6960 | -139.2 | 112.5 | 6933.3 | 1039.99 | 7973.29 | Committed
PO-10417 | 4 | PRJ-MSA | PRJ-MSA-W1.2 | Breaker · 3P 63A | 20 | 750 | 15000 | -300 | 112.5 | 14812.5 | 2221.88 | 17034.38 | Received
PO-10418 | 1 | PRJ-MSA | PRJ-MSA-W3.3 | Formwork plywood | 10 | 120 | 1200 | -36 | 160 | 1324 | 198.6 | 1522.6 | Invoiced
PO-10418 | 2 | PRJ-MSA | PRJ-MSA-W4.1 | Scaffold frame | 12 | 340 | 4080 | -122.4 | 160 | 4117.6 | 617.64 | 4735.24 | Invoiced
PO-10418 | 3 | PRJ-MSA | PRJ-MSA-W1.2 | Breaker · 3P 63A | 20 | 580 | 11600 | -348 | 160 | 11412 | 1711.8 | 13123.8 | Closed
PO-10418 | 4 | PRJ-MSA | PRJ-MSA-W2.3 | Pump · centrifugal 5HP | 25 | 750 | 18750 | -562.5 | 160 | 18347.5 | 2752.12 | 21099.62 | Committed
PO-10418 | 5 | PRJ-MSA | PRJ-MSA-W3.1 | Insulation roll · 50mm | 5 | 1100 | 5500 | -165 | 160 | 5495 | 824.25 | 6319.25 | Received
PO-10419 | 1 | PRJ-MSA | PRJ-MSA-W4.1 | Scaffold frame | 12 | 120 | 1440 | -72 | 400 | 1768 | 265.2 | 2033.2 | Invoiced
PO-10419 | 2 | PRJ-MSA | PRJ-MSA-W1.2 | Breaker · 3P 63A | 20 | 340 | 6800 | -340 | 400 | 6860 | 1029 | 7889 | Invoiced
PO-10419 | 3 | PRJ-MSA | PRJ-MSA-W2.3 | Pump · centrifugal 5HP | 25 | 580 | 14500 | -725 | 400 | 14175 | 2126.25 | 16301.25 | Closed
PO-10420 | 1 | PRJ-MSA | PRJ-MSA-W1.2 | Breaker · 3P 63A | 20 | 120 | 2400 | 0 | 0 | 2400 | 360 | 2760 | Committed
PO-10420 | 2 | PRJ-MSA | PRJ-MSA-W2.3 | Pump · centrifugal 5HP | 25 | 340 | 8500 | 0 | 0 | 8500 | 1275 | 9775 | Received
PO-10420 | 3 | PRJ-MSA | PRJ-MSA-W3.1 | Insulation roll · 50mm | 5 | 580 | 2900 | 0 | 0 | 2900 | 435 | 3335 | Invoiced
PO-10420 | 4 | PRJ-MSA | PRJ-MSA-W4.2 | Steel rebar · 12mm | 8 | 750 | 6000 | 0 | 0 | 6000 | 900 | 6900 | Invoiced

## Allocation_Rule
Allocation rule — header delta → line cost
Governed. Traceable back to the originating document line.
# | Rule | Formula | Notes
01 | Header discount | -discount × (line_value / Σ line_values) | Header-level % rebate distributed to lines in proportion to line value.
02 | Header charge | header_charge / n_lines | Flat header charge spread equally across PO lines (or by governed alternative basis).
03 | Tax base | line_value − discount_allocated + charge_allocated | Tax base follows the allocated line — not the raw line_value.
04 | Tax amount | tax_base × 15% | KSA VAT standard rate. Exemptions handled via rule catalog (not included in sample).
05 | Line net | tax_base + tax_amount | Final governed line-level cost — what downstream WBS / Activity reports read.

## Reconciliation_WBS
DEMO · 3-way reconciliation by WBS — committed (PO) vs received (GRN) vs invoiced (AP)
Project | WBS | Committed (Σ PO) | Received (Σ GRN) | Invoiced (Σ AP) | Variance · Committed − Invoiced | Variance % | Flag
PRJ-AUR | PRJ-AUR-W1.1 | 6555.57 | 3191.25 | 3191.25 | 3364.32 | 51.32% | Action
PRJ-AUR | PRJ-AUR-W1.2 | 16905 | 16905 | 16905 | 0 | 0% | On track
PRJ-AUR | PRJ-AUR-W2.1 | 1622.88 | 0 | 0 | 1622.88 | 100% | Action
PRJ-AUR | PRJ-AUR-W2.2 | 16745.5 | 15663.58 | 8841.2 | 7904.3 | 47.2% | Watch
PRJ-AUR | PRJ-AUR-W3.2 | 10470.17 | 10470.17 | 2806.57 | 7663.6 | 73.19% | Action
PRJ-AUR | PRJ-AUR-W3.3 | 19339.55 | 10961.8 | 7130 | 12209.55 | 63.13% | Action
PRJ-AUR | PRJ-AUR-W4.1 | 22448.92 | 22448.92 | 7843.92 | 14605 | 65.06% | Action
PRJ-AUR | PRJ-AUR-W4.3 | 29414.12 | 29414.12 | 29414.12 | 0 | 0% | On track
PRJ-DLT | PRJ-DLT-W1.1 | 11865.7 | 11865.7 | 10008.45 | 1857.25 | 15.65% | Watch
PRJ-DLT | PRJ-DLT-W1.3 | 5198 | 1483.5 | 1483.5 | 3714.5 | 71.46% | Action
PRJ-DLT | PRJ-DLT-W2.1 | 14328.85 | 14328.85 | 6725.05 | 7603.8 | 53.07% | Action
PRJ-DLT | PRJ-DLT-W2.2 | 12107.2 | 12107.2 | 12107.2 | 0 | 0% | On track
PRJ-DLT | PRJ-DLT-W3.2 | 40823.47 | 27379.97 | 24357.77 | 16465.7 | 40.33% | Watch
PRJ-DLT | PRJ-DLT-W3.3 | 8193.75 | 8193.75 | 8193.75 | 0 | 0% | On track
PRJ-DLT | PRJ-DLT-W4.1 | 14421 | 14421 | 14421 | 0 | 0% | On track
PRJ-DLT | PRJ-DLT-W4.2 | 1048.8 | 1048.8 | 1048.8 | 0 | 0% | On track
PRJ-DLT | PRJ-DLT-W4.3 | 51418.42 | 31492.75 | 9826.75 | 41591.67 | 80.89% | Action
PRJ-DUN | PRJ-DUN-W1.2 | 23531.3 | 15929.8 | 2990 | 20541.3 | 87.29% | Action
PRJ-DUN | PRJ-DUN-W1.3 | 15198.4 | 15198.4 | 15198.4 | 0 | 0% | On track
PRJ-DUN | PRJ-DUN-W2.1 | 15152.4 | 0 | 0 | 15152.4 | 100% | Action
PRJ-DUN | PRJ-DUN-W2.3 | 50591.37 | 50591.37 | 30920.62 | 19670.75 | 38.88% | Watch
PRJ-DUN | PRJ-DUN-W3.1 | 12561.45 | 12561.45 | 11892.15 | 669.3 | 5.328% | On track
PRJ-DUN | PRJ-DUN-W3.3 | 1338.6 | 1338.6 | 1338.6 | 0 | 0% | On track
PRJ-DUN | PRJ-DUN-W4.1 | 6296.94 | 1745.7 | 1745.7 | 4551.24 | 72.28% | Action
PRJ-DUN | PRJ-DUN-W4.2 | 15669.44 | 8539.44 | 8539.44 | 7130 | 45.5% | Watch
PRJ-MSA | PRJ-MSA-W1.1 | 690 | 0 | 0 | 690 | 100% | Action
PRJ-MSA | PRJ-MSA-W1.2 | 40807.18 | 38047.18 | 21012.8 | 19794.38 | 48.51% | Watch
PRJ-MSA | PRJ-MSA-W2.2 | 4339.29 | 4339.29 | 1211.29 | 3128 | 72.09% | Action
PRJ-MSA | PRJ-MSA-W2.3 | 47175.87 | 26076.25 | 16301.25 | 30874.62 | 65.45% | Action
PRJ-MSA | PRJ-MSA-W3.1 | 9654.25 | 9654.25 | 3335 | 6319.25 | 65.46% | Action
PRJ-MSA | PRJ-MSA-W3.3 | 12153.77 | 12153.77 | 12153.77 | 0 | 0% | On track
PRJ-MSA | PRJ-MSA-W4.1 | 14741.73 | 6768.44 | 6768.44 | 7973.29 | 54.09% | Action
PRJ-MSA | PRJ-MSA-W4.2 | 6900 | 6900 | 6900 | 0 | 0% | On track

## Exceptions
DEMO · Procurement exception queue — routed by rule, scoped by owner
Exception ID | Severity | Rule | PO / Line | Project · WBS | Owner | Age (days) | Next action
EX-10421-L2 | High | Tax base mismatch | PO-10421 · 2 | PRJ-AUR · W2.1 | Finance Ops | 4 | Reclass tax base → line, post correction
EX-10437-L1 | Medium | Header charge > 5% of value | PO-10437 · 1 | PRJ-DUN · W1.3 | Procurement | 2 | Validate charge with vendor; confirm basis
EX-10444-* | Medium | Receipt qty > PO qty | PO-10444 · all | PRJ-DLT · W4.2 | Warehouse | 1 | Quarantine surplus; raise variance ticket
EX-10458-L3 | Low | Invoice posted, no GRN | PO-10458 · 3 | PRJ-MSA · W3.1 | AP | 3 | Raise GRN retro; confirm receipt evidence
EX-10462-L1 | High | Discount > contract ceiling | PO-10462 · 1 | PRJ-AUR · W1.1 | Finance Ops | 5 | Review vendor agreement; escalate
EX-10470-* | Low | Header discount = 0 expected | PO-10470 · all | PRJ-DUN · W2.3 | Procurement | 1 | Confirm missing rebate; re-request from vendor
EX-10479-L2 | Medium | Line net ≠ tax_base + tax | PO-10479 · 2 | PRJ-DLT · W1.2 | Finance Ops | 0 | Recompute; suspected rounding